## Projects
MTEP06 Appendix A and B Projects - 11/06/06 DRAFT | [14 empty] | Preliminary Categorization |  |  | Project Info from Facility Table
App AB | PrjID | Prj_Rec_Date | Owner_PrjID | Region | Rep_Source | Proj_Name | Proj_Desc | State | State2 | State2_frac | Budget_Status | Reg_Approvals | Alternatives | Comments | Allocation Category | Share Status | Exclude FF1 | Expected ISD | Max Voltage | Min Voltage | Project Est_Cost | Facil Count | Plan_Status
A | 90 | 2005-07-11 | 69 | West | ALTW | Emery-Lime Crk 161kV, Ckt 2 | Emery - Lime Creek 161 ckt 2, Sum rate 326 | IA |  |  | Pending | Pending |  |  | Other | Excluded | Y | 2007-06-01 | 161 |  | 8000000 | 1 | Planned
A | 1204 | 2006-01-31 |  | West | ALTW | Adams-Rochester 161 kV line termination upgrade | Replace disconnect jumpers at Adams on Adams-Rochester 161 kV line | MN | [6 empty] | TBD | TBD |  | 2006-10-01 | 161 |  | 5000 | 1 | Planned
A | 1287 | 2006-08-24 | 11 | West | ALTW | Replace Salem xfmr with 448/448 MVA xfmr | Replace Salem xfmr with 448/448 MVA xfmr | IA | [6 empty] | TBD | TBD |  | 2011-06-01 | 345 | 161 | 5000000 | 1 | Planned
A | 1288 | 2006-08-24 | 10 | West | ALTW | Replace Hazleton #1 xfmr with a larger 335/335 MVA xfmr | Replace Hazleton #1 xfmr with a larger 335/335 MVA xfmr | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 345 | 161 | 3500000 | 1 | Planned
A | 1289 | 2006-08-24 | 11 | West | ALTW | 115 kV line from Marshalltown to Stoney Point will be rebuilt/upgraded between 2008 and 2011 | 115 kV line from Marshalltown to Stoney Point will be rebuilt/upgraded between 2008 and 2011 | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 115 |  | 3900000 | 3 | Planned
A | 1342 | 2006-10-06 | 3 | West | ALTW | Lewis Fields 161 kV substation which taps the SwampFX - Coggon 115 kV line | Build a new 161 kV substation Lewis Fields to be tapped to the 115 kV line Swamp Fox - Coggon at 5% distance via a new 161/115 kV transformer. Also build a new 161 kV line from Hiawatha to Lewis Fields | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 161 | 115 | 4550000 | 2 | Proposed
A | 1344 | 2006-10-06 | 5 | West | ALTW | Build a new 345 kV Beverly substation which taps the Arnold -Tiffin 345 kV line | Build a new 345 kV Beverly Tap substation and tapped to 345 kV line Arnold -Tiffin at 40% distance away from Arnold. Add a new 335 MVA 345/161 kV transformer and build a new 161 kV line connecting the new substation to Beverly 161 kV bus | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 345 | 161 | 4300000 | 2 | Planned
A | 1347 | 2006-10-06 | 8 | West | ALTW | Install two breakers at both ends of Liberty 161 kV bus | Install two breakers at both ends of Liberty 161 kV bus | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 161 |  | 300000 | 1 | Planned
A | 1348 | 2006-10-06 | 9 | West | ALTW | Upgrade terminal equipment for Prairie Creek - Marion 115 kV line. Rebuild 115 kV line Marion - Swamp Fox - Coggon | Upgrade terminal equipment for 115 kV line Prairie Creek - Marion so that new ratings become 198/198 MVA limited by conductor rating. Rebuild 115 kV line Marion - Swampfx7 - Coggon to the new rating as 198/198 MVA | IA | [6 empty] | BaseRel | Shared |  | 2011-06-01 | 115 |  | 5304167 | 2 | Planned
A | 1349 | 2006-10-06 | 15 | West | ALTW | Replace Dundee 161/115 kV transformer with new ratings as 112/112 MVA | Replace Dundee 161/115 kV transformer with new ratings as 112/112 MVA | IA | [6 empty] | Other | Not Shared |  | 2011-06-01 | 161 | 115 | 100000 | 1 | Planned
A | 77 | 2005-07-11 | 54 | Central | Ameren | Callaway-Franks 345 kV Line | Callaway - Franks 345 kV line - New 345 kV line | MO |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2006-12-01 | 345 |  | 29966200 | 1 | Under Construction
A | 143 | 2006-03-17 | 121 | Central | Ameren | Cahokia-Pinckneyville-1 230 kV | Cahokia - N. Coulterville section of Cahokia-Pinckneyville-1 230 kV - Increase ground clearance | IL |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 230 |  | 476700 | 1 | Planned
A | 144 | 2006-03-17 | 122 | Central | Ameren | Crab Orchard - Marion South 138 kV | Crab Orchard - Marion South 138 kV - Reconductor line | IL |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 2712300 | 1 | Planned
A | 149 | 2006-03-17 | 127 | Central | Ameren | Mason-Sioux-7 345 kV | Mason-Sioux-7 345 kV - Breaker addition at Mason | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 345 |  | 605900 | 1 | Planned
A | 153 | 2006-03-17 | 131 | Central | Ameren | Central-Watson-1 138 kV | CEE Tap - Watson section of Central-Watson-1 138 kV - Reconductor line | MO |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2008-06-01 | 138 |  | 311400 | 1 | Planned
A | 155 | 2006-03-17 | 133 | Central | Ameren | Joachim 345/138 kV | Joachim 345/138 kV - New Substation | MO |  |  | Budgeted | Not Required | A Dupo area 345/138 kV substation was briefly considered to relieve the Tyson transformers, but this option is considerably more expensive and less effective than the recommended Joachim option. |  | Other | Excluded | Y | 2008-06-01 | 345 | 138 | 12963300 | 1 | Planned
A | 707 | 2006-03-17 |  | Central | Ameren | Adair 161/69 kV Substation | Adair 161/69 kV Substation - Install 161 kV Breaker for Thomas Hill Line outage | MO |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-11-01 | 161 |  | 335900 | 1 | Under Construction
A | 708 | 2006-03-17 |  | Central | Ameren | Casey-Breed 345 kV | Casey-Breed 345 kV Line - Reconductor river crossing | IL |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 345 |  | 303900 | 1 | Planned
A | 711 | 2006-03-17 |  | Central | Ameren | Wood River-Gillespie 138 kV | Wood River-Gillespie 138 kV - Reconductor | IL |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 939500 | 1 | Planned
A | 712 | 2006-03-17 |  | Central | Ameren | Mason 345/138 kV Substation | Labadie-Mason-3 345 kV Terminal equipment replacement | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 345 |  | 184100 | 1 | Planned
A | 719 | 2006-03-17 |  | Central | Ameren | Labadie Plant | Labadie Plant - Replace 2-345 kV Breakers | MO |  |  | Budgeted | Not Required |  |  | TBD | TBD |  | 2008-06-01 | 345 |  | 1897100 | 1 | Planned
A | 856 | 2005-07-11 |  | Central | Ameren | Osage 138 kV Substation | Osage 138 kV Substation - Replace bus conductor in bus #1 and line to Eldon | MO | [6 empty] | Other | Not Shared |  | 2006-12-01 | 138 |  | 65000 | 1 | Under Construction
A | 857 | 2005-07-11 |  | Central | Ameren | Rush Island-Joachim 345 kV Line | Rush Island-Joachim 345 kV - Replace terminal equipment at Rush Island | MO | [6 empty] | TAP | Service |  | 2007-06-01 | 345 |  | 283200 | 1 | Planned
A | 858 | 2005-07-11 |  | Central | Ameren | Sioux-Huster-1 138 kV | Sioux-Huster-1 138 kV - Increase ground clearance on 6 miles of 795 kcmil ACSR | MO | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 1024500 | 1 | Planned
A | 859 | 2005-07-11 |  | Central | Ameren | Central-Watson-1 138 kV | Central-Watson-1 138 kV - Reconductor 5.1 miles 954 kcmil ACSR between Central and Twr. 55 | MO | [6 empty] | Other | Not Shared |  | 2008-06-01 | 138 |  | 1500300 | 1 | Planned
A | 1241 | 2006-03-17 |  | Central | Ameren | Mattoon, West Wind Farm Connection | Install 138 kV Breaker at Mattoon, West Substation to connect Wind Farm | IL | [6 empty] | TAP | Service |  | 2007-03-01 | 138 |  | 555400 | 1 | Planned
A | 875 | 2005-07-11 |  | Central | AmerenCILCO | Kickapoo 138/69 kV Substation | Kickapoo 138/69 kV Substation - Replace terminal equipment | IL | [6 empty] | Other | Not Shared |  | 2006-11-15 | 138 |  | 156700 | 1 | Under Construction
A | 876 | 2005-07-11 |  | Central | AmerenCILCO | Tazewell 345/138 kV Substation | Tazewell 345/138 kV Substation - Replace 2000 A terminal equipment with 3000 A on line to Powerton | IL | [6 empty] | Other | Not Shared |  | 2007-06-01 | 345 |  | 1042900 | 1 | Planned
A | 150 | 2006-03-17 |  | Central | AmerenIP | Prairie State Power Plant transmission outlet | Establish a new Prairie State 345 kV switchyard including a 6-position breaker and ½ bus arrangement to accommodate 2 generating units and 4-345 kV outlet lines with 9-345 kV circuit breakers. Tap the existing Baldwin-Stallings 345 kV line 4531 "in and out" and build 7.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard. Tap the existing Baldwin-Mt. Vernon 345 kV line 4541 "in and out" and build 1.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard. At the Baldwin 345 kV switchyard, replace 9-345 kV circuit breakers that would be overstressed as a result of the Prairie State development. Also install 3-345 kV circuit breakers for a new Baldwin-Rush Island 345 kV line and a new connection for the Baldwin 345/138 kV transformer. Build a new 26 mile 345 kV 3000 A summer emergency capability line from Baldwin to Rush Island. | IL |  |  | Pending | Pending | Several connection options were considered, including radial Prairie State-Baldwin 345 kV lines, but the proposed arrangement satisfies both powerflow and stability issues better than the other options. |  | TAP | Service |  | 2008-06-01 | 345 |  | 63039600 | 5 | Planned
A | 724 | 2006-10-04 |  | Central | AmerenIP | Rising-Bondville Rt. 10 138 kV line | Rising-Bondville 138 kV - Install 138 kV breaker at Bondville, construct 3 miles new 138 kV line | IL |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2006-12-01 | 138 |  | 2442500 | 1 | Under Construction
A | 725 | 2006-10-04 | 725 | Central | AmerenIP | LaSalle Area Development | N. LaSalle-Wedron Fox River 138 kV - 20 miles new line, 2-138 kV breakers at N. LaSalle, 1 138 kV Breaker at Wedron Fox River | IL |  |  | Approved | Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 20489370 | 1 | Planned
A | 726 | 2006-10-04 | 725 | Central | AmerenIP | LaSalle Area Development | Ottawa-Wedron Fox River 138 kV - Construct 14 miles new 138 kV line, 1 new 138 kV breaker at Ottawa | IL |  |  |  | Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 8045400 | 1 | Planned
A | 728 | 2006-10-04 |  | Central | AmerenIP | Wood River-Roxford 1502 138 kV line | Wood River-Roxford 1502 138 kV line - Reconductor | IL |  |  | Approved | Not Required |  |  | TBD | TBD |  | 2008-06-01 | 138 |  | 5264900 | 1 | Planned
A | 732 | 2006-03-17 |  | Central | AmerenIP | S. Bloomington-State Farm 138 kV | S. Bloomington-State Farm 138 kV - Reconductor | IL |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 1172900 | 1 | Planned
A | 736 | 2006-03-17 |  | Central | AmerenIP | W. Tilton 138 kV Substation | W. Tilton 138 kV Substation - Install 138 kV breaker | IL |  |  | Not Budgeted | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 1709400 | 1 | Planned
A | 738 | 2006-03-17 |  | Central | AmerenIP | Latham-Lanesville 138 kV Line | 138 kV Line 1342C tap - Line 1342A - Reconductor structure 423 to 467A | IL |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 1994400 | 1 | Planned
A | 739 | 2006-03-17 |  | Central | AmerenIP | Franklin County Power Plant Connection | Franklin County Power Plant Connection - Tap 345 kV Line 4561 Tap, and Install new 345 kV ring bus | IL |  |  | Not Budgeted | Required |  |  | TAP | Service |  | 2009-01-01 | 345 |  | 7108700 | 1 | Planned
A | 865 | 2006-03-17 |  | Central | AmerenIP | Havana-Monmouth 138 kV River Crossing | Havana-Monmouth 138 kV Line 1362 - Rebuild river crossing | IL | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 223700 | 1 | Planned
A | 869 | 2005-07-11 |  | Central | AmerenIP | Sidney-Mira Tap 138 kV | Sidney-Mira Tap 138 kV - Reconductor 2 miles 795 kcmil ACSR | IL | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 693800 | 1 | Planned
A | 873 | 2005-07-11 |  | Central | AmerenIP | Baldwin Plant 345 kV Switchyard | Replace 6-345 kV breakers with breakers having 3000 A continuous capability | IL | [6 empty] | TBD | TBD |  | 2009-01-31 | 345 |  | 12726300 | 3 | Planned
A | 1 | 2005-07-11 | 1 | West | ATC LLC | Arrowhead-Gardner Park 345 kV | Arrowhead - Gardner Park 345 kV line | WI | MN |  | Approved | Obtained |  |  | Other | Excluded | Y | 2008-06-30 | 345 | 230 | 391667218.88 | 7 | Planned
A | 2 | 2005-07-11 |  | West | ATC LLC | Weston - Northpoint 115 kV reconductor | Reconductor Weston-Dewey Tap-Northpoint 115 kV line with 795 ACSR conductor. | WI |  | 0 | Approved | Approved | Alternatives to the reconductor of this line were considered (such as constructing new facilities) but were deemed infeasible due to cost differential, regulatory and/or time constraints. Several conductor types were identified as possible candidates for this reconductor: 477 ACSR at 300F clearance, 795 ACSR at 200F clearance, 795 ACSR at 300F clearance and 477 ACSR T2 at 200F clearance. |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 11071369 | 2 | Planned
A | 21 | 2005-07-11 | 10 | West | ATC LLC | Metonga T-D interconnection | Venus-Metonga (was Crandon) 138 kV line | WI |  |  | Approved | Pending |  |  | Other | Not Shared |  | 2007-06-01 | 115 |  | 8745840 | 1 | Under Construction
A | 22 | 2005-11-18 | 11 | West | ATC LLC | Femrite-Sprecher new 138 kV; Sprecher-Reiner-Sycamore conversion to 138 kV | Femrite - Sprecher 138 (new), Sprecher - Reiner 138 (conversion), Reiner - Sycamore 138 (conversion), | WI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 10600000 | 3 | Under Construction
A | 62 | 2005-11-18 | 44 | West | ATC LLC | Wien-McMillan 115 kV | Wien - Stratford - McMillan 115 ckt , Sum rate 202 | WI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-03-01 | 115 |  | 1750000 | 1 | Planned
A | 64 | 2005-07-11 | 46 | West | ATC LLC | Kegonsa-McFarland-Femrite conversion to 138 kV | Kegonsa - McFarland -Femrite conversion to 138 kV | WI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 3410000 | 2 | Under Construction
A | 101 | 2005-07-11 | 82 | West | ATC LLC | Kelly-Whitcomb 115 kV uprate | Kelly - Whitcomb 115 ckt , Sum rate 241 | WI |  |  | Pending | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 115 |  | 1900000 | 1 | Planned
A | 168 | 2005-07-11 | 146 | West | ATC LLC | Werner West 345/138 kV transformer | Werner West transformer - 345/138 ckt , Sum rate 500 | WI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2006-12-31 | 345 | 138 | 14300000 | 1 | Under Construction
A | 177 | 2006-03-16 | 155 | West | ATC LLC | Gardner Park-Central Wisconsin 345 kV line projects | Construct Gardner Park-Central Wisconsin 345 kV line and Construct new Central Wisconsin 345 kV substation | WI |  |  | Approved | Approved | Alternative #1: Arrowhead-Stone Lake-Gardner Park and Gardner Park-Morgan 345 kV lines. Alternative #2: Arrowhead-Stone Lake-Gardner Park and a second Gardner Park- Rocky Run 345 kV line. Alternative #3: Arrowhead-Stone Lake-Gardner Park and Low Voltage (115 and 138 kV) Requirements. |  | Other | Not Shared |  | 2009-12-01 | 345 |  | 128900000 | 6 | Planned
A | 339 | 2005-07-11 | newgrp15 | West | ATC LLC | Lake Mills Transmission-Distribution interconnection | Construct a Jefferson-Lake Mills-Stony Brook 138 kV line Uprate Rockdale to Jefferson 138 kV line Uprate Rockdale to Boxelder 138 kV line Uprate Boxelder to Stonybrook 138 kV line | WI |  |  | Pending | Pending | Option 1: Build a new London-Lake Mills-Jefferson line Option 2: Build a 345 kV Substation with 345/138 kV Transformation at North Randolph and radial 138 kV line from Jefferson to Lake Mills Option 3: Build a new Box Elder-Lake Mills-Jefferson 138 kV line |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 20450000 | 6 | Planned
A | 345 | 2006-11-02 | newgrp20 | West | ATC LLC | Morgan - Werner West 345 kV line (includes Clintonville-Werner West 138) | Morgan - Werner West 345 kV line, Clintonville - Werner West 138 kV line primarily on 345 kV line structures, and terminate the existing Werner - White Lake 138 kV line at the Werner West switching station | WI |  |  | Approved | Approved | 1. Morgan-North Appleton alternative Construct a new Morgan-N Appleton 345/138 kV double circuit line (assumed 42-mile length) 2. Low Voltage Enhancements alternative Add a 4th 345/138 kV transformer at N Appleton and construct a 138 kV ring bus. Rebuild various 138 kV lines. |  | BaseRel | Shared |  | 2009-12-01 | 345 |  | 139778849 | 4 | Planned
A | 350 | 2006-07-05 | newgrp3 | West | ATC LLC | Weston-Sherman-Hilltop 115 kV | Weston - Sherman Street - Hilltop 115 kV line rebuild as double circuit | WI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 7750000 | 3 | Planned
A | 352 | 2006-03-16 | newgrp4 | West | ATC LLC | Cranberry-Conover 115 kV and Conover-Plains conversion to 138 kV | Construct Cranberry-Conover 115 kV line, Rebuild/convert Conover-Plains 69 kV line to 138 kV, Construct 138 kV bus and install 138/115 kV 150 MVA and 138/69 kV 60 MVA transformers at Conover, Construct 138 kV bus and install 60 MVA transformer at Bobcta, Relocate Iron River substation (Iron Grove), Construct 138 kV bus and install a 138/69 kV, 60 MVA transformer at Iron Grove | WI |  |  | Approved | Pending | Alternative #1: Weston - Venus 115 kV line and 115 kV line Rebuilds Alternative #2: Clear Lake - Park Falls 115 kV line Alternative #3: Venus - Plains 138 kV line |  | BaseRel | Shared |  | 2009-12-31 | 138 | 115 | 117800000 | 7 | Planned
A | 432 | 2005-07-11 | 313 | West | ATC LLC | Summit Lake Upgrade existing 11.3 to 16.9 MVAR capacitor bank | Summit Lake 115, install additional 5.6 Mvars of capacitance | WI |  |  | Pending | Not Required |  |  | Other | Excluded | Y | 2006-11-01 | 115 |  | 1000000 | 1 | Planned
A | 433 | 2005-07-11 | 314 | West | ATC LLC | Wautoma 32.6 MVAR capacitor bank | Install 2-24.5 MVAR capacitor banks at Wautoma 138 kV and one-16.33 MVAR capacitor bank at 69 Kv | WI |  |  | Pending | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 1200000 | 1 | Planned
A | 446 | 2005-07-11 | 325 | West | ATC LLC | Hartford 36 MVAR capacitor bank | Hartford 138 kV, 36 MVAR Capacitor bank | WI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-04-30 | 138 |  | 750000 | 1 | Planned
A | 551 | 2005-07-11 | p2-110 | West | ATC LLC | Stone Lake Substation | Stone Lake 345/161 tap of Arrowhead-Gardner Park 345 kV line | WI |  |  | Pending | Required |  |  | Other | Excluded | Y | 2008-06-01 | 345 | 161 | 8100000 | 1 | Planned
A | 566 | 2006-10-04 | 566 | West | ATC LLC | Plymouth T-D interconnection | Forest Junction / Charter Steel to Plymouth 138 kV line and T-D substation. Construct 1.3 mile double circuit from Plymouth municipal utility to existing line. | WI |  |  | Approved | Pending |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 2500000 | 1 | Planned
A | 570 | 2005-07-11 | 570 | West | ATC LLC | Rock River-Bristol-Elkhorn conversion to 138 kV | Rock River - Bristol - Elkhorn conversion to 138 kV | WI |  |  | Pending | Pending |  |  | Other | Excluded | Y | 2009-06-01 | 138 |  | 15063960 | 6 | Planned
A | 571 | 2005-07-11 | 571 | West | ATC LLC | North Madison-Waunakee 138 kV line | New North Madison - Huiskamp 138 kV line and a new 138/69 kV substation near Huiskamp including a 100 MVA 138/69-kV transformer | WI |  |  | Pending | Pending |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 8700000 | 1 | Proposed
A | 572 | 2006-10-04 | 572 | West | ATC LLC | Menominee 138/69 kV transformer | Loop West Marinette - Bay de Noc 138 kV line into Menominee. Total project cost $2,000,000. | WI |  |  | Pending | not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 2000000 | 2 | Proposed
A | 877 | 2006-03-16 | new100 | West | ATC LLC | Elm Road (Oak Creek) Generation Related Additions | Reconductor Oak Creek-Ramsey 138 kV line (2009), Reconductor Oak Creek-Allerton 138 kV line (2009), Replace relaying on 230 kV circuits at Oak Creek (2009), Replace two 345 kV circuit breakers at Pleasant Prairie on the Racine and Zion lines with IPO breakers and upgrade relaying (2009), Expand Oak Creek 345 kV switchyard to interconnect one new generator (2009), Loop Ramsey5-Harbor 138 kV line into Norwich and Kansas to form a new line from Ramsey-Norwich and Harbor-Kansas 138 kV lines (2009), Uprate Kansas-Ramsey6 138 kV line (2009), Install second 500 MVA 345/138 kV transformer at Oak Creek (2010), Expand 345 kV switchyard at Oak Creek to interconnect one new generator (2010), Uprate Oak Creek-Root River 138 kV line (2010), Uprate Oak Creek-Nicholson 138 kV line (2010). | WI |  |  | Approved | Pending | There were no viable alternatives considered for this project. The projects listed above made use of existing rights-of-way and upgrading existing facilities to accommodate the new generation. |  | Other | Not Shared |  | 2010-06-01 | 345 | 138 | 44706194 | 12 | Planned
A | 1451 | 2005-11-18 | 11 | West | ATC LLC | Femrite-Sprecher new 138 kV; Sprecher-Reiner-Sycamore conversion to 138 kV | Femrite - Sprecher 138 (new), Sprecher - Reiner 138 (conversion), Reiner - Sycamore 138 (conversion), | WI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 10600000 | 3 | Under Construction
A | 102 | 2006-03-16 | 83 | West | ATC LLC | Port Washington generator additions projects | Port Washington generator additions; Port Washington-Saukville, Port Washington-Range Line 138 kV rebuilds | WI |  |  | Pending | Pending |  |  | BaseRel | Shared |  | 2014-06-01 | 138 |  | 15600000 | 3 | Planned
A | 42 | 2005-07-11 | 17 | Central | CIN | Bedford to Seymour 13829 Reconductor | Reconductor 13829 line from Bedford - Shawswick - Pleasant Grove - Airport Road Jct - Seymour. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2009-06-01 | 138 |  | 10970605 | 4 | Planned
A | 91 | 2005-07-11 | 72 | Central | CIN | Hillcrest 345/138 | Construct new 345/138 kV Hillcrest substation. Tap Suart to Foster 345kV line. Construct new 138kV line from Eastwood to Hillcrest. | OH |  |  | Approved | Not Required |  |  | BaseRel | Shared |  | 2008-06-01 | 345 | 138 | 10306336.59 | 2 | Planned
A | 115 | 2005-07-11 | 86 | Central | CIN | New London to Webster 230 Reconductor | Reconductor New London to Webster St 230 | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 230 |  | 9455194 | 1 | Planned
A | 116 | 2005-07-11 | 87 | Central | CIN | Westwood Bk2 345/138 | Add 2nd 345kV line from AEP Dequine to Westwood and 2nd Westwood 345/138 kV transformer. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 345 | 138 | 6836707 | 3 | Planned
A | 199 | 2005-07-11 | 178 | Central | CIN | Kokomo HP 230/138 | Add 4th 230/138 kV transformer at Kokomo Highland Park. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 230 | 138 | 3278756 | 1 | Planned
A | 200 | 2005-07-11 | 179 | Central | CIN | W Laf Purdue 138 Switches | Upgrade 138kV switches at West Lafayette Purdue. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 9877 | 1 | Planned
A | 201 | 2005-07-11 | 180 | Central | CIN | W Laf 138 Switches | Changing out switches to achieve conductor rating. NW Tap - West Lafayette 138 | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 100000 | 1 | Planned
A | 619 | 2006-03-10 |  | Central | CIN | IPL Petersburg 345 Breaker | Complete breaker and half scheme at Petersburg Plant. IPL total estimate 1,100,000. 200,000 is Cinergy share of project. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-12-31 | 345 |  | 200000 | 1 | Planned
A | 624 | 2005-07-11 |  | Central | CIN | Cloverdale to Plainfield 138 Lightning Protection | Upgrade static and grounding on the Cloverdale to Plainfield South 138kV circuit. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-12-31 | 138 |  | 2387209 | 1 | Planned
A | 627 | 2005-07-13 | 304D7834 | Central | CIN | Kenton to West End New 138 Circuit | Construct new 138kV line from Kenton to West End. | KY | OH |  | Approved | Obtained |  |  | Other | Excluded | Y | 2009-06-01 | 138 |  | 1980041 | 3 | Planned
A | 628 | 2005-07-11 |  | Central | CIN | Kok HP to Kok Delco 138 100C Uprate | Uprate 138kV line from Kokomo Highland Park to Kokomo Delco to 100C operating temperature. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 100000 | 1 | Planned
A | 629 | 2005-07-11 | 628A | Central | CIN | Kok HP to Kok Chrysler 138 100C Uprate | Uprate 138kV line from Kokomo Highland Park to Kokomo Chrysler to 100C operating temperature. | IN |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 100000 | 1 | Planned
A | 631 | 2005-07-11 |  | Central | CIN | Columbus 600A 138kV Switches | Replace 600A switches at Columbus. Increase rating for Columbus to Seymour 13830 circuit. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-12-31 | 138 |  | 65695 | 1 | Planned
A | 632 | 2005-07-11 |  | Central | CIN | Gallagher to HE Georgetown 138kV Reconductor | Reconductor section of the 13885 circuit from Gallagher to HE Georgetown. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2009-06-01 | 138 |  | 1065110 | 1 | Planned
A | 765 | 2005-07-11 |  | Central | CIN | Cloverdale 138kV Cap | Add 43.2 MVAR 138kV capacitor at Cloverdale. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-12-01 | 138 |  | 524860 | 1 | Planned
A | 766 | 2005-07-11 |  | Central | CIN | Clarksville 138kV Cap | Add 57.6 MVAR 138kV capacitor at Clarksville. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 738662 | 1 | Planned
A | 767 | 2005-07-11 |  | Central | CIN | Hastings Park 138kV Cap | Add 57.6 MVAR 138kV capacitor at Greenfield Hastings Park. | IN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 598722 | 1 | Planned
A | 807 | 2005-07-11 | B | Central | CIN | Dresser Bk 1&2 Limiting Equipment | Replace 138kV breakers and switches to achieve full transformer rating. | IN |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2009-06-01 | 345 | 138 | 858000 | 2 | Planned
A | 838 | 2005-07-11 | AG | Central | CIN | Speed 69kV Cap | Add 57.6 MVAR 69kV capacitor at Speed. | IN |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2006-12-31 | 138 |  | 500000 | 1 | Planned
A | 839 | 2005-07-11 | AH | Central | CIN | Crawfordsville 69kV Cap | Add 28.8 MVAR 69kV capacitor at Crawfordsville. | IN |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 500000 | 1 | Planned
A | 842 | 2005-07-11 |  | Central | CIN | Blackwell 138/69 | Construct new Blackwell 138/69kV substation. Tap LGEE 138kV line into substation. | KY |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2007-04-30 | 138 |  | 589000 | 1 | Planned
A | 849 | 2005-07-11 | AR | Central | CIN | Peabody Jct 600A Switches | Replace Peabody Jct 600A switches with 1200A switches. | IN |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 318341 | 2 | Planned
A | 851 | 2005-07-11 | AT | Central | CIN | Laf Cumberland to Laf AE Staley 138 Reconductor | Reconductor section of 13806 circuit with 954ACSR 100C. | IN |  |  | Approved | Not required |  |  | Other | Not Shared |  | 2011-06-01 | 138 |  | 325000 | 1 | Planned
A | 1193 | 2006-10-02 | 104F8436 | Central | CIN | Nickel | Extend 5680 through new Nickel 138/12 sub to be built on development property. | OH | [6 empty] | Other | Not Shared |  | 2010-06-01 | 138 |  | 150376.81 | 1 | Planned
A | 1195 | 2005-11-28 | 604E6256 | Central | CIN | Cloverdale Ethanol 138 | Construct new 138kV line from Cloverdale to new Putnam Energy ethanol plant. | IN | [6 empty] | Other | Not Shared |  | 2007-05-01 | 138 |  | 229811 | 1 | Planned
A | 1196 | 2005-11-28 | 602F6290 | Central | CIN | New London to Kok Highland Park 23009 Wave Traps | Replace 23009 800A wave traps at New London and Kokomo Highland Park with 1200A wave traps. | IN | [6 empty] | Other | Not Shared |  | 2006-12-31 | 230 |  | 29671.83 | 2 | Planned
A | 1198 | 2005-11-28 | 802F6503 | Central | CIN | Bedford Switch Automation | Add motors and automation to the 34506 and 34521 line switches. | IN | [6 empty] | Other | Not Shared |  | 2007-06-01 | 345 |  | 152390.14 | 1 | Planned
A | 1199 | 2005-11-28 | 804F6505 | Central | CIN | Dresser to Water St 100C Urate | Uprate 13868 conductor to 100C operating temperature from Dresser to S 1st St to Water St. New limit 1200A terminal equipment. | IN | [6 empty] | Other | Not Shared |  | 2010-06-01 | 138 |  | 20000 | 2 | Planned
A | 1200 | 2005-11-28 | 702F6501 | Central | CIN | Speed Bk3 Limiting Equipment | Upgrade 2000A 138kV breaker & switch and any other Bk3 limiting equipment. Replace any equipment that would limit the 345/138 xfr to less than the hot spot rating of 520 MVA. | IN | [6 empty] | Other | Not Shared |  | 2010-06-01 | 345 | 138 | 173193.11 | 1 | Planned
A | 1201 | 2005-11-28 | 804C5822 | Central | CIN | Oakland City to Princeton 100C Uprate | Uprate 13863 to 100C operating temperature from Oackland City to Princeton by adding 3 structures. New limit 1200A terminal equipment. | IN | [6 empty] | Other | Not Shared |  | 2006-12-31 | 138 |  | 111331 | 1 | Planned
A | 1244 | 2006-03-27 |  | Central | CIN | Cayuga to Frankfort 23013 Wave Trap Upgrade | Upgrade wave traps at Cayuga and Frankfort to increase line rating to 797 MVA. | IN | [6 empty] | Other | Not Shared |  | 2011-06-01 | 230 |  | 167560 | 2 | Planned
A | 1246 | 2006-03-27 | 602G6548 | Central | CIN | Five Points 23030 Wave Trap | Replace 800A wave trap with a 2000A wave trap. Increase line rating for Five Points to Geist 230kV line. | IN | [6 empty] | Other | Not Shared |  | 2011-06-01 | 230 |  | 24038 | 1 | Planned
A | 1247 | 2006-03-27 | 604G6544 | Central | CIN | Greentown to Peru SE 23021 uprate to 100C | Upgrade Greentown to Peru SE 230kV line to 100C operating temperature. | IN | [6 empty] | Other | Not Shared |  | 2011-06-01 | 230 |  | 28403 | 1 | Planned
A | 1251 | 2006-03-27 |  | Central | CIN | Kokomo Highland Park to Noblesville 23008 Wave Trap Upgrade | Replace 800A wave traps with 2000A wave traps at Kok HP and Noblesville. Increase 230kV line rating from Kok HP to Carmel 146th St Jct to Noblesville. | IN | [6 empty] | Other | Not Shared |  | 2011-06-01 | 230 |  | 54038 | 2 | Planned
A | 1252 | 2006-03-27 | 602C5687 | Central | CIN | Kokomo Highland Park 23028 Wave Trap | Replace 800A wave trap with a 2000A wave trap. Increase 230kV line rating to Thorntown. | IN | [6 empty] | Other | Not Shared |  | 2006-12-31 | 230 |  | 30000 | 1 | Planned
A | 1253 | 2006-03-27 | 502G6547 | Central | CIN | Noblesville 23007 Wave Trap | Replace 800A wave trap with a 2000A wave trap. Increase line rating for Noblesville to Geist 230kV line. | IN | [6 empty] | Other | Not Shared |  | 2011-06-01 | 230 |  | 24038 | 1 | Planned
A | 1254 | 2006-03-27 | 704G6587 | Central | CIN | Charletown to CMC new 138kV line | Construct 8.5 mi. of 138kV line from Charlestown to CMC. | IN | [6 empty] | Other | Not Shared |  | 2009-12-31 | 138 |  |  | 1 | Planned
A | 1262 | 2006-07-05 | 702G6641 | Central | CIN | HE Durgee Rd | HE 138/12 kV substation. | IN |  |  |  | Not required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 227341 | 1 | Planned
A | 584 | 2005-06-15 | 584 | West | DPC/XEL | Genoa-Coulee 161 kV line upgrade | Genoa-Coulee 161 kV line upgrade | WI | [6 empty] | Other | Not Shared |  | 2007-06-01 | 161 |  | 4057132 | 1 | Planned
A | 615 | 2006-10-03 |  | East | FE | Galion 345/138 kV transformer prep | Galion 345/138 kV transformer prep | OH |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-12-01 | 345 | 138 | 1815566 | 1 | Planned
A | 616 | 2006-10-03 |  | East | FE | Crissinger - Tangy 138 kV line | Crissinger - Tangy 138 kV line | OH |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 2713000 | 1 | Planned
A | 890 | 2006-10-03 |  | East | FE | North Medina Substation | Add a new 345/138kV substation at the junction of the Star-Carlisle 345kV and Star-West Akron #2 138kV lines | OH | [6 empty] | BaseRel | Shared |  | 2008-06-01 | 345 | 138 | 8405000 | 1 | Planned
A | 1316 | 2006-09-11 | COH-06-060313-125705 | East | FE | Dale Sub - Install Reactor | Reactor to be Installed on the Dale-West Canton 138 kV line at the Dale Susbstation | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 401800 | 1 | Under Construction
A | 1326 | 2006-09-13 | NOH-07-060221-152713 | East | FE | Add Capacitor Banks at Harding and JuniperSubstations | Addtion of a 300 MVAr capacitor bank at the Harding 345 kV bus in 2008 and Addtion of a 300 MVAr capacitor bank at the Juniper 345 kV bus in 2009 | OH |  |  | Approved | Not Required |  |  | BaseRel | Shared |  | 2009-06-01 | 345 |  | 5454346 | 2 | Planned
A | 1327 | 2006-09-13 | COH-06-050519-151858 | East | FE | Babb - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2009-06-01 | 138 |  | 488600 | 1 | Planned
A | 1328 | 2006-09-13 | COH-07-050622-154415 | East | FE | Barberton - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2010-06-01 | 138 |  | 677600 | 1 | Planned
A | 1329 | 2006-09-13 | COH-07-050623-094932 | East | FE | West Akron - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2009-06-01 | 138 |  | 257000 | 1 | Planned
A | 1330 | 2006-09-13 | COH-07-050623-095518 | East | FE | South Akron - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 426000 | 1 | Planned
A | 1331 | 2006-09-13 | COH-06-050519-152347 | East | FE | East Akron - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2011-06-01 | 138 |  | 305000 | 1 | Planned
A | 1332 | 2006-09-13 | COH-06-060313-125000 | East | FE | Cloverdale - Install 138 kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Budgeted | Not Required |  |  | Other | Not Shared |  | 2009-06-01 | 138 |  | 378000 | 1 | Planned
A | 1333 | 2006-09-13 | SOH-06-050509-071724 | East | FE | Brookside -Add 138kV Cap Banks | Add 2 - 50 MVAR Cap Bank with 1 - 138 kV Switcher | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2010-06-01 | 138 |  | 1000200 | 1 | Planned
A | 1334 | 2006-09-13 | SOH-06-050509-072919 | East | FE | Longiew -Add 138kV Cap Banks | Add 2 - 50 MVAR Cap Bank with 1 - 138 kV Switcher | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2010-06-01 | 138 |  | 523800 | 1 | Planned
A | 1335 | 2006-09-13 | SOH-07-050509-073659 | East | FE | Roberts -Add 138kV Cap Bank | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 379285 | 1 | Planned
A | 1336 | 2006-09-13 | SOH-06-050506-150255 | East | FE | Gallion Transformers #3 and #4 345 kV Circuit Breaker Addtion | Add 345kV breaker to complete 345kV ring-bus as well as extend 138kV bus to include another breaker string to the existing breaker-and-a-half scheme. | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-01 | 138 |  | 1815566 | 1 | Under Construction
A | 1350 | 2006-10-03 | COH-06-060313-112229 | East | FE | Cloverdale Sub - Split 138 kV Bus | Rearrange the 138 kV bus at Cloverdale to electrically separate the North and the South bus and provide a separate 138 kV breaker for xfmr #4 | OH |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 630900 | 1 | Under Construction
A | 596 | 2005-06-15 |  | West | GRE | Vermillion River - Empire 115 kV line | Vermillion River - Empire 115 kV line | MN | [6 empty] | Other | Excluded | Y | 2007-05-01 | 115 |  | 2750000 | 1 | Planned
A | 601 | 2005-06-15 |  | West | GRE | Mud Lake - Wilson Lake 115 kV line | Mud Lake - Wilson Lake 115 kV line | MN | [6 empty] | Other | Excluded | Y | 2008-06-01 | 115 |  | 6000000 | 1 | Planned
A | 1290 | 2006-08-24 | 12 | West | GRE | Willmar - Granite Fall 230 kV line limit will be 382 MVA by 2007 (CT and wavetrap replacement to higher amperage this fall) | Willmar - Granite Fall 230 kV line limit will be 382 MVA by 2007 (CT and wavetrap replacement to higher amperage this fall) | MN | [6 empty] | Other | Not Shared |  | 2006-12-31 | 230 |  | 250000 | 1 | Planned
A | 1318 | 2006-09-08 | 925 | Central | HE | Decatur County Switch Station (DCSS) | 161/138kV Switching Station w/138kV Ring Bus | IN |  |  | Budgeted | Required | None |  | BaseRel | Shared |  | 2007-09-01 | 161 | 138 | 7000000 | 3 | Planned
A | 1319 | 2006-09-08 | 825 | Central | HE | Decatur County Switch Station Tap | 138kV Taplines from Cinergy 138kV Transmission | IN |  |  | Budgeted | Required | None |  | BaseRel | Shared |  | 2007-09-01 | 138 |  | 500000 | 1 | Planned
A | 1320 | 2006-09-08 | 826/926 | Central | HE | Greensburg Honda Subs & Tap Lines | Two 138/12.47kV substations and tap lines from DCSS | IN |  |  | Budgeted | Required | None |  | Other | Not Shared |  | 2007-09-01 | 138 |  | 3750000 | 2 | Planned
A | 1321 | 2006-09-08 | 827/927 | Central | HE | Napoleon to DCSS Transmission Project | 161kV Transmission from Napoloen to DCSS, 30 MVAR Cap | IN |  |  | Budgeted | Required | None |  | BaseRel | Shared |  | 2008-09-01 | 161 |  | 8000000 | 2 | Planned
A | 1322 | 2006-09-08 | 829/929 | Central | HE | Owensville Primary Substaton | 138/69kV Primary Station at Owensville | IN |  |  | Budgeted | Required | None |  | Other | Not Shared |  | 2008-04-01 | 138 |  | 2500000 | 1 | Planned
A | 1323 | 2006-09-08 | 930 | Central | HE | Sandborn Primary Substation | 161/69kV Primary Station at Sandborn | IN |  |  | Budgeted | Required | None |  | Other | Not Shared |  | 2008-04-01 | 161 |  | 6000000 | 1 | Planned
A | 40 | 2006-10-03 | IPL-05 | Central | IPL | Cumberland-Julietta-Indian Crk 138kV Line | Add new 138kV Line from Cumberland to Julietta to Indian Creek | IN |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 1818011.02 | 2 | Planned
A | 893 | 2006-10-03 | IPL-02 | Central | IPL | North 138 kV 150 MVAR Capacitor | Capacitor Bank SizeUpgrade: North 138 kV 100 MVAR To 150 MVAR | IN |  |  | Pending | Not Required |  |  | Other | Not Shared |  | 2008-06-01 | 138 |  | 300000 | 1 | Planned
A | 895 | 2006-10-03 | IPL-04 | Central | IPL | Georgetown To Northeast 138kV Loop-In | Loop Georgetown to Northeast 138kV Line Into North Substation | IN |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-07-01 | 138 |  | 3000000 | 2 | Under Construction
A | 503 | 2005-08-10 | p2-48 | East | ITC | Wixom-Quaker 230 | Project to add 345/230 kV transformer at Wixom, un-six-wire Wixom to Hancock 120 kV ckt, decommission Hancock to Quaker 120 kV ckt, add 230/120 kV transformer at Quaker (on new bus), create new 230 kV ckt from Wixom to Quaker, and reconductor 4 miles of the existing Hancock to Southfield 120 kV circuit. | MI |  |  | Pending | Pending |  |  | Other | Excluded | Y | 2007-05-30 | 345 | 120 | 10000000 | 4 | Planned
A | 509 | 2005-08-10 | p2-56 | East | ITC | Lenox Station | Belle River-Lenox and Lenox-Jewel 345 kV lines, Lenox 345/120 kV transformer, and 120 kV station that ties together several 120 kV lines in the area. (St Clair, Victor, Augusta tap, Grayling 1 & 2). Was New Haven, named changed to Lenox. | MI |  |  | Pending | Obtained |  |  | Other | Excluded | Y | 2006-12-31 | 345 | 120 | 15000000 | 8 | Planned
A | 518 | 2005-08-10 | p2-66 | East | ITC | Bismark-Golf | Bismark-Golf 120 kV line: create a 120 kV station at Golf and build a new 120 kV line from Bismarck to Golf. | MI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2007-05-30 | 120 |  | 4000000 | 3 | Planned
A | 578 | 2005-08-10 | 578 | East | ITC | DVARs at Wyatt and Lee | Installs DVARs at Wyatt Station and Lee Station | MI |  |  | Approved | Obtained |  |  | Other | Excluded | Y | 2006-12-31 | 120 |  | 3500000 | 1 | Planned
A | 586 | 2005-08-10 |  | East | ITC | Stephens - Erin 120 kV line #3 | Constructs new 120 kV Cable from Stephens to Erin | MI |  |  | Pending | Pending |  |  | BaseRel | TBD |  | 2007-12-31 | 120 |  | 34000000 | 1 | Planned
A | 686 | 2005-08-10 | ITC7 | East | ITC | Majestic 345/120 kV switching station | Create a Majestic-Madrid 120 kV circuit by un-six wiring the existing Majestic-Madrid 345 kV circuit and connecting the available conductor to a new 120 kV bus and position off the Madrid 120 kV bus and the new 120 kV substation via a 345/120 kV transformer at the Majestic station. Poroject also requiresbus expansions at both Madrid 120 kV and 345 kV stations | MI |  |  | Pending | Pending |  |  | BaseRel | Shared |  | 2007-12-31 | 345 | 120 | 13000000 | 4 | Planned
A | 692 | 2005-08-10 | ITC8 | East | ITC | Bismark-Troy 345 | Creates a Bismarck-Troy 345 kV line & a Troy 345/120 kV transformer. | MI |  |  | Pending | Pending |  |  | BaseRel | Shared |  | 2008-05-31 | 345 | 120 | 50000000 | 2 | Planned
A | 905 | 2005-08-10 | ff | East | ITC | Marysville Decommissioning | Decommission Marysville Station, expand Bunce Creek Station creating new Bunce Creek - Cypress, Bunce Creek - Menlo, Bunce Creek - Wabash 2 120 kV lines. | MI |  |  | none |  |  |  | Other | Not Shared |  | 2006-12-31 | 120 |  | 3500000 | 3 | Planned
A | 907 | 2005-08-10 | hh | East | ITC | Goodison Station | Build Goodison Station, with a Belle River-Goodison 345 kV, Pontiac-Goodison 345 kV, new 345/120 kV Xfmr, new Pontiac-Goodison 120 kV line, Goodison-Tienken 120 kV, Sunbird-Goodison 120 kV, and Tienken-Spokane 120 kV. | MI |  |  | Pending |  | Central System Alternatives Alternatives for P692 and P907 1. Alternative #1 (P692) a. Tie 120kV buses at Pontiac. b. Build Bismarck-Troy 345kV cable. c. Add Troy 345/120kV transformer. 2. Alternative 2: a. Tie 120kV buses at Pontiac. b. Build Wixom-Hancock 230kV circuit. c. Build Quaker-Hancock 230kV circuit. d. Build Bloomfield-Hancock 230kV circuit. e. Build Bloomfield-Troy 230kV circuit. f. Add Troy 23011 20kV transformer. g. Unparallel Lily-Bloomfield 120kV circuit. h. Unparallel Lily-Hancock 120kV circuit. i. Remove Bloomfield-Troy (Long Lake) 120kV circuit. j. Tie Long Lake buses together. k. Build Chestnut-Red Run 230kV circuit. 1. Build Jewell-Red Run 230kV circuit. m. Build Northeast-Red Run 230kV circuit. n. Tie Jewell 230kV buses together. o. Add Chestnut 230/120kV transformer. p. Build Logan2-Red Run 120kV circuit. q. Build Skylark-Red Run 120kV circuit. r. Remove Logan2-Skylark 120kV circuit. s. Remove Chestnut-Red Run 120kV circuit. t. Remove Skylark-Ramville 120kV circuit. 3. Alternative #3: a. Tie 120kV buses at Pontiac. b. Tap Belle River-Blackfoot 345kV circuit to create Hunters Creek 345kV station. c. Add Hunters Creek 3451120kV transformer. d. Build Chestnut-Red Run 230kV circuit. e. Build Jewell-Red Run 230kV circuit. f. Build Northeast-Red Run 230kV circuit. g. Tie Jewell 230kV buses together. h. Add Chestnut 230/120kV transformer. i. Build Logan2-Red Run 120kV circuit. j . Build Skylark-Red Run 1 20kV circuit. k. Remove Logan2-Skylark 120kV circuit. l. Remove Chestnut-Red Run 120kV circuit. m. Remove Skylark-Ramville 120kV circuit. 4. Alternative #4: a. Tie 120kV buses at Pontiac. b. Tap Belle River-Pontiac 345kV circuit to create Gunn 345kV station. c. Add Gunn 3451120kV transformer. d. Build Sunbird-Gum 120kV circuit. e. Build Pontiac-Gunn 120kV circuit. f. Build Tienken-Gunn 120kV circuit. g. Tie Tienken buses together. h. Remove Colorado-Tienkens 120kV circuit. i. Build Chestnut-Red Run 230kV circuit. j . Build Jewell-Red Run 230kV circuit. k. Build Northeast-Red Run 230kV circuit. l. Tie Jewel1 230kV buses together. m. Add Chestnut 23011 20kV transformer. n. Build Logan2-Red Run 120kV circuit. o. Build Skylark-Red Run 120kV circuit. p. Remove Logan2-Skylark 120kV circuit. q. Remove Chestnut-Red Run 120kV circuit. r. Remove Skylark-Ramville 120kV circuit s. Add 5% Reactor off Gunn-Tienkens 120kV circuit. 5. Alternative #5: a. Tie 120kV buses at Pontiac. b. Tap Belle River-Blackfoot 345kV circuit to create Hunters Creek 345kV station. c. Add Hunters Creek 3451120kV transformer. d. Build Bismarck-Troy 345kV cable. e. Add Troy 3451120kV transformer. 6. Alternative #6: a. Tie 120kV buses at Pontiac. b. Tap Belle River-Pontiac 345kV circuit to create Gunn 345kV station. c. Add Gunn 3451120kV transformer. d. Build Sunbird-Gunn 120kV circuit. e. Build Pontiac-Gum 120kV circuit. f. Build Tienken-Gunn 120kV circuit. g. Tie Tienken buses together. h. Remove Colorado-Tienkens 120kV circuit. i. Build Bismarck-Troy 345kV cable. j. Add Troy 3451120kV transformer. k. Add 5% Reactor off Gum-Tienkens 120kV circuit. RMC 6/14/2005 |  | BaseRel | Shared |  | 2008-05-31 | 345 | 120 | 50000000 | 7 | Planned
A | 911 | 2005-08-10 | ll | East | ITC | Placid 345/120 Xfmr | Construct second 345/120 kV transformer at the Placid station. Project involves expansions at both Placid 120 kV and 345 kV stations | MI |  |  | Pending |  |  |  | BaseRel | Shared |  | 2007-05-30 | 345 | 120 | 10000000 | 1 | Planned
A | 1300 | 2006-08-16 | ITC22 | East | ITC | Pontiac-Joslyn and Joslyn-Walton Equipment upgrade | Replace line terminal equipment in order to raise the thermal rating of the Pontiac-Joslyn and Joslyn-Walton 120 kV circuits. | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-05-30 | 120 |  | 500000 | 2 | Planned
A | 1301 | 2006-08-16 | ITC23 | East | ITC | Yost Line Breaker | Adds a line breaker on the Yost end of the Yost-Polaris 120 kV Circuit to reduce the trasnmission system exposure to faults on distribution circuits | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-12-31 | 120 |  | 300000 | 1 | Planned
A | 1304 | 2006-08-16 | ITC26 | East | ITC | Monroe Breaker | Adds a new breaker on the 120 kV side of Monroe Xfmr 303 | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-12-31 | 345 | 120 | 300000 | 1 | Planned
A | 1305 | 2006-08-16 | ITC27 | East | ITC | Caniff GIS Replacement | Replaces the Gas insulated Switchgear and all breakers at Caniff, and also creates a ring bus configuration. GIS was nearing end of life and would require high maintenance costs | MI |  |  | Approved | needs review |  |  | BaseRel | Shared |  | 2007-05-31 | 345 | 120 | 14400000 | 1 | Planned
A | 1306 | 2006-08-16 | ITC28 | East | ITC | Midtown GIS Replacement | Replaces the Gas insulated Switchgear and all breakers on the 120 kV at Midtown, and also creates a ring bus configuration. GIS was nearing end of life and would require high maintenance costs | MI |  |  | Approved | needs review |  |  | BaseRel | Shared |  | 2007-12-31 | 120 |  | 6000000 | 1 | Planned
A | 1307 | 2006-08-16 | ITC29 | East | ITC | Catilina Substation | Replace the 120 kV Breaker, buses, and station equipment at Catalina Sub as part of a customer intterconnection request | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-05-01 | 120 |  | 1000000 | 1 | Planned
A | 1309 | 2006-08-16 | ITC31 | East | ITC | Breaker Replacement Program | Targets the replacement of breakers nearing their end of life where maintenance costs will be just as high as new breakers | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-12-31 | 345 |  | 3000000 | 12 | Planned
A | 1310 | 2006-08-16 | ITC31 | East | ITC | Breaker Replacement Program | Targets the replacement of breakers nearing their end of life where maintenance costs will be just as high as new breakers | MI |  |  | Approved | needs review |  |  | Other | Not Shared |  | 2007-12-31 | 230 |  | 2000000 | 12 | Planned
A | 246 | 2005-06-15 | TRN.410.02 | West | LES | North Tier 115 kV, Phase II | NW68th & Holdrege - NW 12th & Arbor 115 ckt 1, Sum rate 373 | NE |  |  | Budgeted | Required |  |  | Other | Excluded | Y | 2008-12-31 | 115 |  | 1712000 | 1 | Planned
A | 804 | 2006-09-29 | TRN.440.07 | West | LES | Rebuild North Tier 115 kV | Rebuild part of 19th & Alvo - 70th & Bluff 115 ckt 1, Sum rate 363 | NE |  |  |  | Not Required |  |  | TBD | TBD |  | 2008-12-31 | 115 |  | 300000 | 1 | Planned
A | 548 | 2005-08-02 | p2-107 | West | MDU | Bismarck Downtown-East Bismarck 115 kV upgrade to at least 160 MVA | Bismarck Downtown-East Bismarck 115 kV upgrade to at least 160 MVA | ND | [6 empty] | Other | Not Shared |  | 2007-11-01 | 115 |  | 363000 | 1 | Planned
A | 1008 | 2005-08-02 |  | West | MDU | Bismarck/Mandan 115 kV Circuits transferred from old to new Memorial Bridge | Bismarck/Mandan 115 kV Circuits transferred from old to new Memorial Bridge | ND | [6 empty] | BaseRel | Shared |  | 2009-11-01 | 115 |  | 6560000 | 2 | Planned
A | 481 | 2006-09-29 | 74 | East | METC | Tallmadge 345/138 kV TB3 transformer #3 | Tallmadge 345/138 kV TB3 transformer #3 addition | MI |  |  | Approved | Not Required |  |  | BaseRel | Shared |  | 2007-05-01 | 345 | 138 | 13500000 | 1 | Planned
A | 493 | 2005-07-27 | 123 | East | METC | Tallmadge Remove Reactors | Tallmadge Remove Reactors | MI | [6 empty] | Other | Not Shared |  | 2007-05-01 | 345 |  | 20000 | 1 | Planned
A | 497 | 2006-09-29 | 23 | East | METC | Tallmadge - Wealthy Street 138 kV line #2 | Tallmadge - Wealthy Street 138 kV line #2 | MI |  |  | Not Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 40000 | 1 | Planned
A | 644 | 2005-07-27 | 64 | East | METC | Rogue River 138 ckt # 1 | Rogue River 138 ckt # 1 | MI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-15 | 138 |  | 160000 | 1 | Planned
A | 645 | 2006-09-29 | 56 | East | METC | American Bumper - David 138 ckt # 1 | Rebuild line to 795 ACSS | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 2500000 | 1 | Planned
A | 658 | 2006-09-29 | 82 | East | METC | Gaylord - Livingston 138 ckt # 1 | Reconductor 1.5 miles to 795 ACSS | MI |  |  | Not Budgeted | Not Required |  |  | TAP | Service |  | 2008-05-01 | 138 |  | 500000 | 1 | Planned
A | 660 | 2005-07-27 | 101 | East | METC | Keystone - Clearwater - Stover 138 kV line Phase 1 | Rebuild 23.2 miles to 795 ACSS, Keystone to Clearwater | MI |  |  | Budgeted | Not Required |  |  | BaseRel | Shared |  | 2009-05-01 | 138 |  | 10200000 | 1 | Planned
A | 774 | 2006-09-29 | 61 | East | METC | Gaylord 138 kV 36 MVAR Capacitors | Gaylord 138 kV 36 MVAR Capacitors | MI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-12-01 | 138 |  | 900000 | 1 | Under Construction
A | 775 | 2006-09-29 | 62 | East | METC | Iosco 138 kV 18 MVAR Capacitors | Iosco 138 kV 18 MVAR Capacitors | MI |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2006-12-01 | 138 |  | 800000 | 1 | Under Construction
A | 976 | 2005-07-27 | 48 | East | METC | Alpine - Add one line switch | Install a tap pole and one switch on Four Mile-N Belding 138kV line | MI | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 80000 | 1 | Planned
A | 977 | 2005-07-27 | 49 | East | METC | Marquette 138 kV station | Replace breaker failure scheme | MI | [6 empty] | Other | Not Shared |  | 2006-05-01 | 138 |  | 200000 | 1 | Under Construction
A | 981 | 2005-07-27 | 63 | East | METC | Wabasis | Install a tap pole and two switches on N. Belding - Vergennes 138kV Line | MI | [6 empty] | Other | Not Shared |  | 2009-06-01 | 138 |  | 160000 | 1 | Planned
A | 982 | 2005-07-27 | 65 | East | METC | Crahen | Install a tap pole and one switch on Spaulding-Race St.-Four Mile 138kV line | MI | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 80000 | 1 | Planned
A | 988 | 2005-07-27 | 120 | East | METC | Simpson - Batavia 138 kV line | Build 30 miles new 138 kV line, 795 ACSS | MI | [6 empty] | TBD | TBD |  | 2011-06-01 | 138 |  | 13000000 | 1 | Planned
A | 1015 | 2005-08-12 | 131 | East | METC | Oden | Oden - New Capacitor | MI | [6 empty] | Other | Not Shared |  | 2008-06-01 | 138 |  | 510000 | 1 | Planned
A | 1016 | 2005-08-12 | 132 | East | METC | Bard Road | Bard Road - New Capacitor | MI | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 596000 | 1 | Planned
A | 1017 | 2005-08-12 | 133 | East | METC | Croton | Croton - New Capacitor | MI | [6 empty] | Other | Not Shared |  | 2007-06-01 | 138 |  | 596000 | 1 | Planned
A | 1390 | 2006-10-25 | 140 | East | METC | Goss Station 345kV Bus | Rebuild Goss 345kV bus from GIS to air insulated and replace 345kV breakers | MI |  |  | Approved | Not Required |  |  | BaseRel | Shared |  | 2007-12-01 | 345 |  | 5800000 | 1 | Planned
A | 1391 | 2006-10-25 | 141 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 148 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1392 | 2006-10-25 | 142 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 188 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1393 | 2006-10-25 | 143 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 288 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1394 | 2006-10-25 | 144 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 388 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1395 | 2006-10-25 | 145 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 500 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1396 | 2006-10-25 | 146 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 588 at Campbell | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1397 | 2006-10-25 | 147 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 36M9 at Spaulding | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1398 | 2006-10-25 | 148 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 36B7 at Spaulding | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1399 | 2006-10-25 | 149 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 377 at Morrow | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1400 | 2006-10-25 | 150 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 288 at Claremont | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1401 | 2006-10-25 | 151 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 388 at Claremont | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1402 | 2006-10-25 | 152 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 13B7 at Goss | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1403 | 2006-10-25 | 153 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 13M9 at Goss | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1404 | 2006-10-25 | 154 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 6W8 at Argenta | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1405 | 2006-10-25 | 155 | East | METC | Overdutied Breaker Replacement Plan -Year 5 of 5 | Replace 138kV breaker 499 at Hemphill | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 138 |  | 160000 | 1 | Planned
A | 1406 | 2006-10-25 | 156 | East | METC | Breaker Repair or Replace Program | Replace 138kV Alpena 188 breaker | MI |  |  | Budgeted | Not Required |  |  | Other | Not Shared |  | 2008-12-31 | 138 |  | 160000 | 1 | Planned
A | 1407 | 2006-10-25 | 157 | East | METC | Ludington 345kV Reactor | Repair or replace faulty (gasing) 100MVAR reactor and replace the existing circuit switcher with a breaker | MI |  |  | Budgeted | Not Required |  |  | Other | Not Shared |  | 2007-12-01 | 345 |  | 1500000 | 1 | Planned
A | 1408 | 2006-10-25 | 158 | East | METC | RTU / SCADA upgrade | Install and/or upgrade RTU's and SCADA points throughout system | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-05-01 | 345 | 138 | 801000 | 1 | Planned
A | 1410 | 2006-10-25 | 160 | East | METC | Mobile 138kV Bulk Capacitor | Purchase a mobile 14.4 - 36MVAR capacitor for flexible use where needed throughout the system |  |  |  | Approved | Not Required |  |  | TBD | TBD |  | 2008-12-01 | 138 |  | 700000 | 1 | Planned
A | 1411 | 2006-10-25 | 161 | East | METC | Campbell Unit 3 Automatic Relay Runback SPS | Install auto relay runback scheme on Campbell Unit 3 per MISO G479 project | MI |  |  | Approved | Not Required |  |  | TAP | Service |  | 2007-03-01 | 345 |  | 75000 | 1 | Planned
A | 1412 | 2006-10-25 | 162 | East | METC | Covert - Negative Sequence Mitigation | Re-arrange phases on 345kV Palisades-Argenta Ckt #1 or #2 and on 345kV Palisades-Cook Ckt #2 | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 345 |  | 905000 | 2 | Planned
A | 1413 | 2006-10-25 | 163 | East | METC | Bagley-Gaylord 138kV line | Rebuild line to 795 ACSS | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2009-05-01 | 138 |  | 350000 | 1 | Planned
A | 1414 | 2006-10-25 | 164 | East | METC | Thetford 345kV Line Relaying | Upgrade line relaying on 345kV lines | MI |  |  | Budgeted | Not Required |  |  | Other | Not Shared |  | 2007-12-31 | 345 |  | 300000 | 1 | Planned
A | 1415 | 2006-10-25 | 165 | East | METC | Solar | Install a tap pole and one switch on each of the Tittabawassee-HSC and Lawndale-HSC 138kV lines. | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-10-01 | 138 |  | 160000 | 1 | Planned
A | 1416 | 2006-10-25 | 166 | East | METC | HSC | Install a second 138kV Tittabawasee-HSC line (14.7 miles) along with required 138kV breakers at each end (5 total breakers) and install a 2 mile 138kV double circuit to swap the existing Tittabawasee and Lawndale line connections into HSC. | MI |  |  | Approved | Not Required |  |  | BaseRel | Shared |  | 2007-10-01 | 138 |  | 5800000 | 2 | Planned
A | 1417 | 2006-10-25 | 167 | East | METC | Race Street | Install a 138kV tie-breaker to loop the Spaulding-Four Mile 138kV Line into Race Street | MI |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2007-06-01 | 138 |  | 2200000 | 1 | Planned
A | 264 | 2006-03-24 | 264 | West | MH | Wuskwatim Generation Outlet Transmission Facilities | New outlet transmission facilities required for a new 200 MW generating plant being built near Thompson, Manitoba. This project includes Birchtree - Wuskwatim 230 line, Herblet Lake - Wuskwatim 230 line, 2 Herblet Lake - Wuskwatim 230 lines, & a Thompson Birchtree 150/-20 MVAR SVC. | Manitoba |  |  | Budgeted | Obtained |  |  | TBD | TBD | N/A | 2011-10-31 | 230 |  | 129172597.38 | 5 | Planned
A | 442 | 2006-03-24 | 442 | West | MH | Winnipeg to Brandon Transmission System Improvements | addition of three Portage South station 10 MVAR 66 kV capacitors and 1 Brandon 115, 54 MVAR Capacitor | Manitoba |  |  | Budgeted | Pending |  |  | TBD | TBD | N/A | 2010-10-31 | 115 |  | 472909.3548 | 1 | Planned
A | 1358 | 2006-10-15 |  | West | MP | Grand Rapids - Capacitor 115 add new | Grand Rapids - Capacitor 115 add new | MN | [6 empty] | Other | Not Shared |  | 2006-12-30 | 115 |  | 320000 | 1 | Planned
A | 279 | 2005-07-29 | 274 | West | MPC/XEL/OTP/MP | Boswell - Wilton 230 kV Line | Boswell - Wilton 230 ckt 1, Sum rate 390 | MN |  |  | Pending | Pending | Coal Creek - Underwood - Harvey - Prairie 345 kV Line; Garrison - Max - Minot - Rugby - Drayton 230 kV Line; Bismarck - Jamestown - Fargo 345 kV Line; Boswell - Wilton 230 kV Line; Dorsey - Karlstad - Winger 345 kV Line; Fargo - Moorhead - Morris - Granite Falls - Blue Lake 345 kV Line; Watertown - Granite Falls - Blue Lake 345 kV Line |  | BaseRel | Shared |  | 2010-07-01 | 230 |  | 35963293 | 1 | Proposed
A | 757 | 2006-10-03 | 9320027 | East | NIPS | Dune Acres - Add 138 kV Capacitors - 100 MVAR | Add one step of capacitors, for a total 100 MVAR, on the Dune Acres 138 kV bus. | IN |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-02-01 | 138 |  | 1083600 | 1 | Planned
A | 925 | 2006-10-03 | 71C6613 | East | NIPS | ISG2 to Marktown - Upgrade Capacity | Upgrade circuit capacity on existing .6 miles of 300 KCM Cu line by bundling both sets of 300 KCM CU line on shared tower line between Marktown and ISG #2 to increase capacity to 316 MVA. | IN | [6 empty] | Other | Not Shared |  | 2006-12-01 | 138 |  | 240500 | 1 | Planned
A | 1298 | 2006-10-03 | 71C6805 | East | NIPS | Inland #5 to Marktown - Upgrade Capacity | Upgrade Cir. 13830 capacity on existing 2.2 miles of 400 KCM Cu line by upgrading conductor to 954 KCM ACSR between Marktown and Inland #5 Substation. | IN |  |  | Budgeted | Not required |  |  | Other | Not Shared |  | 2008-05-01 | 138 |  | 750000 | 1 | Planned
A | 274 | 2005-07-29 | 269 | West | OTP | Appleton - Dawson 115 kV Line | Appleton - Dawson 115 ckt 1, Sum rate 96 | MN | [6 empty] | Other | Not Shared |  | 2008-08-01 | 115 |  | 474000 | 1 | Planned
A | 275 | 2005-07-29 | 270 | West | OTP | Canby - Dawson 115 kV Line | Dawson - Canby 115 ckt 1, Sum rate 96 | MN | [6 empty] | Other | Not Shared |  | 2008-08-01 | 115 |  | 538000 | 1 | Planned
A | 973 | 2005-11-01 | G392 | West | OTP | Big Stone II Generation Project | Build New Big Stone - Ortonville 230 kV Line, Convert Ortonville - Johnson Jct. 115 kV line to 230 kV, Convert Johnson Jct. - Morris 115 kV Line to 230 kV, Install a new Johnson Jct. 230/115 kV Transformer, Replace existing Morris 230/115 kV Transforme, Build New Big Stone - Canby 230 kV Line, Convert existing Canby - Granite Falls 115 kV Line to 230 kV, Install a new Canby 230/115 kV Transformer, Upgrade existing Big Stone - Browns Valley 230 kV Line | MN | SD |  | Pending | Pending | Big Stone - Willmar 230 kV Line |  | TAP | Service |  | 2011-06-01 | 230 | 115 | 114750000 | 9 | Planned
A | 1362 | 2006-10-15 |  | West | OTP | Louisurg - Dawson 115 Convert an existing 41.6 kV line to 115 kV | Louisurg - Dawson 1 115 Convert an existing 41.6 kV line to 115 kV | MN | [6 empty] | Other | Not Shared |  | 2008-08-01 | 115 |  | 988000 | 1 | Planned
A | 755 | 2005-07-29 |  | West | OTP/MRES/GRE | Alexandria Capacitor Addition | Alexandria Switching Station 115 kV 25 MVAR Capacitors | MN | [6 empty] | Other | Not Shared |  | 2007-06-01 | 115 |  | 530000 | 1 | Planned
A | 81 | 2005-06-15 | 57 | Central | SIPC | Marion Power Plant - Carrier Mills 161 kV line | Construct a 161 kV line connecting the Marion 161 kV Plant to a new Carrier Mills 161/69 kV Substation. The project includes the construction of nearly 27 miles of 161 kV transmission line and converting a 69 kV switching station into a 161/69 kV substation. | IL |  |  | Pending | Not Required | Alternative plans explored, such as rebuilding existing 69 kV lines and building a new 69 kV system tie line, appeared to be only a temporary correction to the problems at hand. |  | Other | Excluded | Y | 2007-06-01 | 161 |  | 7083000 | 1 | Planned
A | 1002 | 2006-06-29 |  | Central | Vectren (SIGE) | New Northeast to Oak Grove to Culley Line 138 kV | New Northeast to Oak Grove to Culley Line 138 kV | IN |  |  | Budgeted |  |  |  | BaseRel | Shared |  | 2008-12-31 | 138 |  | 8500000 | 2 | Planned
A | 1004 | 2006-06-29 |  | Central | Vectren (SIGE) | New 345/138 kV Substation at Francisco | New 345/138 kV substation at Francisco | IN |  |  | Budgeted |  |  |  | BaseRel | Shared |  | 2007-05-31 | 345 | 138 | 19630000 | 1 | Planned
A | 1005 | 2006-06-29 |  | Central | Vectren (SIGE) | New 138 kV transmission double circuit Francisco to Northwest/Northeast | New 138 kV transmission double circuit Francisco to Northwest/Northeast Subs with Blue Grass Substation | IN |  |  | Budgeted |  |  |  | BaseRel | Shared |  | 2009-05-31 | 138 |  | 19000000 | 2 | Planned
A | 1257 | 2006-06-29 |  | Central | Vectren (SIGE) | New transmission line Gibson (Cinergy) to AB Brown to Reid (BREC) | New 345 kV transmission line Gibson (Cinergy) to AB Brown to Reid (BREC) | IN | KY |  | Budgeted |  |  |  | BaseRel | Shared |  | 2011-05-31 | 345 | 138 | 74575000 | 3 | Planned
A | 1259 | 2006-06-29 |  | Central | Vectren (SIGE) | New transmission line Dubois to Newtonville | New transmission line Dubois to Newtonville | IN |  |  | Approved |  |  |  | BaseRel | Shared |  | 2007-05-31 | 138 |  | 14400000 | 1 | Planned
A | 1205 | 2006-02-10 | 2006-01 | East | WPSC | Cheboygan II Breaker Station | Add a 69KV breaker in the line from Tower to Pelston | MI |  |  | Budgeted | Obtained |  |  | Other | Not Shared |  | 2006-08-01 | 69 |  | 550000 | 1 | Planned
A | 1206 | 2006-02-10 | 2006-02 | East | WPSC | Bass Lake - Lake County Line Rebuild | Line Rebuild to 795ACSR for future 138KV operation | MI |  |  | Budgeted | Obtained |  |  | Other | Not Shared |  | 2006-08-01 | 69 |  | 1800000 | 1 | Planned
A | 1207 | 2006-02-10 | 2006-03 | East | WPSC | Hersey - Osceola Line Re-rate | Rerate line to 75C | MI |  |  | Budgeted | Obtained |  |  | Other | Not Shared |  | 2006-08-01 | 69 |  | 200000 | 1 | Planned
A | 1208 | 2006-02-10 | 2006-04 | East | WPSC | Oden 12MVAR Capacitor Bank | Add 12MVAR Capacitor Bank at Oden Substation | MI |  |  | Budgeted | Obtained |  |  | Other | Not Shared |  | 2006-08-01 | 69 |  | 300000 | 1 | Planned
A | 1226 | 2006-03-15 | 2007-06 | East | WPSC | Kalkaska Gen - Westwood Line Rebuild | Kalkaska Gen - Kalkaska JCT - Westwood Line Rebuild. Summer Rating 102.4 MVA | MI |  |  | Pending | Not Required. | n/a |  | Other | Not Shared |  | 2008-02-01 | 69 |  | 2905000 | 1 | Planned
A | 1227 | 2006-03-15 | 2007-08 | East | WPSC | Gaylord Gen - Bagley Junction | Gaylord Gen - Bagley Junction Rebuild. Summer Rating 102.4 MVA | MI |  |  | Pending | Not Required. | n/a |  | Other | Not Shared |  | 2008-02-01 | 69 |  | 1000000 | 1 | Planned
A | 1228 | 2006-03-16 | 2008-05 | East | WPSC | ANR Elpaso New Load | Add 14MW load off of Wolverine's Westwood Junction | MI |  |  | Pending | Not Required. |  |  | Other | Not Shared |  | 2008-08-01 | 69 |  | 1800000 | 1 | Planned
A | 1229 | 2006-03-16 | 2006-05 | East | WPSC | Plains Junction Breaker Station | Replace Relaying and Breakers at Plains Junction Substation | MI |  |  | Approved | Not Required. |  |  | Other | Not Shared |  | 2006-11-01 | 69 |  | 625000 | 1 | Planned
A | 1230 | 2006-03-16 | 2006-06 | East | WPSC | White Cloud Breaker Station | Replace Relaying and Breakers at White Cloud Substation | MI |  |  | Approved | Not Required. |  |  | Other | Not Shared |  | 2006-09-01 | 69 |  | 625000 | 1 | Planned
A | 1231 | 2006-03-16 | 2006-07 | East | WPSC | Superior Corn Substation | Add new load point neer Wolverine's Odessa Substation | MI |  |  | Approved | Not Required. |  |  | Other | Not Shared |  | 2006-06-01 | 69 |  | 550000 | 1 | Planned
A | 1272 | 2006-07-13 | 2010-03 | East | WPSC | Redwood 75MVA Transformer | Add 75MVA Transformer at Redwood Substation a separate line from Redwood Junction will be ran to energize the transformer. | MI |  |  | Pending | Not Required |  |  | Other | Not Shared |  | 2010-08-01 | 138 | 69 | 1900000 | 1 | Planned
A | 56 | 2006-03-27 | 41 | West | XEL | Chisago - Apple River | Chisago - Lindstrom - Shafer- Lawrence Creek 69 kV rebuild to 115 kV, Lawrence Creek - St Croix Falls - Apple River 69 kV rebuild to 161 kV. New Lawrence Creek 161/115/69 kV substation | MN |  |  | Approved | Required | 1. Chisago-Apple River 69 kV line rebuild 2. Reconfigure 69 kV system and add reactive support 3. Distributed generation which was cost prohibitive |  | Other | Excluded | Y | 2010-12-31 | 161 | 115 | 34480000 | 5 | Planned
A | 265 | 2006-07-12 | 260 | West | XEL | Glencoe - McLeod 115 | Glencoe - McLeod 115 ckt 1, Sum rate 310 | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2006-07-31 | 115 |  | 4282860 | 1 | Planned
A | 267 | 2006-07-12 | 262 | West | XEL | Lawrence - Minnehaha 115 | Lawrence - Minnehaha 115 ckt 1, Sum rate 310 | SD |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-05-01 | 115 |  | 829667 | 1 | Planned
A | 268 | 2006-07-12 | 263 | West | XEL | Minnehaha - Lincoln County 115 | Minnehaha - Lincoln County 115 ckt 1, Sum rate 310 | SD |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-05-01 | 115 |  | 925398 | 1 | Planned
A | 269 | 2006-07-12 | 264 | West | XEL | Prairie Island - Red Rock 345 | Prairie Island - Red Rock 345 ckt 2, Sum rate 1198 | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 345 |  | 807000 | 1 | Planned
A | 270 | 2006-07-12 | 265 | West | XEL | Champlin - Champlin Tap 115 | Champlin - Champlin Tap 115 ckt 1, Sum rate 310 | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 382923 | 1 | Planned
A | 271 | 2006-07-12 | 266 | West | XEL | Hungry Hollow - Ballard Corner 115 | Hungry Hollow - Ballard Corner 115 ckt 1, Sum rate | MN |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2008-09-01 | 115 |  | 1333975 | 1 | Planned
A | 272 | 2006-03-27 | 267 | West | XEL | Air Lake - Vermillion River 115 | Air Lake - Vermillion River 115 ckt 1, Sum rate 200 | MN |  |  | Approved | Obtained |  |  | Other | Not Shared |  | 2007-06-01 | 115 |  | 3359095.21 | 1 | Planned
A | 276 | 2006-07-12 | 271 | West | XEL | Inver Hills - Koch 115 kV line reconductor | Inver Hills - Koch 115 kV line rebuild existing line to 600 MVA | MN |  |  | Approved |  |  |  | Other | Excluded | Y | 2006-12-31 | 115 |  |  | 1 | Planned
A | 366 | 2006-03-27 | St Cloud | West | XEL | Sherburne Co Area 115 kV project | Upgrade Sherco - Monticello 115 and Sherco - St Cloud 115 kV lines, new Sherco 345/115 transformer | MN |  |  | Approved | Not Required | Change existing 345/230kV 336 MVA transformer at Monticello to 2 x 448 MVA units. Rebuild Monticello to Salida Crossing to 194 industrial Park to St Cloud 115kV line to 795 kcm ACSS Monticello change out wavetrap, CT and disconnect to raise rating of 230KV line from Monticello - Benton from 400 to 472 MVA. |  | Other | Excluded | Y | 2007-06-01 | 345 | 115 | 7763734 | 5 | Planned
A | 377 | 2006-07-12 | Wind 425 | West | XEL | Xcel Energy Wind 425 MW project | Buffalo Ridge (SW MN) 425 MW of Generation Outlet: Lakefield to Fox Lake new 161 kV, Spring 06 Bird Island to Franklin rebuild 69 kV, Complete Chanarambie - Lake Yankton - Lyon Co. new 115 kV, Complete Lyon substation, Complete Lyon County 115 kV 2X30 Mvar capacitors, Complete Wilmarth to Martin Co. 345 kV upgrade, Complete Paynesville to Wakefield 115 kV rebuild, Complete Willmar to Kerkhoven 115 kV rebuild, Complete Summit to Dome to Loon Tap 115 kV rebuild, Complete Grant Co. to Brandon 115 kV rebuild, Complete Alexandria to Douglas Co. 115 kV rebuild, Dec 05 Willmar Transformer, Dec 05 Minn Valley Transformers, Dec 05 Black Dog Transformer, Complete Paynesville Transformer, Complete Lake Yankton substation and SVC, Complete Lake Yankton 115 kV 4X20 Mvar capacitors, Complete Brandon to Alexandria 115 kV rebuild, Complete Loon Tap to West Faribault 115 kV rebuild , Complete Troy substation 69 kV new, Complete Lyon County to Marshall 115 kV upgarde, Complete Fox Lake substation upgrade, Spring 2006 West Faribault substation upgrade, Dec 05 Bird Island substation upgrade, Complete Franklin substation upgrade, Complete Douglas substation upgrade , March 05 | MN |  |  | Approved | Obtained |  |  | TAP | Not Shared |  | 2007-01-01 | 161 |  | 15380127.53 | 2 | Planned
A | 385 | 2006-07-12 | Wind 825 | West | XEL | Xcel Energy Wind 425-825 MW project | Buffalo Ridge (SW MN) 825 MW of Generation Outlet: Split Rock to Lakefield Junction new 345 kV Nobles to Chanarambie new 115 kV Nobles Co. substation new Nobles Co 115 kV 40 Mvar capacitor Nobles Co 34.5 kV 2X50 Mvar reactors Fenton substation new Fox Lake to Winnebago 161 kV SPS Brookings Co - Yankee - Buffalo Ridge 115 kV new Yankee substation new Split Rock substation upgrade Lakefield Junction substation upgrade Chanarambie substation upgrade Buffalo Ridge substation upgrade White substation upgrade Lakefield Junction to Lakefield Generation Emery - Lime Creek (Alliant West - Iowa) Series Compensation Wilmarth - Lakefield Generation line Lakefield Jct - Lakefield Generation capacity increase | MN |  |  | Approved | Pending | 1. Option 1- Split Rock-Lakefield Jct 345 kV 2. Option : Lyon County -Franklin 115 kV, Buffalo Ridge -White 115 kV, Chanarambie-Heron Lk 161 kV 3. Option 4 - Lyon County- Ft Ridgley 115 kV 4. Option 5 Reconductor as needed |  | TAP | Not Shared |  | 2010-06-01 | 345 | 115 | 124947480.6572 | 13 | Planned
A | 417 | 2006-07-12 | 309 | West | XEL | Westgate 115, 80 MVAR Capacitor | Westgate 115, 80 MVAR Capacitor | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 1500000 | 1 | Planned
A | 609 | 2006-07-12 |  | West | XEL | Long Lake - Oakdale 115 kV line | Long Lake - Oakdale 115 kV line | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 760000 | 1 | Planned
A | 671 | 2006-07-12 |  | West | XEL | Oakdale - Tanners Lake 115 | Oakdale - Tanners Lake 115 ckt # 1 | MN |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 115 |  | 800000 | 1 | Planned
A | 673 | 2006-07-12 |  | West | XEL | Champlin Tap - Crooked Lake 115 | Champlin Tap - Crooked Lake 115 ckt # 1 | MN |  |  | Approved | Not Required |  |  | Other | Not Shared |  | 2008-06-01 | 115 |  | 310000 | 1 | Planned
A | 674 | 2006-07-12 |  | West | XEL | High Bridge - Rogers Lake 115 | High Bridge - Rogers Lake 115 ckt # 1 | MN |  |  | Approved | Not Required |  |  | TAP | Service |  | 2008-05-01 | 115 |  | 2400000 | 1 | Planned
A | 780 | 2006-07-12 |  | West | XEL | Lakefield Gen - Wilmarth Series Compensation | Fieldon Township 345 kV Series Capacitor 20 ohms | MN |  |  | Approved | Obtained | See Transmission outlet analysis for SW Minnesota (Buffalo Ridge Area) generation addition volume 1 and volume 2 |  | TAP | Service |  | 2007-11-01 | 345 |  | 10100000 | 1 | Planned
A | 1364 | 2006-10-15 |  | West | XEL | Lakefield Jct - Lakefield Generation 345 kV line - Raise the structures to increase the thermal rating | Lakefield Jct - Lakefield Generation 345 kV line - Raise the structures to increase the thermal rating | MN | [6 empty] | TAP | Service |  | 2007-05-01 | 345 |  |  | 1 | Planned
A | 1366 | 2006-10-15 |  | West | XEL | Cannon Falls Generating station - Interconnection upgrades | Cannon Falls Generating station - Transformer relocated from Cannon Falls substation, Build in and out of the Cannon Falls generating station from Cannon Falls - Empire 115 kV line, Build in and out of the Cannon Falls generating station from Cannon Falls - Spring Creek line | MN | [6 empty] | TAP | Service |  | 2008-05-01 | 161 | 115 | 13940004 | 5 | Planned
B | 1291 | 2006-08-24 | 13 | West | ALTW | Build one 161 kV substation at 5% between E Calamus - Dewitt (34122-34124). Build one 2-mile new 161 kV line between the new substation and Grand Mound (34123) with normal-open | Build one 161 kV substation at 5% between E Calamus - Dewitt (34122-34124). Build one 2-mile new 161 kV line between the new substation and Grand Mound (34123) with normal-open | IA | [9 empty] | 2011-06-01 | 161 |  |  | 1 | Proposed
B | 1340 | 2006-10-06 | 1 | West | ALTW | Build a new Hazleton – Lore - Salem 345 kV line with a Lore 345/161 kV 335/335 MVA transformer (option 2) | Build a new Hazleton – Lore - Salem 345 kV line with a Lore 345/161 kV 335/335 MVA transformer (option 2) | IA | [9 empty] | 2011-06-01 | 345 | 161 | 59500000 | 2 | Proposed
B | 1345 | 2006-10-06 | 6 | West | ALTW | Replace the limiting facility of CTs and conductor inside the substations for Quad Cities-Rock Creek-Salem 345 kV line | Replace the limiting facility of CTs and conductor inside the substations for 345 kV line Quad Cities-Rock Creek-Salem so the line rating can be raised to the same as conductor rating between substations | IA | [9 empty] | 2011-06-01 | 345 |  | 150000 | 1 | Proposed
B | 1346 | 2006-10-06 | 7 | West | ALTW | Upgrade conductor inside the substation so the ratings of Rock Creek 345/161 kV transformer are 448 MVA limited by transformer | Upgrade conductor inside the substation so the ratings of Rock Creek 345/161 kV transformer are 448 MVA limited by transformer | IA | [9 empty] | 2011-06-01 | 345 | 161 | 100000 | 1 | Proposed
B | 1374 | 2006-10-12 |  | West | ALTW | Marshalltown - Stoney Point 115 kV line upgrade | Marshalltown - Stoney Point 115 kV line upgrade | IA | [9 empty] | 2010-06-01 | 115 |  | 6100000 | 1 | Planned
B | 78 | 2006-10-04 | 55 | Central | Ameren | Jefferson City Area Development | Moreau - Apache Flats 161 kV line, Loose Creek - Jefferson City 345 kV line, Jefferson City 345/161kV Transformer | MO |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 345 | 161 | 16467600 | 2 | Planned
B | 151 | 2005-07-11 | 129 | Central | Ameren | Buck Knob-Dupo Ferry-1 138 kV | Buck Knob-Dupo Ferry-1 138 kV - Reconductor line | IL |  |  | Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 5170600 | 1 | Proposed
B | 152 | 2006-10-04 | 130 | Central | Ameren | Big River-Rockwood 138 kV | Big River-Rockwood 138 kV - Construct new line | MO |  |  | Budgeted | Not Required | [5 empty] | 2010-06-01 | 138 |  | 12794000 | 1 | Proposed
B | 710 | 2006-10-04 |  | Central | Ameren | Kinmundy-Salem 138 kV | Kinmundy-Salem 138 kV - Increase ground clearance | IL |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 661200 | 1 | Proposed
B | 715 | 2006-10-04 |  | Central | Ameren | Wildwood-Gray Summit-1 138 kV | Wildwood-Gray Summit-1 138 kV - Reconductor line | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 64250 | 1 | Proposed
B | 716 | 2006-10-04 |  | Central | Ameren | Wildwood-Gray Summit-2 138 kV | Wildwood-Gray Summit-2 138 kV - Reconductor line | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 64250 | 1 | Proposed
B | 717 | 2005-07-11 |  | Central | Ameren | Conway-Tyson-3 138 kV | Conway-Orchard Gardens section of Conway-Tyson-3 138 kV - Increase ground clearance | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 100000 | 1 | Proposed
B | 718 | 2005-07-11 |  | Central | Ameren | Conway-Tyson-4 138 kV | Conway-Orchard Gardens section of Conway-Tyson-4 138 kV - Increase ground clearance | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 138 |  | 100000 | 1 | Proposed
B | 720 | 2006-10-04 |  | Central | Ameren | Page 138/34 kV Substation | Page 138/34 kV Substation - Replace 3-138 kV Breakers | MO |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-12-01 | 138 |  | 539400 | 1 | Proposed
B | 721 | 2005-07-11 |  | Central | Ameren | Wildwood 345/138 kV Substation | Wildwood 345/138 kV Substation - Add 2-345 kV Breakers | MO |  |  | Budgeted | Not Required | [5 empty] | 2009-06-01 | 345 |  | 1873200 | 1 | Proposed
B | 783 | 2005-07-11 |  | Central | Ameren | Robinson-Marathon 138 kV Substation | Robinson-Marathon 138 kV Substation - Increase 18 MvarCapacitor bank to 36 Mvar | IL |  |  | Budgeted | Not Required | [5 empty] | 2007-06-01 | 138 |  | 151900 | 1 | Proposed
B | 1233 | 2006-03-17 |  | Central | Ameren | Cahokia-Ashley-2 138 kV | Replace bus conductor and retap CTs | MO | [9 empty] | 2009-06-01 | 138 |  | 116300 | 1 | Proposed
B | 1235 | 2006-03-17 |  | Central | Ameren | Fredericktown-AECI Fredericktown | Increase ground clearance on 12 miles | MO | [9 empty] | 2009-06-01 | 161 |  | 970500 | 1 | Proposed
B | 1237 | 2006-03-17 |  | Central | Ameren | Cambell-Euclid-Page 138 kV | Rebuild 5.25 miles dbl-ckt. 138 kV | MO | [9 empty] | 2010-06-01 | 138 |  | 15254100 | 1 | Proposed
B | 1238 | 2006-03-17 |  | Central | Ameren | GM-Point Prairie 161 kV to AECI Enon Sub. | Extend 1 mile of 161 kV to AECI Enon Substation | MO | [9 empty] | 2010-06-01 | 161 |  | 1303500 | 1 | Proposed
B | 1240 | 2006-03-17 |  | Central | Ameren | Reconductor Sioux-Huster-1 and -3 138 kV | Reconductor 15 miles of Sioux-Huster-1 and 13 miles of Sioux-Huster-3 | MO | [9 empty] | 2010-12-01 | 138 |  | 1882100 | 2 | Proposed
B | 141 | 2006-03-17 | 119 | Central | AmerenCILCO | Duck Creek-Tazewell 345 kV | Duck Creek-Tazewell 345 kV - Convert bus duct to overhead | IL |  |  | Not Budgeted | Not Required |  |  | Other | Excluded | Y | 2009-06-01 | 345 |  | 119500 | 1 | Proposed
B | 874 | 2005-07-11 |  | Central | AmerenCILCO | East Springfield 138/69 kV Substation | East Springfield 138/69 kV Substation - Replace terminal equipment | IL | [9 empty] | 2009-06-01 | 138 |  | 344300 | 1 | Proposed
B | 734 | 2006-03-17 | 734 | Central | AmerenIP | Washington Street Substation Development | Washington Street Sub - Install ring bus and split S.Bloomington to Raab Rd. 138 kV Line 1326, tap 138 kV Line 1364. 138 kV Line 1364 - Reconductor from S. Bloomington Substation to Tower 512 | IL |  |  | Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 5760300 | 2 | Proposed
B | 737 | 2006-03-17 |  | Central | AmerenIP | Bluff City 138 kV Substation | Bluff City 138 kV Substation - Install 138 kV breaker | IL |  |  | Not Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 1756400 | 1 | Proposed
B | 866 | 2005-07-11 |  | Central | AmerenIP | Latham 345/138 kV Substation | Latham 345/138 kV Substation - Install 138 kV breaker for 'in-out' taps to 138 kV Line 1342, construct 0.38 miles 138 kV line for 'in-out' connections | IL | [9 empty] | 2007-06-01 | 138 |  | 1658000 | 1 | Proposed
B | 870 | 2005-07-11 |  | Central | AmerenIP | Sidney-Paxton 138 kV | Sidney-Paxton 138 kV - Reconductor 18 miles of 350 kcmil Cu | IL | [9 empty] | 2008-06-01 | 138 |  | 5690300 | 1 | Planned
B | 872 | 2005-07-11 |  | Central | AmerenIP | Mahomet-Champaign 138 kV Line 1592 | Mahomet-Champaign 138 kV Line 1592 - Reconductor 1.55 miles of 477 kcmil ACSR from Mahomet Substation to Twr. 29 | IL | [9 empty] | 2008-06-01 | 138 |  | 725500 | 1 | Proposed
B | 1234 | 2006-03-17 |  | Central | AmerenIP | Havana, South-Mason City, West 138 kV | Increase ground clearance on 18.4 miles | IL | [9 empty] | 2009-06-01 | 138 |  | 642300 | 1 | Proposed
B | 1236 | 2006-03-17 |  | Central | AmerenIP | Stallings-Prairie State Plant 345 kV | Replace 2000 A terminal equipment with 3000 A equipment | IL | [9 empty] | 2009-06-01 | 345 |  |  | 1 | Proposed
B | 1239 | 2006-03-17 |  | Central | AmerenIP | Normal, East-Brokaw 138 kV | Replace 600 A terminal equipment at Normal, East Sub. With 1200 A | IL | [9 empty] | 2010-06-01 | 138 |  |  | 1 | Proposed
B | 1351 | 2006-03-17 |  | Central | AmerenIP | Pana North - Decatur Rt. 51 L1462 | Pana North - Decatur Rt. 51 L1462 | [10 empty] | 2010-06-01 | 138 |  |  | 1 | Proposed
B | 175 | 2005-07-11 | 153 | West | ATC LLC | Ellinwood-Sunset Point 138 kV | Ellinwood - Sunset Point 138 ckt , Sum rate | WI |  |  | Not Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 2500000 | 1 | Planned
B | 333 | 2006-03-16 | newgrp12 | West | ATC LLC | Hiawatha-Indian Lake conversion to 138 kV and Hiawatha-Pine River-Mackinac conversion to 138 kV | Construct Mackinac 138 kV substation (new Straits substation) - 2007 Relocate 69 kV Rexton tap to 69 kV Hiawatha-Pine River line (6909) - 2009 Relocate 69 kV Trout Lake tap to 69 kV Hiawatha-Pine River line (6909) - 2009 Construct Mackinac 138 kV substation additions (portions may be earlier for maintenance issues) - 2009 Rebuild Hiawatha-Pine River-Mackinac 69 kV to 138 kV - 2009 Construct 138 kV bus and install one 138/69 kV, 50 MVA transformers at Pine River - 2009 Convert rebuilt Hiawatha-Indian Lake circuit (operated at 69 kV) to 138 kV - 2009 Construct 138 kV ring bus at Hiawatha SS - 2009 Install 138 kV substation modifications at Indian Lake SS - 2009 | WI |  |  | Pending | Not Required | No viable alternatives were considered for this project. |  | Other | Excluded | Y | 2009-05-01 | 138 |  | 6200000 | 3 | Proposed
B | 347 | 2005-07-11 | newgrp21 | West | ATC LLC | Rubicon-Hustisford-Horicon 138 kV | Construct a Rubicon-Hustisford 138 kV line, Rebuild Hustisford-Horicon 69 kV to 138 kV, Construct 138/69 kV substation at a site near Horicon and install a 138/69 kV transformer | WI |  |  | Pending | Required | Alternative 1: Conversion of Academy to South Beaver Dam line to 138 kV and New South Beaver Dam to Prospect Street Line Alternative 2: Rebuild and Conversion of South Fond Du Lac to Springbrook 69 kV line to to 138 kV |  |  |  |  | 2008-06-01 | 138 |  | 7200000 | 2 | Proposed
B | 356 | 2006-03-16 | newgrp6 | West | ATC LLC | Rockdale-West Middleton 345 kV | Construct 345 kV line from Rockdale to West Middleton, Construct a 345 kV bus and install a 345/138 kV 500 MVA transformer at West Middleton, Expand Rockdale 345 kV substation | WI |  |  | Pending | Pending | No other reasonable transmission alternatives exist, that is, numerous 138 kV facilities would need to be constructed in lieu of the preferred project. |  |  |  |  | 2011-06-01 | 345 | 138 | 72644254 | 3 | Proposed
B | 544 | 2005-07-11 | p2-104 | West | ATC LLC | Bluemound 200 MVAR capacitor bank | Bluemound 200 MVAR capacitors | WI | [9 empty] | 2008-06-01 | 138 |  | 3300000 | 1 | Proposed
B | 567 | 2005-07-11 | 567 | West | ATC LLC | North Appleton-Lawn Road-White Clay 138 kV uprate | North Appleton - Lawn Road - White Clay 138 kV line upgrade. This project increases line clearance on the 30 mile line. | WI |  |  | not budgeted | Not Required |  |  | Other | Excluded | Y | 2007-06-01 | 138 |  | 600000 | 2 | Planned
B | 574 | 2005-07-11 | 574 | West | ATC LLC | Monroe County - Council Creek 161 kV line projects | Monroe County - Council Creek 161 kV line, Council Creek 161/138 kV transformer; Petenwell-Saratoga 138 kV rebuild and Council Creek-Petenwell uprate 138 kV | WI |  |  | Pending | Required | [5 empty] | 2010-06-01 | 161 | 138 | 34200000 | 4 | Proposed
B | 880 | 2005-07-11 | new103 | West | ATC LLC | Lost Dauphin-North Appleton-Mason Street 138 kV uprates | Lost Dauphin-North Appleton-Mason Street 138 kV uprates | WI | [9 empty] | 2008-06-01 | 138 |  | 3300000 | 2 | Proposed
B | 882 | 2006-07-05 | new105 | West | ATC LLC | Octonagon 16.32 MVAR capacitor bank | Octonagon 16.32 MVAR capacitor bank | MI |  |  | Approved | Not Required | [5 empty] | 2007-06-01 | 138 |  | 1200000 | 1 | Proposed
B | 886 | 2005-07-11 | new109 | West | ATC LLC | North Lake (Cedar) sub relocation | North Lake (Cedar) substation relocation | MI |  |  | Approved | N/A | Rebuild existing Cedar substation in present location. |  |  |  |  | 2008-06-01 | 138 |  | 7300000 | 1 | Planned
B | 887 | 2005-07-11 | new110 | West | ATC LLC | Bain 345 kV bus | Bain 345 kV bus | WI | [9 empty] | 2009-06-01 | 345 |  | 2100000 | 1 | Proposed
B | 888 | 2005-07-11 | new111 | West | ATC LLC | Plains second 345/138 kV transformer | Plains second 345/138 kV transformer | MI | [9 empty] | 2008-06-01 | 345 | 138 | 5400000 | 1 | Proposed
B | 1256 | 2006-05-08 | 1256 | West | ATC LLC | Paddock - Rockdale 345kV | Paddock - Rockdale 345kV circuit #2 and supporting projects of lower voltage levels | WI |  |  | Proposed | Required | [5 empty] | 2010-04-01 | 345 |  | 126500000 | 4 | Proposed
B | 1267 | 2006-07-05 | new1 | West | ATC LLC | New Oak Ridge-Verona 138-kV line and a 138/69-kV transformer at Verona | Construct new Oak Ridge-Verona 138-kV line and install a 138/69-kV transformer at Verona | WI | [9 empty] | 2009-06-01 | 138 |  | 17900000 | 1 | Proposed
B | 1269 | 2006-07-05 | new3 | West | ATC LLC | Arcadian transformer replacement | Replace Arcadian 345/138kV transformer #3 with a 500MVA transformer. | WI |  |  | Proposed | not required | [5 empty] | 2011-06-01 | 345 | 138 | 3500000 | 1 | Proposed
B | 1270 | 2006-07-05 | new4 | West | ATC LLC | Upgrade Arcadian - Waukesha 138kV lines | Increase clearances of the two Arcadian - Waukesha 138kV lines | WI |  |  | Not Budgeted | Not Required | [5 empty] | 2011-06-01 | 138 |  |  | 2 | Proposed
B | 1271 | 2006-07-05 | new5 | West | ATC LLC | Upgrade Oak Creek - Pennsylvania 138kV line | Increase clearance of the Oak Creek - Pennsylvania 138kV line | WI |  |  | Not Budgeted | Not Required | [5 empty] | 2011-06-01 | 138 |  |  | 1 | Proposed
B | 1279 | 2006-08-31 | 1 | West | ATC LLC | North Beaver Dam 49 MVAR cap bank | install two 24.5 MVAR cap bank at North Beaver Dam | WI | [9 empty] | 2009-06-01 | 138 |  | 1800000 | 1 | Proposed
B | 1281 | 2006-08-31 | 3 | West | ATC LLC | uprate the Portage to Trienda X-19 to 293/339 MVA | uprate the Portage to Trienda X-19 to 293/339 MVA | WI | [9 empty] | 2008-06-01 | 138 |  | 1031249 | 1 | Proposed
B | 1284 | 2006-08-31 | 5 | West | ATC LLC | Tie the 138kV radial line Racine - Somers - Albers to the 138kV substation at Albers. Also upgrade the 138kV radial line to 345/477 summer normal/emergency ratings. | Tie the 138kV radial line Racine - Somers - Albers to the 138kV substation at Albers. Also upgrade the 138kV radial line to 345/477 summer normal/emergency ratings. | WI | [9 empty] | 2010-06-01 | 138 |  | 4181904 | 4 | Proposed
B | 1450 | 2006-10-27 |  | West | ATC LLC | Cornell (4.5 ohm reactor) on Cornell - Fiebrantz138 kV line | Cornell (4.5 ohm reactor) on Cornell - Fiebrantz138 kV line | MN |  | 0 | [7 empty] | 2008-06-01 | 138 |  | 4651493 | 1 | Proposed
B | 618 | 2005-07-11 |  | Central | CIN | Beckjord 138 Reconfigure | Rebuild the Beckjord 138 Substation so it can be tied together under normal conditions. | OH |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2009-12-31 | 138 |  | 1738266 | 1 | Proposed
B | 625 | 2006-07-05 |  | Central | CIN | Pierce/Beckjord 345/138 kV transformer addition | Add 3rd 345/138kV transformer, 400MVA, from Pierce 345kV bus to Beckjord 138kV North bus. | OH |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2008-06-01 | 345 | 138 | 2527029 | 1 | Proposed
B | 852 | 2006-07-05 | AU | Central | CIN | Crawfordsville to Tipmont Concord to Lafayette SE 138 Reconductor | Reconductor 13819 circuit with 954ACSR 100C. | IN |  |  | Approved | Not required | [5 empty] | 2009-12-31 | 138 |  | 8567189 | 2 | Planned
B | 1264 | 2006-07-05 | 702G6714 | Central | CIN | Speed | Replace existing 345/138 transformer at Speed with a new transformer rated at 3,000A or higher. | IN |  |  |  | Not required | [5 empty] | 2011-06-01 | 345 | 138 | 5000000 | 1 | Proposed
B | 1317 | 2006-09-11 | COH-05-050318-152342 | East | FE | Hayes Substation | Hayes Substation installed to split the Greenfield to Avery and Greenfield to Beaver 138 kV lines as well as the Davis Besse to Beaver 345 kV line. The 345 kV system will be tied into the 138 kV system via a 345/138 kV transformer at this substation. | OH |  |  | Not Budgeted | Not Required | [5 empty] | 2009-06-01 | 345 | 138 | 11000000 | 2 | Proposed
B | 1324 | 2006-09-13 | N/A yet | East | FE | recond. Walbridge Jct.-Maclean | Increaes conductor size from 636 ACSR 26/7, possibly with 477 ACSS/TW conductors | OH |  |  | Not Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 247900 | 1 | Proposed
B | 1339 | 2006-10-05 | EOH-06-050805-134827 | East | FE | Maysville Substation - Add 138 kV Capacitor Bk. | Add 1 - 50 MVAR Cap Bank with 1 - 138 kV Breaker | OH |  |  | Not Budgeted | Not Required | [5 empty] | 2010-06-01 | 138 |  | 451700 | 1 | Proposed
B | 599 | 2005-06-15 |  | West | GRE | Crooked Lake - Enterprise Park 115 kV line | Crooked Lake - Enterprise Park 115 kV line | MN | [6 empty] | Other | Excluded | Y | 2009-06-01 | 115 |  | 3600000 | 1 | Planned
B | 600 | 2005-06-15 |  | West | GRE | Baxter - Southdale 115 kV line | Baxter - Southdale 115 kV line | MN | [6 empty] | Other | Excluded | Y | 2008-06-30 | 115 |  | 3500000 | 1 | Planned
B | 1018 | 2004-12-23 |  | West | GRE | Little Falls - Pierz conversion to 115 kV | Convert Little Falls - Pierz 34 kV line to 115 kV operation | MN | [9 empty] | 2011-06-01 | 115 |  | 900000 | 1 | Proposed
B | 1354 | 2006-10-15 |  | West | GRE | Dotson -Storden 161 and Dotson - Searles 161 | Dotson -Storden 161 and Dotson - Searles 161 | MN | [9 empty] | 2010-05-01 | 161 | 115 |  | 3 | proposed
B | 603 | 2005-06-15 |  | West | GRE/XEL | Alexandria - West St. Cloud 115 kV line | Alexandria - West St. Cloud 115 kV line | MN | [9 empty] | 2011-06-01 | 115 |  | 36954688 | 1 | Proposed
B | 204 | 2005-06-15 | 183 | Central | HE | Tapline 138 to Buena Vista, Batesville, & North Charleston | Buena Vista-Tapline 138, Batesville-Tapline 138, North Charleston-Tapline 138 | IN | [9 empty] | 2009-06-01 | 138 |  | 1850000 | 2 | Proposed
B | 694 | 2005-06-15 | ITC9 | East | ITC | Saratoga Station | Saratoga 345/120 kV switching station | MI | [9 empty] | 2009-12-31 | 345 | 120 | 29600000 | 10 | Proposed
B | 900 | 2005-08-10 | aa | East | ITC | Duvall Tie | Construct a section breaker at Duvall station to tie buses 101 and 102 together. Also construct addition 0.8 miles of wood poles to establish a Hager to Hines 120 kV circuit | MI |  |  | Pending | Pending | [5 empty] | 2008-12-31 | 120 |  | 2600000 | 3 | Proposed
B | 902 | 2005-08-10 | cc | East | ITC | Greenwood 345/120 Xmfr | Puts in new 345/120 kV Xfmr at Greenwood and constructs new Greenwood-Wabash 120 kV and Greenwood-Adams 120 kV | MI |  |  | none | [6 empty] | 2008-12-31 | 345 | 120 | 12000000 | 3 | Proposed
B | 903 | 2005-08-10 | dd | East | ITC | Stephens - Bismark | Creates a Bismark-Stephens 230 kV line with a 230/120 kV Xfmr at Stephens, and also builds a new Stephens-Redrun 120 kV | MI |  |  | none | [6 empty] | 2008-12-31 | 230 | 120 | 9000000 | 3 | Proposed
B | 908 | 2005-08-10 | ii | East | ITC | Lulu Station | Phase One - Construct a 345 kV switching station at the Lulu site, including 8 345 kV breakers and Cut in the Majestic - Lemoyne 345 kV circuit into new Lulu station and the Milan-Allen Junction-Monroe 3-4 345 kV circuit into new Lulu station. Phase Two - Split the Lulu to Lemoyne 345 kV circuit into a Lulu to Monroe 1-2 345 kV circuit and a Leymoyne to Monroe 3-4 345 kV circuit, creating a new 3 mile 345 kV double circuit tower line. | MI |  |  | none | [6 empty] | 2008-05-30 | 345 |  | 24000000 | 7 | Proposed
B | 909 | 2005-08-10 | jj | East | ITC | 230 kV Northwest | Tap one of the METC Thetford to Hampton 345 kV circuits west of the ITC Atlanta 120 kV station, build a new 2.3 mile 345 kV line from the tap to the Atlanta station, install a 345/230 kV transformer at Atlanta, build a new 13.6 mile 230 kV circuit from Atlanta to the Tuscola station, install a 230/120 kV transformer at Tuscola, convert 22.5 mile 120 kV circuit from Tuscola down to a new 345 kV switching station at the Hunters Creek station to 230 kV, install a 345/230 kV transformer and a 230/120 kV transformer at Hunters Creek, and tap the Belle River to Blackfoot 345 kV circuit at Hunters Creek. | MI |  |  | none | [6 empty] | 2010-05-30 | 345 | 120 | 48000000 | 11 | Proposed
B | 910 | 2005-08-10 | kk | East | ITC | Coventry Station upgrade | Constructs new Coventry-Cody 230 kV line using the same right-of-way currently occupied by the Coventry-Cody 120 kV circuit. Project involves constructing a new 345/230 kV tranformer at Coventry along with a 230/120 kV transformer at Cody. Project also invloves expansion of the Coventry 345 kV station. | MI |  |  | Pending | [6 empty] | 2007-12-31 | 345 | 120 | 20000000 | 4 | Planned
B | 1011 | 2006-07-05 | ITC22 | East | ITC | Durant-Genoa 120 kV | Builds a new 120 kV Durant sub-station with a new circuit from Genoa to Durant, and also breaks up 3-ended Prizm-Proud-Placid 120 kV line | MI |  |  | Pending | [6 empty] | 2006-12-31 | 120 |  | 12500000 | 3 | Planned
B | 1012 | 2005-08-10 | zz | East | ITC | Wyane - Newburg Split | Split existing six-wired 120 kV circuit from Wayne to Newburg creating a new 2.8 mile 120 kV circuit. | MI |  |  | Pending | [6 empty] | 2007-05-30 | 120 | 120 | 1200000 | 1 | Proposed
B | 1295 | 2006-08-28 |  | East | ITC | Quaker - Southfield | Adds a new 120 kV circuit from the Quaker station to the Southfield station. | MI |  |  | Proposed |  | Under Study |  |  |  |  | 2010-06-30 | 120 |  |  | 1 | Proposed
B | 1302 | 2006-08-16 | ITC24 | East | ITC | Hines and Walton Station Equipment Replacement | Replaces equipment and buses at Hines and Walton Stations to increase thermal ratings to relieve overloads | MI |  |  | Approved | needs review | [5 empty] | 2007-05-31 | 120 |  | 1500000 | 2 | Planned
B | 1303 | 2006-08-16 | ITC25 | East | ITC | Arrowhead Ring Bus | Creates a new ring bus configuration at Arrowhead station | MI |  |  | Approved | needs review | [5 empty] | 2007-05-31 | 120 |  | 4000000 | 1 | Planned
B | 1308 | 2006-08-16 | ITC30 | East | ITC | B3N Interconnection | Returns the Bunce Creek to Scott 220 kV circuit to service, and replaces the Phase Angle Regulator with 2 new PARs in series | MI |  |  | Approved | needs review | [5 empty] | 2007-12-31 | 220 |  | 25500000 | 2 | Planned
B | 247 | 2005-06-15 | TRN.610.06 | West | LES | North Tier 345 kV | A 26-mile 345-kV line extending from the LES owned Wagener Substation to the LES owned NW68th & Holdrege Substation. | NE |  |  | Budgeted | Required | The existing NPPD owned Pauline - Moore 345-kV line was an alternative in the form of a Pauline - NW68th & Holdrege 345-kV line. |  | Other | Excluded | Y | 2008-12-31 | 345 |  | 28077000 | 1 | Planned
B | 805 | 2006-09-29 | TRN.610.03 | West | LES | NW68th & Holdrege 345/115 kV #2 | Add 2nd NW68th & Holdrege 345/115 kV transformer, rate 336 MVA | NE |  |  |  | Not Required | [5 empty] | 2010-05-01 | 345 | 115 | 3300000 | 1 | Proposed
B | 1381 | 2006-10-10 | TRN.450.00 | West | LES | SW Lincoln 115 kV Transmission | Rebuild Sheldon line #1197, re-terminate Sheldon line #1099, add a 115kV substation, and make other related transmission modifications. | NE |  |  | Approved | Not Required | [5 empty] | 2011-05-01 | 115 |  | 4540001 | 6 | Planned
B | 1355 | 2006-10-15 |  | West | MDU | Heskett - Additional 230/115 kV Switchyard and 115 kV Capacitor | Heskett - Additional 230/115 kV Switchyard 230 115 Switchyard in parallel w/ existing Heskett switchyard | ND | [9 empty] | 2009-11-01 | 230 | 115 |  | 2 | Planned
B | 1356 | 2006-10-15 |  | West | MDU | Glenham - Reactors 230 115 Control high voltage on WAPA Bismarck - Oahe 230 kV line | Glenham - Reactors 230 115 Control high voltage on WAPA Bismarck - Oahe 230 kV line | ND | [9 empty] | 2009-11-01 | 230 | 115 |  | 1 | Proposed
B | 240 | 2005-07-27 | 87 | East | METC | Garfiled - Hemphill 138 ckt 1 | Garfiled - Hemphill 138 ckt 1, Sum rate 521 | MI |  |  | Not Budgeted | Not Required |  |  | Other | Excluded | Y | 2011-06-01 | 138 |  | 1900000 | 1 | Proposed
B | 494 | 2006-09-29 | 58 | East | METC | Battle Creek - Verona 138kV #1 Line | Remove Sag Limit | MI |  |  | Budgeted | Not Required |  |  | Other | Excluded | Y | 2007-12-01 | 138 |  | 50000 | 1 | Proposed
B | 643 | 2006-09-29 | 60 | East | METC | Gaines - Thompson Road 138 ckt # 1 | Gaines - Thompson Road 138 ckt # 1 | MI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-03-01 | 138 |  | 1425000 | 1 | Under Construction
B | 648 | 2005-07-27 | 75 | East | METC | Various Distribution Connections 138 ckt # 1 | Various Distribution Connections 138 ckt # 1 | MI |  |  | Budgeted | Not Required | [5 empty] | 2007-06-01 | 138 |  | 2000000 | 1 | Proposed
B | 653 | 2005-07-27 | 88 | East | METC | Various Distribution Connections 138 ckt # 1 | Various Distribution Connections 138 ckt # 1 | MI |  |  | Budgeted | Not Required | [5 empty] | 2008-06-01 | 138 |  | 2000000 | 1 | Proposed
B | 663 | 2005-07-27 | 105 | East | METC | Various Distribution Connections 138 ckt # 1 | Various Distribution Connections 138 ckt # 1 | MI |  |  | Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 2000000 | 1 | Proposed
B | 740 | 2006-07-05 | 41, 44, 45, 46 | East | METC | 345 kV line relaying and communications upgrade project - Phase 1 | Phase 1 Upgrade 345 kV line relaying and communications on Gallagher - Tittabawassee, Keystone - Livingston, and Livingston - Gallagher lines. | MI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2007-03-01 | 345 |  | 2794000 | 3 | Planned
B | 776 | 2005-07-27 | 76 | East | METC | Various 138 kV 72 MVAR Capacitors | Various 138 kV 72 MVAR Capacitors | MI |  |  | Budgeted | Not Required | [5 empty] | 2007-06-01 | 138 |  | 2000000 | 1 | Proposed
B | 777 | 2005-07-27 | 89 | East | METC | Various 138 kV 72 MVAR Capacitors | Various 138 kV 72 MVAR Capacitors | MI |  |  | Budgeted | Not Required | [5 empty] | 2008-06-01 | 138 |  | 2000000 | 1 | Proposed
B | 984 | 2005-07-27 | 114 | East | METC | Denver 345/138 kV station | Build new 345/138 kV station, 50 miles 345 kV line, 60 miles 138 kV lines | MI | [9 empty] | 2011-06-01 | 345 |  | 77132000 | 1 | Proposed
B | 1409 | 2006-10-25 | 159 | East | METC | System Spare Transformer | Install a spare 345/138kV transformer at Tittabawasee | MI |  |  | Approved | Not Required | [5 empty] | 2007-06-01 | 345 | 138 | 2600000 | 1 | Planned
B | 1433 | 2006-10-25 | 181 | East | METC | Buskirk | Install bulk substation served from the Beals-Hazelwood 138kV Line | MI |  |  | Budgeted | Not Required | [5 empty] | 2008-06-01 | 138 |  | 2200000 | 1 | Proposed
B | 1434 | 2006-10-25 | 182 | East | METC | Five Mile | Install bulk substation served from the Spaulding 138kV ring bus | MI |  |  | Budgeted | Not Required | [5 empty] | 2008-06-01 | 138 |  | 750000 | 1 | Proposed
B | 1441 | 2006-10-25 | 189 | East | METC | Ellis (Hile Road) | Install bulk substation served from a new Ellis spur from Sternberg | MI |  |  | Budgeted | Not Required | [5 empty] | 2009-06-01 | 138 |  | 3250000 | 1 | Proposed
B | 1445 | 2006-10-25 | 193 | East | METC | Emmet | Install a second distribution transformer at Emmet | MI |  |  | Budgeted | Not Required | [5 empty] | 2010-06-01 | 138 |  | 2750000 | 1 | Proposed
B | 1447 | 2006-10-25 | 195 | East | METC | Horseshoe Creek (Deja) | Install bulk substation served from the Eureka-Deja-Vestaburg 138kV Line | MI |  |  | Budgeted | Not Required | [5 empty] | 2010-06-01 | 138 |  | 2200000 | 1 | Proposed
B | 291 | 2006-03-24 | 291 | West | MH | Great Falls & Pine Falls-Bloodvein Improvements | Replacement lines and equipment to existing 66 kV and upgrade to 115 kV supplies | Manitoba |  |  | Budgeted | Pending |  |  | TBD | TBD | N/A | 2011-11-01 | 115 |  | 23107160.0184 | 2 | Proposed
B | 604 | 2006-03-24 | 604 | West | MH | Flin Flon Area Transmission Improvements Phase II | Transmission: Design and construct 6 km of single circuit, 115 kV line between Herblet Lake station and Chisel Lake disconnect switch 1521. Upgrade 73 km of HS15 between Herblet Lake and Sherridon Station. Fix towers and insulators where required and clean up right of way. Salvage 65 km of 115 kV line HS15 between I1F/12F tap and Sherridon station. At Herblet Station, build a wood pole 115 kV line and provide a provision for temporarily connecting H59C to the 115 kV line HS15. At Cliff Lake station build a wood pole 115 kV line and provide a provision for temporarily connecting bank 3 secondary to line H59C Station: De-commission and salvage the Mile 13 station. Salvage 230-115-13.8 kV 30/40/45 MVA station service transformer at Ponton station. Relocate Ponton 30/40/45 MVA transformer bank to Herblet Lake station. Co-terminate the transformer on the 230 kV side and add one 115 kV breaker and associated equipment. At Cliff Lake station install/modify bank 3 protection equipment as required. Increase the capacity of communication diesel generating facilities and use as the permanent back-up local service supply for Ponton station. | Manitoba |  |  | Budgeted | Pending | Alternative to the 115 kV line from Herblet Lake to the Chisel Lake tap to provide a dedicated supply to Sherridon: 1. Supply Sherridon station via new 25 kV distribution facilities from Snow Lake station. This option was rejected because it would have resulted in longer outages and allowed for no load growth at Sherridon. Alternatives to the relocation of the Ponton 50 MVA, 230 – 115 kV transformer to Herblet Lake station: 1. Purchase and install a new 230 – 115 kV transformer at Herblet Lake station. 2. Relocate Cliff Lake Bank 3 to Herblet Lake station. Alternative to the Ponton station service equipment: 1. Purchase and install a new 230 kV – 120 V power voltage transformer a Ponton station. All of the above alternatives were not pursued because they would have resulted in increased complexity and cost. |  | TBD | TBD | N/A | 2008-03-01 | 115 |  | 11463675.6594 | 2 | Proposed
B | 912 | 2006-06-28 | 2 | West | MH | Point du Bois Generating Station Rehabilitation/Redevelopment | Point du Bois - Rover 115 kV new line will replace aging existing two 66 kV lines | Manitoba |  |  | Pending | Required |  |  | TBD | TBD | N/A | 2010-05-01 | 115 |  | 24803532.3607 | 1 | Proposed
B | 915 | 2006-06-28 | 5 | West | MH | Selkirk Area Improvements | This project consists of a new 230 kV line from Rosser to Parkdale and development of a new 230/110 kV station to replace the existing Parkdale station. Rosser 230-115 kV Transformer Upgrade, 176 to 250 MVA | Manitoba |  |  |  | Required |  |  | TBD | TBD | N/A | 2007-04-30 | 230 | 115 | 2464590.26 | 1 | Proposed
B | 917 | 2006-06-28 | 7 | West | MH | Southwest Winnipeg Transmission Improvements | re-conductor of section of St Vital -LaVerendrye(YV5) 115 to increase Sum rate to 178.9 MVA and reconfigure lines VH2 & XS49 | Manitoba |  |  | Pending | Required |  |  | TBD | TBD | N/A | 2007-03-31 | 115 |  | 682640.69 | 3 | Proposed
B | 1013 | 2006-06-28 | 1 | West | MH | Neepawa 230 - 66 kV Station | A new 230/66 kV station is to be built which will include sectionalizing Line D54C into the station, a 230/66kV, 90 MVA transformer & new 230 and 66 kV ring busses | Manitoba |  |  | Pending | Required |  |  | TBD | TBD | N/A | 2011-10-31 | 230 |  | 32925183.9082 | 2 | Proposed
B | 1383 | 2006-10-25 |  | East | MISO/FE | Richland area upgrades (ITC imports) | Reconductoring and terminal upgrades on Richland - Naomi and Richland - Ridgville 138 kV line in FE area | OH | [9 empty] | 2009-06-01 | 138 |  | 5000000 | 2 | Proposed
B | 277 | 2005-06-15 | 272 | West | MP | Badoura Project | Badoura - Pequot Lakes 115 ckt 1, Sum rate 182 | MN |  |  | Approved | Pending | [5 empty] | 2008-06-30 | 115 |  |  | 1 | Planned
B | 1286 | 2006-08-24 | 8 | West | MP | Add a 15 Mvar capacitor bank at Two Harbors in 2007 | Add a 15 Mvar capacitor bank at Two Harbors in 2007 | MN | [9 empty] | 2007-06-01 | 115 |  |  | 1 | Proposed
B | 1292 | 2006-08-24 | 14 | West | MP | Raise tower height on ETCO-Forbes 115 kV line | Raise tower height on ETCO-Forbes 115 kV line so the 336 ACSR conductor rating can reach 122/134 MVA | MN | [9 empty] | 2011-06-01 | 115 |  |  | 1 | Proposed
B | 1359 | 2006-10-15 |  | West | MP | International Falls - Capacitor 115 add new | International Falls - Capacitor 115 add new | MN | [9 empty] | 2007-06-30 | 115 |  | 245000 | 1 | Proposed
B | 1360 | 2006-10-15 |  | West | MP | Two Harbors - Capacitor 115 add new | Two Harbors - Capacitor 115 add new | MN | [9 empty] | 2007-12-30 | 115 |  | 350000 | 1 | Proposed
B | 1021 | 2005-08-29 |  | West | MP/GRE | Embararss to Tower 115 kV Line | 115 kV line from 34L tap to Tower 46 kV | MN |  |  |  |  | generation or 46 kV line |  |  |  |  | 2008-11-01 | 115 |  | 7314000 | 1 | Proposed
B | 1022 | 2005-08-29 |  | West | MP/GRE | Badoura-Long Lake 115 kV line | 115 kV line from MP Badoura to GRE Long Lake | MN |  |  |  |  | Akeley to Long Lake |  |  |  |  | 2009-11-01 | 115 |  | 8621000 | 1 | Proposed
B | 1361 | 2006-10-15 |  | West | MP/GRE | Badoura - Pine River 115 and Badoura - Birch Lake 115 lines | Badoura - Pine River 115 and Badoura - Birch Lake 115 lines | MN | [9 empty] | 2009-06-30 | 115 |  |  | 2 | Planned
B | 612 | 2006-10-03 | 9325101 | East | NIPS | Hiple - Add 2nd 345-138 kV Transformer | Install a 2nd 345/138 kV 560 MVA transformer, associated breakers and bus at F.G. Hiple Substation. | IN | [9 empty] | 2008-05-01 | 345 | 138 | 3992400 | 1 | Proposed
B | 922 | 2006-10-03 | 71C6331 | East | NIPS | Michigan City to Luchtman Rd -Upgrade Capacity | Increase circuit capacity between Michigan City Gen. Station and Luchtman Road (5 mi.). Upgrade to 954 KCM ACSR and 316 MVA rating. | IN | [9 empty] | 2007-05-01 | 138 |  | 1705400 | 1 | Proposed
B | 549 | 2005-07-29 | p2-108 | West | OTP | Jamestown Reactor Addition | Jamestown 115 kV 25 MVAR reactor | ND | [9 empty] | 2008-01-01 | 115 |  | 436672 | 1 | Proposed
B | 971 | 2005-07-29 | OTP1 | West | OTP/MPC | Winger 230/115 kV Transformer Upgrade | Winger 230/115 kV Transformer upgrade | MN |  |  | Pending | Pending | Add a 2nd Transformer or replace existing transformer with a larger unit. |  |  |  |  | 2010-12-31 | 230 | 115 | 3715350.8388 | 1 | Proposed
B | 1007 | 2006-06-29 |  | Central | Vectren (SIGE) | New 345 kV transmission line Duff to Culley to Smith (OMU) | New 345 kV transmission line Duff to Culley to Smith (OMU) | IN | KY |  | Budgeted |  | Project 1006: New 345 kV transmission line Culley to Knottsville (BREC/LGEE). Projects 1006 and 1007 are mutually exclusive |  |  |  |  | 2009-12-31 | 345 | 138 | 54900000 | 3 | Planned
B | 1023 | 2006-06-29 |  | Central | Vectren (SIGE) | Blue Grass 138/69 kV substation and Blue Grass - Elliot 138 kV line | Blue Grass 138/69 kV substation will tap new Francisco - Northwest and Northeast 138 kV lines and have a new line from Blue Grass to Elliot | IN |  |  | Budgeted | [6 empty] | 2009-05-31 | 138 |  | 3900000 | 1 | Planned
B | 1209 | 2006-02-10 | 2007-01 | East | WPSC | Hersey 69KV Ring Bus | Convert 6 breaker bus at Hersey to Ring Bus | MI |  |  | Budgeted | Pending | [5 empty] | 2007-08-01 | 69 |  | 2300000 | 1 | Proposed
B | 1210 | 2006-02-10 | 2007-02 | East | WPSC | Lewiston II Breaker Station | Add a 69KV breaker in the line from Atlanta to Gaylord | MI |  |  | Budgeted | Pending | [5 empty] | 2007-08-01 | 69 |  | 520000 | 1 | Proposed
B | 1211 | 2006-02-10 | 2007-03 | East | WPSC | Grand Traverse - Grawn Line Rebuild | Line Rebuild to 795ACSR for future 138KV operation | MI |  |  | Budgeted | Pending | [5 empty] | 2007-08-01 | 69 |  | 1200000 | 1 | Proposed
B | 1212 | 2006-02-10 | 2007-04 | East | WPSC | Alpine - Gaylord Line Re-rate | Rerate line to 75C | MI |  |  | Budgeted | Pending | [5 empty] | 2007-08-01 | 69 |  | 400000 | 1 | Proposed
B | 1213 | 2006-02-10 | 2007-05 | East | WPSC | Vestaburg Capacitor Bank | Add 6MVAR Capacitor Bank at Vestaburg Substation | MI |  |  | Budgeted | Pending | [5 empty] | 2007-08-01 | 69 |  | 3000 | 1 | Proposed
B | 1214 | 2006-02-10 | 2008-01 | East | WPSC | Garfield - Grawn Line Rebuild | Line Rebuild to 795ACSR for future 138KV operation | MI |  |  | Budgeted | Pending | [5 empty] | 2008-08-01 | 69 |  | 1700000 | 1 | Proposed
B | 1215 | 2006-02-10 | 2008-02 | East | WPSC | Advance - Wilson Line Re-rate | Rerate line to 75C | MI |  |  | Budgeted | Pending | [5 empty] | 2008-08-01 | 69 |  | 200000 | 1 | Proposed
B | 1216 | 2006-02-10 | 2008-03 | East | WPSC | Garfield - Hall Street Line Re-rate | Rerate line to 75C | MI |  |  | Budgeted | Pending | [5 empty] | 2008-08-01 | 69 |  | 150000 | 1 | Proposed
B | 1217 | 2006-02-10 | 2008-04 | East | WPSC | Grawn 69KV Ring Bus | Convert 4 breaker bus at Grawn to Ring Bus | MI |  |  | Budgeted | Pending | [5 empty] | 2008-08-01 | 69 |  | 1900000 | 1 | Proposed
B | 1218 | 2006-02-10 | 2009-01 | East | WPSC | Atlanta 69KV Ring Bus | Convert 4 breaker bus at Atlanta to Ring Bus | MI |  |  | Budgeted | Pending | [5 empty] | 2009-08-01 | 69 |  | 1900000 | 1 | Proposed
B | 1219 | 2006-02-10 | 2009-02 | East | WPSC | Lake County - Star Lake Line Rebuild | Line Rebuild to 795ACSR for future 138KV operation | MI |  |  | Budgeted | Pending | [5 empty] | 2009-08-01 | 69 |  | 1800000 | 1 | Proposed
B | 1220 | 2006-02-10 | 2009-03 | East | WPSC | Copemish - Bass Lake Line Rerate | Rerate line to 75C | MI |  |  | Budgeted | Pending | [5 empty] | 2009-08-01 | 69 |  | 1200000 | 1 | Proposed
B | 1221 | 2006-02-10 | 2010-01 | East | WPSC | Redwood - New Era Line Rebuild | Line Rebuild to 795ACSR for future 138KV operation | MI |  |  | Budgeted | Pending | [5 empty] | 2010-08-01 | 69 |  | 1500000 | 1 | Proposed
B | 1222 | 2006-02-10 | 2010-02 | East | WPSC | Lake County - Star Lake Line Rebuild | Convert 4 breaker bus at Lake County to Ring Bus | MI |  |  | Budgeted | Pending | [5 empty] | 2010-08-01 | 69 |  | 3800000 | 1 | Proposed
B | 1273 | 2006-07-27 | 2007-09 | East | WPSC | Alpine to Elmira Line Re-rate | Rerate the line from Alpine Sub to Elmira Sub for an operating temperature of 75C | MI |  |  | Pending | Not Required | [5 empty] | 2007-10-01 | 69 |  | 200000 | 1 | Proposed
B | 1274 | 2006-07-27 | 2007-10 | East | WPSC | Allendale to Blendon Line Re-rate | Rerate the line from Allendale Sub to Blendon Sub for an operating temperature of 75C | MI |  |  | Pending | Not Required | [5 empty] | 2007-10-01 | 69 |  | 150000 | 1 | Proposed
B | 1275 | 2006-07-27 | 2007-11 | East | WPSC | Boyne City to Wilson Line Re-Rate | Rerate the line from Boyne City Sub to Wilson Sub for an operating temperature of 75C | MI |  |  | Pending | Not Required | [5 empty] | 2007-10-01 | 69 |  | 200000 | 1 | Proposed
B | 1276 | 2006-07-27 | 2010-04 | East | WPSC | Burnips to Goodwin Line Re-Rate | Rerate the line from Burnips Sub to Goodwin Sub for an operating temperature of 75C | MI |  |  | Pending | Not Required | [5 empty] | 2010-10-01 | 69 |  | 900000 | 1 | Proposed
B | 1277 | 2006-07-27 | 2011-01 | East | WPSC | Wayland to Goodwin Line Re-Rate | Rerate the line from Wayland Sub to Goodwin Sub for an operating temperature of 75C | MI |  |  | Pending | Not Required | [5 empty] | 2011-10-01 | 69 |  | 350000 | 1 | Proposed
B | 1278 | 2006-08-04 | 2007-12 | East | WPSC | North Shade 6MVAR Cap Bank | Add 6MVAR capacitor bank to North Shade substation | MI |  |  | Proposed | Not Required | [5 empty] | 2007-10-01 | 69 |  | 150000 | 1 | Proposed
B | 1299 | 2006-09-01 | 2011-02 | East | WPSC | Lake County 168MVA Transformer | Replace 75MVA Transformer with 168MVA Transformer at Lake County Substation. | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-01 | 69 |  | 2600000 | 1 | Proposed
B | 1311 | 2006-09-07 | 2011-05 | East | WPSC | Copemish - Karlin line rerate | Rerate line to 75C | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-01 | 69 |  | 1400000 | 1 | Proposed
B | 1312 | 2006-09-07 | 2011-06 | East | WPSC | Grawn - Karlin line rerate | Rerate line to 75C | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-02 | 69 |  | 650000 | 1 | Proposed
B | 1313 | 2006-09-07 | 2011-07 | East | WPSC | Baldwin - Plains X line rerate | Rerate line to 75C | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-03 | 69 |  | 700000 | 1 | Proposed
B | 1314 | 2006-09-07 | 2011-08 | East | WPSC | Plains X - Star Lake line rerate | Rerate line to 75C | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-04 | 69 |  | 700000 | 1 | Proposed
B | 1315 | 2006-09-07 | 2011-09 | East | WPSC | Potter - Grand Traverse line rerate | Rerate line to 75C | MI |  |  | Pending | Not Required. | [5 empty] | 2011-08-05 | 69 |  | 225000 | 1 | Proposed
B | 675 | 2006-07-12 |  | West | XEL | Rebuild Westgate to Scott County 69 kV to 115 kV | Upgrade 20.1 miles Westgate-Deephaven-Excelsior-Scott County 69kV to 115 kV using 795 ACSS conductor, Upgrade 2 miles Westgate-Eden Prairie 115kV #1 and #2 to 400MVA (PrjID 606), Substation work at Deephaven, Excelsior and Scott County. | MN |  |  | Not Budgeted | Required | 115 kV Westgate to Glen Lake to Gleason Lake |  |  |  |  | 2009-06-01 | 115 |  | 14000000 | 1 | Proposed
B | 1285 | 2006-08-24 | 7 | West | XEL | Build 18 miles 115 kV line from Glencoe - West Waconia | Build 18 miles 115 kV line from Glencoe - West Waconia | MN | [9 empty] | 2011-06-01 | 115 |  |  | 1 | Proposed
B | 1296 | 2006-08-24 | 16 | West | XEL | Add a breaker at 5P52 at Long Lake, removes the multi-terminal category B contingency | Add a breaker at 5P52 at Long Lake, removes the multi-terminal category B contingency | MN | [9 empty] | 2011-06-01 | 115 |  |  | 1 | Proposed
B | 1297 | 2006-08-24 | 15 | West | XEL | Reconductor Monticello - Oakwood - Hassan 115 kV line | Reconductor Monticello - Oakwood - Hassan 115 kV line with 795 ACSS | MN | [9 empty] | 2011-06-01 | 115 |  |  | 2 | Proposed
B | 1365 | 2006-10-15 |  | West | XEL | Edina - Eden Prairie 115 Reconductor | Edina - Eden Prairie 1 115 Reconductor | MN | [9 empty] | 2007-06-01 | 115 |  |  | 1 | Planned
B | 1368 | 2006-10-15 |  | West | XEL | Three Lakes 115/69 kV substation | Three Lakes 115/69 kV substation on existing Kinnickinnic - Roberts 69 kV line and Pine Lake - Willow River 115 kV line | WI | [9 empty] | 2009-05-01 | 115 |  |  | 2 | Proposed
B | 1370 | 2006-10-15 |  | West | XEL | Convert/Relocate the 69 kV Rush River substation to existing 161 kV line from Pine Lake - Crystal Cave | Convert/Relocate the 69 kV Rush River substation to existing 161 kV line from Pine Lake - Crystal Cave | WI | [9 empty] | 2009-05-01 | 161 |  |  | 2 | Proposed
B | 1371 | 2006-10-15 |  | West | XEL | Black Dog - Wilson 115 kV #1 Reconductor | Black Dog - Wilson 115 kV #1 Reconductor | MN | [9 empty] | 2009-06-01 | 115 |  |  | 1 | Planned
B | 1372 | 2006-10-15 |  | West | XEL | Glencoe - West Waconia 115 New Line | Glencoe - West Waconia 115 New Line | MN | [9 empty] | 2010-06-01 | 115 |  |  | 1 | Proposed
B | 1373 | 2006-10-15 |  | West | XEL | Ft. Ridgeley - Searles Jct 115 new line and Searles Jct - New Ulm 69 Reconductor | Ft. Ridgeley - Searles Jct 115 new line and Searles Jct - New Ulm 69 Reconductor | MN | [9 empty] | 2010-06-01 | 115 |  |  | 1 | Proposed
B | 1375 | 2006-10-15 |  | West | XEL | BRIGO - Buffalo Ridge Incremental Generation Outlet | BRIGO: Hazle Creek - Minn Valley 115 New Line, Hazle Creek - SVC 115 New, Lake Yankton - SE Marshall 115 kV line (new), Nobles - Fenton 115 kV line #2 (new), Winnebago Jct 161 Capacitor Banks, McLeod 115 Capacitor Banks | MN | [6 empty] | TAP | Service |  | 2010-06-01 | 161 |  | 36000000 | 7 | Planned
B | 1376 | 2006-10-15 |  | West | XEL | Poplar Lake 161/69 sub on St Croix Falls - Apple River 161 kV line | Poplar Lake 161/69 sub on St Croix Falls - Apple River 161 kV line | WI | [9 empty] | 2011-05-01 | 161 |  |  | 2 | Proposed
B | 1378 | 2006-10-15 |  | West | XEL | West St. Cloud - Granite City 115 Reconductor | West St. Cloud - Granite City 115 Reconductor | MN | [9 empty] | 2011-06-01 | 115 |  |  | 1 | Proposed
B | 1024 | 2005-10-12 | SE MN - SW WI | West | XEL/DPC/RPU | Southeast MN - Southwest WI upgrades | Construct Prairie Island-Rochester-North LaCrosse 345 kV line, Alma-LaCross tap-Genoa 161 rebuild, Adams-Harmony 161 rebuild, North Rochester 354/161 transformer, North LaCrosse 345/161 transformer | MN | WI | [8 empty] | 2011-12-31 | 345 | 161 | 151800000 | 8 | Proposed
B | 1203 | 2006-01-25 | SW MN - TC EHV | West | XEL/GRE | Southwest Minnesota -Twin Cities EHV Development | Brookings County -Lyon County-Franklin (Double Crt) -Helena-Lk Marion-Hampton Corner 9 (Single Crt) 345 kV | MN | [9 empty] | 2011-06-01 | 345 | 115 | 267680000 | 17 | Proposed
B | 1380 | 2006-10-15 |  | West | XEL/GRE | Scott County - West Waconia 115 | Scott County - West Waconia 1 115 | MN | [9 empty] | 2010-05-01 | 115 |  |  | 1 | proposed
3804498924.2475
Projects Outside Plan Year
B | 1025 | 2005-08-31 | Mesaba Energy | West | EEI | Mesaba Energy Project (Excelsior Energy Inc) | Mesaba Energy project generator outlet lines | MN |  |  |  | Required | [5 empty] | 2012-05-01 | 345 |  |  | 3 | Proposed
B | 174 | 2005-07-11 | 152 | West | ATC LLC | Canal-Dunn Road 138 kV | Canal - Dunn Road 138 ckt , Sum rate 400 | WI |  |  | Not Budgeted | Not Required | [5 empty] | 2012-06-01 | 138 |  | 4200000 | 1 | Planned
B | 568 | 2005-07-11 | 568 | West | ATC LLC | North Lake Geneva - White River 138 kV line | North Lake Geneva - White River 138 kV line | WI |  |  | Pending | Pending |  |  | Other | Excluded | Y | 2012-06-01 | 138 |  | 1250000 | 1 | Proposed
B | 682 | 2006-02-17 |  | West | ATC LLC | Huiskamp-Blount 138 kV line | Convert Huiskamp-Blount 69 kV line to 138 kV | WI |  |  | Pending | Pending | a) Sycamore-Ruskin 69 kV circuit b) Yahara River-Waunakee 69 kV circuit |  |  |  |  | 2012-06-01 | 138 |  | 20000000 | 1 | Proposed
B | 602 | 2005-06-15 |  | West | GRE | Brownton - McLeod 115 kV line | Brownton - McLeod 115 kV line | MN | [9 empty] | 2012-06-01 | 115 |  | 4675000 | 1 | Planned
B | 897 | 2006-10-03 | IPL-07 | Central | IPL | Thompson 345/138kV Autotransformer | Add new 345/138kV autotransformer at Thompson Substation | IN |  |  | Pending | Not Required | [5 empty] | 2012-06-01 | 345 | 138 | 4500000 | 1 | Proposed
B | 286 | 2005-07-29 | 281 | West | GRE/MPC/XEL/OTP/MP/W | TIPS 345 kV Line | Alexandria - Benton County 345 ckt 1, Sum rate 720 | MN |  |  | Pending | Pending | Coal Creek - Underwood - Harvey - Prairie 345 kV Line; Garrison - Max - Minot - Rugby - Drayton 230 kV Line; Bismarck - Jamestown - Fargo 345 kV Line; Boswell - Wilton 230 kV Line; Dorsey - Karlstad - Winger 345 kV Line; Fargo - Moorhead - Morris - Granite Falls - Blue Lake 345 kV Line; Watertown - Granite Falls - Blue Lake 345 kV Line |  |  |  |  | 2012-07-01 | 345 |  | 61069477 | 1 | Proposed
B | 287 | 2005-07-29 | 281 | West | GRE/MPC/XEL/OTP/MP/W | TIPS 345 kV Line | Maple River - Alexandria 345 ckt 1, Sum rate 720 | MN | ND | 0.05 | Pending | Pending | Coal Creek - Underwood - Harvey - Prairie 345 kV Line; Garrison - Max - Minot - Rugby - Drayton 230 kV Line; Bismarck - Jamestown - Fargo 345 kV Line; Boswell - Wilton 230 kV Line; Dorsey - Karlstad - Winger 345 kV Line; Fargo - Moorhead - Morris - Granite Falls - Blue Lake 345 kV Line; Watertown - Granite Falls - Blue Lake 345 kV Line |  |  |  |  | 2012-07-01 | 345 |  | 64283661 | 1 | Proposed
B | 288 | 2006-03-24 | 288 | West | MH | Dorsey to Forbes 500 kV Line Sectionalization (D602F) | This is a new 230 kV station wich will sectionalize the existing 500 kV line D602F into the station as well as several existing 230 kV lines. This station will also have a new 500/230 kV transformer installed. | Manitoba |  |  | Budgeted | Pending |  |  |  |  | N/A | 2012-08-01 | 500 | 230 | 2756010.63 | 1 | Proposed
B | 98 | 2006-03-24 |  | West | MH | Ridgeway - Selkirk 230 line and Selkirk 230/115 transformer | Ridgeway - Selkirk 230 line and Selkirk 230/115 transformer | Manitoba |  |  | Budgeted | Pending |  |  |  |  | N/A | 2012-11-02 | 230 | 115 | 2531730.9253 | 2 | Proposed
B | 1428 | 2006-10-25 | 176 | East | METC | Roosevelt substation | Add 345/138kV transformer and new 138kV line to Black River along with breakers at Roosevelt and Black River | MI |  |  | Budgeted | Not Required | [5 empty] | 2013-05-01 | 345 | 138 | 16000000 | 2 | Proposed
B | 841 | 2005-07-11 | AJ | Central | CIN | Westwood Bk1 Limiting Equipment | Replace 1200A 138kV equipment with 2000A to allow full transformer rating. | IN |  |  | Approved | Not required | [5 empty] | 2013-06-01 | 345 | 138 | 554000 | 1 | Planned
B | 987 | 2005-07-27 | 118 | East | METC | Emmet - Stover 138 kV Line | Build 30 miles new 138 kV line, 795 ACSS | MI | [9 empty] | 2013-06-01 | 138 |  | 10250000 | 1 | Proposed
B | 278 | 2006-03-24 |  | West | MH | Dorsey - Portage South 230 ckt 2 | Dorsey - Portage South 230 ckt 2, Sum rate 384 | Manitoba |  |  | Budgeted | Required |  |  |  |  | N/A | 2013-11-01 | 230 |  | 17923199.6774 | 1 | Proposed
B | 1225 | 2005-11-28 | 98 | East | METC | Thompson Rd-Tallman 138 kV | Thompson Road - Tallman 138 kV line | MI | [9 empty] | 2015-05-01 | 138 |  | 5000000 | 1 | Proposed
B | 853 | 2005-07-11 | AV | Central | CIN | West Lafayette to Cumberland 138 Reconductor | Reconductor section of 13806 circuit with 954ACSR 100C. | IN |  |  | Approved | Not required | [5 empty] | 2015-06-01 | 138 |  | 646000 | 1 | Planned
B | 434 | 2006-10-04 | 315 | West | ATC LLC | Butternut 28.8 MVAR capacitor bank | Butternut 138, 28.8 MVAR Capacitor bank | WI |  |  | Not Budgeted | not Required | [5 empty] | 2015-06-01 | 138 |  | 1050000 | 1 | Proposed
B | 1379 | 2006-10-15 |  | West | XEL | Pulaski - Linn Street - Becker - Liberty 69 kV to 115 kV upgrade | Pulaski - Linn Street - Becker 69 kV to 115 kV upgrade | MN | [9 empty] | 2015-06-01 | 115 |  |  | 3 | Proposed
B | 573 | 2006-07-05 | 573 | West | ATC LLC | North Madison-West Middleton 345 kV | North Madison - West Middleton 345 kV line | WI |  |  |  | Required | [5 empty] | 2016-01-01 | 345 |  | 46700000 | 1 | Proposed
B | 569 | 2006-10-04 | 569 | West | ATC LLC | White River T-D interconnection | South Lake Geneva - White River 138 kV line | WI |  |  | not Budgeted | Required | [5 empty] | 2016-06-01 | 138 |  | 2500000 | 1 | Proposed
B | 575 | 2006-10-04 | 575 | West | ATC LLC | Pulliam-New Suamico conversion to 138 kV for T-D interconnection | Rebuild/Convert Pulliam-New Suamico 69 kV line to 138 kV | WI |  |  | Not Budgeted | Pending | 1) Rebuild Pulliam-New Suamico 69 kV line using various conductor sizes 2) Rebuild/convert Pulliam-New Suamico 69 kV line to double circuit 138 kV |  |  |  |  | 2016-06-01 | 138 |  | 6221325 | 3 | Proposed
B | 1382 | 2006-10-24 | The 765 | East | ITC/METC | Michigan 765 kV Backbone | Project constructs a 765 kV circuit from AEP's Cook station to a new 765 kV station at the Kenowa 345 kV (METC) station including one 765/345 kV transformer at Kenowa. A new 765 kV circuit from the Kenowa station to a new 765 kV station at the Denver location including a 765/138 kV transformer. A new 765 kV circuit from the Denver station to a new 765 kV station at the Sprague Creek location including a 765/345 kV transformer at Sprague Creek. A new 765 kV circuit from the Sprague Creek station to a new 765 kV station at the Bridgewater site including two 765/345 kV transformers. A new 765 kV circuit from Bridgewater to a new 765 kV station near the Indiana - Ohio border tapping the Dumont to Marysville 765 kV circuit. A new 765 kV circuit from the Bridgewater station to AEP's South Canton 765 kV station. The project will also tap the Blackfoot to Madrid 345 kV circuit at the new Sprague Creek 345 kV station and create two Blackfoot to Sprague Creek 345 kV circuits and one Madrid to Sprague Creek 345 kV circuit. And tap the Majestic to Lulu and Majestic to Milan 345 kV circuits at the new Bridgewater 345 kV station and create two Majestic to Bridgewater 345 kV circuits and a Bridgewater to Milan 345 kV circuit and a Bridgewater to Lulu 345 kV circuit. Other options are also being considered including HVDC. | MI | [9 empty] | 2016-12-31 | 765 | 138 | 2500000000 | 18 | Proposed
B | 649 | 2005-07-27 | 81 | East | METC | Argenta - Palisades(Sag) 345 ckt # 1&2 | Argenta - Palisades(Sag) 345 ckt # 1&2 | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-05-01 | 345 |  | 500000 | 1 | Proposed
B | 650 | 2005-07-27 | 72 | East | METC | Battle Creek - Morrow 138 ckt # 1 | Rebuild Battle Creek-Morrow 138 kV line 14.4 miles to 795 ACSS | MI |  |  | Budgeted | Not Required | [5 empty] | 2017-05-01 | 138 |  | 3400000 | 1 | Proposed
B | 662 | 2005-07-27 | 117 | East | METC | Weeds Lake 345/138 kV Station | Construct new 345/138 kV single transformer station | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-05-01 | 345 | 138 | 13000000 | 1 | Proposed
B | 480 | 2006-09-29 | 112 | East | METC | Brickyard - Felch 138 kV line | Rebuild 12.8 miles to 795 ACSS | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-06-01 | 138 |  | 3000000 | 1 | Proposed
B | 642 | 2005-07-27 | 57 | East | METC | Argenta - Hazelwood(Sag) 138 ckt # 1 | Argenta - Hazelwood(Sag) 138 ckt # 1 | MI |  |  | Approved | Not Required |  |  | Other | Excluded | Y | 2017-06-01 | 138 |  | 50000 | 1 | Proposed
B | 646 | 2005-07-27 | 86 | East | METC | Edenville - Warren 138 ckt # 1 | Rebuild Edenville-Warren 138 kV line 14.75 miles to 795 ACSS | MI |  |  | Budgeted | Not Required | [5 empty] | 2017-06-01 | 138 |  | 4000000 | 1 | Proposed
B | 1430 | 2006-10-25 | 178 | East | METC | Buck Creek switching station | Convert 138/46kV substation to a switching station by installing 3 high side 138kV breakers at Buck Creek | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-06-01 | 138 |  | 4500000 | 1 | Proposed
B | 1431 | 2006-10-25 | 179 | East | METC | Vergennes-Kendrick-Plaster Creek 138kV line | Build new 16mile 138kV line from Vergennes to Kendrick and puchase Kendrick-Plaster Creek spur | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-06-01 | 138 |  | 14000000 | 1 | Proposed
B | 1432 | 2006-10-25 | 180 | East | METC | Withey Lake-Twining 138kV line | Rebuild 0.2 miles of Withey Lake-Twining 138kV line | MI |  |  | Not Budgeted | Not Required | [5 empty] | 2017-06-01 | 138 |  | 100000 | 1 | Proposed
B | 585 | 2006-03-27 | 585 | West | OTP | Pelican Rapids 115 kV Line Uprate | Pelican Rapids - Pelican Rapids Turkey Plant 115 kV line | MN |  |  | Pending | Pending | [5 empty] | 2017-06-01 | 115 |  | 858869 | 1 | Planned
B | 1357 | 2006-10-15 |  | West | MH | Conawapa (dc) - Riel (dc) 1 500 direct current line | Conawapa (dc) - Riel (dc) 1 500 direct current line | Manitoba | [8 empty] | N/A | 2017-10-01 | 500 |  |  | 12 | Proposed
B | 651 | 2005-07-27 | 83 | East | METC | Stover - Clearwater 138 kV Line (Phase 2) | Rebuild Stover - Clearwater 138 kV line 8.8 miles to 795 ACSS | MI |  |  | Budgeted | Not Required | [5 empty] | 2018-05-01 | 138 |  | 2800000 | 1 | Proposed
B | 89 | 2006-07-05 | 67 | West | ATC LLC | Mill Road 345/138 kV substation and transformer | Mill Road transformer - 345/138 ckt , Sum rate 500 | WI |  |  | NA. - project deferred to 2019 | NA - project deferred until 2018 | [5 empty] | 2018-06-01 | 345 | 138 | 29200000 | 1 | Proposed
B | 341 | 2006-03-16 | newgrp19 | West | ATC LLC | Rockdale-Mill Road 345 kV line projects | Construct Rockdale-Concord 345 kV line in parallel with existing 138 kV on existing double-width right-of-way. Construct a 345 kV bus and install a 345/138 kV, 500 MVA transformer at Concord. Convert Bark River-Mill Road 138 kV line to 345 kV. Construct a Concord-Bark River 345 kV line. Construct a 345 kV bus and install a 345/138 kV, 500 MVA transformer at Bark River | WI |  |  | Approved | Pending | Rockdale-St. Lawrence 345 kV line Assorted 138 kV fixes |  |  |  |  | 2018-06-01 | 345 | 138 | 94600000 | 5 | Proposed
B | 1429 | 2006-10-25 | 177 | East | METC | Barry-Thompson Rd 138kV line | Build new 17mile 138kV line from Barry to Thompson Rd | MI |  |  | Budgeted | Not Required | [5 empty] | 2018-06-01 | 138 |  | 20000000 | 1 | Proposed
B | 283 | 2006-03-24 | 283 | West | MH | New Rosser Oak Point Station 115-24 kV | A new Rosser - Oak Point station is going to be built to supply area load growth. The project consists of two new 115/24 kV transformers, plus associated station equipment and 24 kV feeders. This station will be tapped of of existing 115 kV lines RY7 and RK6. | Manitoba |  |  | Budgeted | Pending |  |  |  |  | N/A | 2020-05-30 | 115 |  | 1880662.549 | 2 | Proposed
B | 285 | 2006-06-28 |  | West | MH | St. Vital - Steinbach 230 | St. Vital - Steinbach 230 ckt 1, Sum rate 399 | Manitoba |  |  | Budgeted | Required | a second 230-66 kV transformer bank at Richer, which is planned to be in-service in 2007 |  |  |  | N/A | 2020-11-01 | 230 |  | 13653801.9165 | 1 | Proposed
B | 1283 | 2006-08-24 | 5 | West | ATC LLC | Retap CT at Freeman for new ratings of 195 SN/202 SE after confirmation of 167 deg F line clearance | Retap CT at Freeman for new ratings of 195 SN/202 SE after confirmation of 167 deg F line clearance | WI | [10 empty] | 138 |  | 5000 | 1 | Proposed
Note on Q138: Who pays for undergrounding?
Note on Q51: Pre-RECB1 gen int
Note on Q64: Pre-RECB1 gen int
Note on Q45: Radial line

## Facilities
MTEP06 Appendix A and B Project Facilities - 11/06/06 DRAFT
App AB | Facil ID | Record Date | Facility Type | Region | Reporting Source | PrjID | Prj Rec Date | Owner PrjID | Expected ISD | From Sub or Location | To Sub or Device Description | Ckt | Voltage | Volt Low | Sum Rate | Upgrade Desc | Map Grid | State | Miles Upg | Miles New | Need Load | Need Gen Int | Need TSR | Need Other | Plan Status | Est Cost | Est Type | Cancellation Reason | FTR Usage | Comments | Submit Date | Submit Study | Last Change | TO Study | MISO AppA | MAPP Form | Public Flag | Idev File | Upgrade Type | TSR Upg
A | 189 | 2006-10-12 | BR | N-ITWG | ALTW | 90 | 2005-07-11 | 69 | 2007-06-01 | Emery | Lime Creek | 2 | 161 |  | 326 | New Facility | H7 | IA |  | 25 | 100 |  |  |  | Planned | 8000000 | [7 empty] | A102 | Y | Y | Y |  |  | Y
A | 2104 | 2006-01-31 | BR | N-NM | ALTW | 1204 | 2006-01-31 |  | 2006-10-01 | Adams | Rochester | 1 | 161 |  | 201/221 MVA | replace termination jumpers at Adams | I7 | MN |  |  |  |  | 100 |  | Planned | 5000 | Planning MISO | [7 empty] | Y | Y | Y |  |  | Y
A | 2116 | 2006-08-24 | TX | N-ITWG | ALTW | 1287 | 2006-08-24 | 9 | 2011-06-01 | Salem 345/161 kV | transformer | 1 | 345 | 161 | 448/448 | Larger Xfmr |  | IA | 0 | 0 |  |  |  |  | Planned | 5000000 | [8 empty] | Y | Y | Y
A | 2117 | 2006-08-24 | TX | N-ITWG | ALTW | 1288 | 2006-08-24 | 10 | 2011-06-01 | Hazleton 345/161 | transformer | 1 | 345 | 161 | 335/335 | Larger Xfmr |  | IA | 0 | 0 |  |  |  |  | Planned | 3500000 | [8 empty] | Y | Y | Y
A | 2118 | 2006-08-24 | BR | N-ITWG | ALTW | 1289 | 2006-08-24 | 11 | 2011-06-01 | Marshalltwon | Toledo | 1 | 115 |  | 233/233 | Rebuild |  | IA | 15.5 | 0 |  |  |  |  | Planned | 0 | [8 empty] | Y | Y | Y
A | 2119 | 2006-08-24 | BR | N-ITWG | ALTW | 1289 | 2006-08-24 | 11 | 2011-06-01 | Belle Plaine | Toledo | 1 | 115 |  | 233/233 | Rebuild |  | IA | 20 | 0 |  |  |  |  | Planned | 3900000 | [8 empty] | Y | Y | Y
A | 2120 | 2006-08-24 | BR | N-ITWG | ALTW | 1289 | 2006-08-24 | 11 | 2011-06-01 | Belle Plaine | Stoney Point | 1 | 115 |  | 233/233 | Rebuild |  | IA | 27 | 0 |  |  |  |  | Planned | 0 | [8 empty] | Y | Y | Y
A | 2209 | 2006-10-06 | TX | N-ITWG | ALTW | 1342 | 2006-10-06 | 3 | 2011-06-01 | Lewis Fields | transformer | 1 | 161 | 115 |  | new transformer |  | IA |  |  | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | Y | Y
A | 2208 | 2006-10-06 | BR | N-ITWG | ALTW | 1342 | 2006-10-06 | 3 | 2011-06-01 | Lewis Fields | Hiawatha | 1 | 161 |  | 250 | new line |  | IA |  | 8.5 | 100 |  |  |  | Proposed | 2550000 | [8 empty] | Y | Y | Y
A | 2212 | 2006-10-06 | TX | N-ITWG | ALTW | 1344 | 2006-10-06 | 5 | 2011-06-01 | Beverly | transformer | 1 | 345 | 161 | 335 | new substation |  | IA |  |  | 100 |  |  |  | Planned | 4000000 | [8 empty] | Y | Y | Y
A | 2211 | 2006-10-06 | BR | N-ITWG | ALTW | 1344 | 2006-10-06 | 5 | 2011-06-01 | Beverly Tap | Beverly | 1 | 161 |  | 335 | new line |  | IA |  | 7.9 | 100 |  |  |  | Planned | 300000 | [8 empty] | Y | Y | Y
A | 2215 | 2006-10-06 | DV | N-ITWG | ALTW | 1347 | 2006-10-06 | 8 | 2011-06-01 | Liberty | breakers |  | 161 |  |  | Install two CB at both ends of Liberty 161 kV bus |  | IA |  |  | 100 |  |  |  | Planned | 300000 | [8 empty] | Y | Y | Y
A | 2217 | 2006-10-06 | BR | N-ITWG | ALTW | 1348 | 2006-10-06 | 9 | 2011-06-01 | Marion | Coggon | 1 | 115 |  | 198 | upgrade limiting equipment |  | IA |  |  | 100 |  |  |  | Planned | 5104167 | [8 empty] | Y | Y | Y
A | 2216 | 2006-10-06 | BR | N-ITWG | ALTW | 1348 | 2006-10-06 | 9 | 2011-06-01 | Marion | Prairie Creek | 1 | 115 |  | 198 | upgrade limiting equipment |  | IA |  |  | 100 |  |  |  | Planned | 200000 | [8 empty] | Y | Y | Y
A | 2218 | 2006-10-06 | TX | N-ITWG | ALTW | 1349 | 2006-10-06 | 15 | 2011-06-01 | Dundee | transformer | 1 | 161 | 115 | 112 | replace transformer |  | IA |  |  | 100 |  |  |  | Planned | 100000 | [8 empty] | Y | Y | Y |  |  |  | 26954167
A | 46 | 2006-03-17 | BR | C-CSILL | Ameren | 77 | 2005-07-11 | 54 | 2006-12-01 | Callaway | Franks | 1 | 345 |  | 1606 | new 345 kV line | I10 | MO |  | 54 | 100 |  |  |  | Under Construction | 29966200 | Eng | [7 empty] | Y | N | Y
A | 56 | 2006-03-17 | BR | C-CSILL | Ameren | 143 | 2006-03-17 |  | 2007-06-01 | Cahokia | N. Coulterville | 1 | 230 |  | 400 | increase ground clearance | J11 | IL | 45 |  | 100 |  |  |  | Planned | 476700 | Eng | [7 empty] | Y | N | Y
A | 392 | 2006-03-17 | BR | C-CSILL | Ameren | 144 | 2006-03-17 |  | 2008-06-01 | Crab Orchard | Marion South | 1 | 138 |  | 399 | reconductor | K11 | IL | 9.1 |  | 100 |  |  |  | Planned | 2712300 | Eng | [7 empty] | Y | N | Y
A | 397 | 2006-03-17 | BR | C-CSILL | Ameren | 149 | 2006-03-17 |  | 2007-06-01 | Mason | Sioux | 1 | 345 |  |  | breaker addition at Mason | J11 | MO |  |  | 100 |  |  |  | Planned | 605900 | Eng | [7 empty] | Y | N | Y
A | 398 | 2006-03-17 | BR | C-CSILL | Ameren | 150 | 2006-03-17 | PS gen | 2008-06-01 | Rush Island | Baldwin | 1 | 345 |  | 1793 | terminal at Rush Island & river crossing only | J11-K11 | IL |  | 2 |  | 100 |  |  | Planned | 1615100 | [7 empty] | IP04 | Y | N | Y |  | Net?
A | 400 | 2006-03-17 | BR | C-CSILL | Ameren | 153 | 2006-03-17 |  | 2008-06-01 | CEE Tap | Watson | 1 | 138 |  | 370 | reconductor | J11 | MO | 0.8 |  | 100 |  |  |  | Planned | 311400 | Eng | [7 empty] | Y | N | Y
A | 401 | 2006-03-17 | TX | C-CSILL | Ameren | 155 | 2006-03-17 |  | 2008-06-01 | Joachim 345/138 kV | transformer | 1 | 345 | 138 | 560 | new 345/138 kV transformer | J11 | MO |  |  | 100 |  |  |  | Planned | 12963300 | Eng | [7 empty] | Y | N | Y
A | 1398 | 2006-10-04 | BR | C-CSILL | Ameren | 707 | 2006-03-17 |  | 2006-11-01 | Adair (Install Breaker for Thomas Hill Line) | Install 161 kV Breaker at Adair |  | 161 |  | 281 | new 161 kV breaker | I9 | MO |  |  | 100 |  |  |  | Under Construction | 335900 | Eng | [7 empty] | Y | N | Y
A | 1399 | 2006-03-17 | BR | C-CSILL | Ameren | 708 | 2006-03-17 |  | 2007-06-01 | Casey | Breed | 1 | 345 |  | 1332 | reconductor river crossing | L10 | IL | 0.23 |  |  |  |  | 100 | Planned | 303900 | Eng | [7 empty] | Y | N | Y
A | 1402 | 2006-03-17 | BR | C-CSILL | Ameren | 711 | 2006-03-17 |  | 2007-06-01 | Wood River | Gillespie | 1 | 138 |  | 240 | reconductor | K10 | IL | 7.5 |  | 100 |  |  |  | Planned | 939500 | Eng | [7 empty] | Y | N | Y
A | 1403 | 2006-03-17 | BR | C-CSILL | Ameren | 712 | 2006-03-17 |  | 2007-06-01 | Mason | Labadie-Mason-3 Term. Equipment replacement | 1 | 345 |  |  | terminal equipment upgrade at Mason | J11 | MO |  |  | 100 |  |  |  | Planned | 184100 | Eng | [7 empty] | Y | N | Y
A | 1410 | 2006-03-17 | BR | C-CSILL | Ameren | 719 | 2006-03-17 |  | 2008-06-01 | Labadie Plant | Replace 2-345 kV Breakers |  | 345 |  |  | replace existing 345 kV breakers | J11 | MO |  |  | 100 |  |  |  | Planned | 1897100 | Eng | [6 empty] | Gen | Y | N | Y |  | Int or Net?
A | 831 | 2006-10-04 | BR | C-CSILL | Ameren | 856 | 2005-07-11 |  | 2006-12-01 | Osage 138 kV Substation | Eldon | 1 | 138 |  | 200 | Replace bus conductor at Osage Substation | I11 | MO |  |  | 100 |  |  |  | Under Construction | 65000 | Eng | [7 empty] | Y | N | Y
A | 832 | 2006-03-17 | BR | C-CSILL | Ameren | 857 | 2005-07-11 |  | 2007-06-01 | Rush Island | Joachim | 1 | 345 |  | 1200 | Replace terminal equipment at Rush Island | J11 | MO |  |  | 100 |  |  |  | Planned | 283200 | Eng | [7 empty] | Y | N | Y
A | 833 | 2006-03-17 | BR | C-CSILL | Ameren | 858 | 2005-07-11 |  | 2007-06-01 | Sioux | Huster | 1 | 138 |  | 214 | Increase ground clearance | J10 | MO | 6 |  | 100 |  |  |  | Planned | 1024500 | Eng | [7 empty] | Y | N | Y
A | 834 | 2006-03-17 | BR | C-CSILL | Ameren | 859 | 2005-07-11 |  | 2008-06-01 | Central | Watson (Tower 55) | 1 | 138 |  | 370 | Reconductor 5.1 miles 954 kcmil ACSR from Central to Twr. 55 | J11 | MO | 5.1 |  | 100 |  |  |  | Planned | 1500300 | Eng | [7 empty] | Y | N | Y
A | 1942 | 2006-03-17 | CB | C-CSILL | Ameren | 1241 | 2006-03-17 |  | 2007-03-01 | Mattoon, West | Install 138 kV Breaker at Mattoon, West | 1 | 138 |  |  | Install 138 kV Breaker to connect Wind Farm | K10 | IL |  |  |  | 100 |  |  | Planned | 555400 | Eng | [7 empty] | Y | N | Y |  | Interconnection
A | 853 | 2006-10-04 | BR | C-CSILL | AmerenCILCO | 875 | 2005-07-11 |  | 2006-11-15 | Kickapoo | Mason City-Decatur |  | 138 |  | 155 | Replace 600 A terminal equipment with 1200 A at Kickapoo | K9 | IL |  |  | 100 |  |  |  | Under Construction | 156700 | Eng | [7 empty] | Y | N | Y
A | 854 | 2006-03-17 | BR | C-CSILL | AmerenCILCO | 876 | 2005-07-11 |  | 2007-06-01 | Tazewell | Powerton | 1 | 345 |  | 1339 | Replace 2000 A terminal equipment at Tazewell with 3000 A | K9 | IL |  |  | 100 |  |  |  | Planned | 1042900 | Eng | [7 empty] | Y | N | Y
A | 1422 | 2006-03-17 | BR | C-CSILL | AmerenIP | 150 | 2006-03-17 | PS gen | 2008-06-01 | Baldwin | Rush Island | 1 | 345 |  | 1793 | 26 miles of new 345 kV line | J11-K11 | IL |  | 26 |  | 100 |  |  | Planned | 46149200 | [7 empty] | IP04 | Y | N | Y |  | Net?
A | 1423 | 2006-03-17 | BR | C-CSILL | AmerenIP | 150 | 2006-03-17 | PS gen | 2008-06-01 | Line 4531 tap | Prairie State Power Plant | 2 | 345 |  | 1470 | 345 kV connection to new generation | K11 | IL |  | 7.5 |  | 100 |  |  | Planned | 2283900 | [7 empty] | IP04 | Y | N | Y |  | Int?
A | 1424 | 2006-03-17 | BR | C-CSILL | AmerenIP | 150 | 2006-03-17 | PS gen | 2008-06-01 | Line 4541 tap | Prairie State Power Plant | 2 | 345 |  | 1470 | 345 kV connection to new generation | K11 | IL |  | 1.5 |  | 100 |  |  | Planned | 12991400 | [7 empty] | IP04 | Y | N | Y |  | Int?
A | 1667 | 2005-10-06 | SUB | C-CSILL | AmerenIP | 150 | 2006-03-17 | PS gen | 2008-06-01 | Prairie State | substation | 1 | 345 |  | 1793 | new switchyard (6 position, 4 lines, 2 units) | J11-K11 | IL |  |  |  | 100 |  |  | Planned | [8 empty] | IP04 | Y | N | Y |  | Int?
A | 1417 | 2006-10-04 | BR | C-CSILL | AmerenIP | 724 | 2006-10-04 |  | 2006-12-01 | Rising | Bondville Rt. 10 | 1 | 138 |  | 266 | new 138 kV breaker at Rising and 3 miles new 138 kV line | K9 | IL |  | 3 | 100 |  |  |  | Under Construction | 2442500 | Eng | [7 empty] | Y | N | Y
A | 1418 | 2006-03-17 | BR | C-CSILL | AmerenIP | 725 | 2006-10-04 | 725 | 2008-06-01 | N. LaSalle | Wedron Fox River | 1 | 138 |  | 266 | 2 CB at N LaSalle, 1 CB at Wedron Fox River Substation | K8 | IL |  | 25 | 100 |  |  |  | Planned | 20489370 | Eng | [7 empty] | Y | N | Y
A | 1419 | 2006-03-17 | BR | C-CSILL | AmerenIP | 726 | 2006-10-04 | 725 | 2008-06-01 | Ottawa | Wedron Fox River | 1 | 138 |  | 266 | 1 CB at Ottawa, new 138 kV line to Wedron Fox River Substation | K8 | IL |  | 8 | 100 |  |  |  | Planned | 8045400 | Eng | [7 empty] | Y | N | Y
A | 1421 | 2006-03-17 | BR | C-CSILL | AmerenIP | 728 | 2006-10-04 |  | 2008-06-01 | Wood River | Roxford L1502 | 1 | 138 |  | 382 | reconductor | K10 | IL | 4.36 |  | 100 |  |  |  | Planned | 5264900 | Eng | [7 empty] | Y | N | Y
A | 1425 | 2006-03-17 | BR | C-CSILL | AmerenIP | 732 | 2006-03-17 |  | 2007-06-01 | S. Bloomington | State Farm | 1 | 138 |  | 337 | Reconductor 1.3 miles 1272 kcmil ACSR | K9 | IL | 1.3 |  | 100 |  |  |  | Planned | 1172900 | Eng | [7 empty] | Y | N | Y
A | 1429 | 2006-03-17 | BR | C-CSILL | AmerenIP | 736 | 2006-03-17 |  | 2007-06-01 | W. Tilton | Tilton Energy Center |  | 138 |  |  | new 138 kV breaker addition at W. Tilton | L9 | IL |  |  | 100 |  |  |  | Planned | 1709400 | Eng | [7 empty] | Y | N | Y
A | 1431 | 2006-03-17 | BR | C-CSILL | AmerenIP | 738 | 2006-03-17 |  | 2007-06-01 | Line 1342C tap | Line 1342A | 1 | 138 |  | 280 | Line 1342A (structure 423 to 467A reconductor) | K9 | IL | 5.23 |  | 100 |  |  |  | Planned | 1994400 | Eng | [7 empty] | Y | N | Y
A | 1432 | 2006-03-17 | BR | C-CSILL | AmerenIP | 739 | 2006-03-17 |  | 2009-01-01 | Line 4561 Tap | Franklin County Power Plant | 1 | 345 |  |  | 345 kV connection (new ring bus) to new generation | K11 | IL |  |  |  | 100 |  |  | Planned | 7108700 | Eng | [6 empty] | IP17 | Y | N | Y |  | Int?
A | 841 | 2006-03-17 | BR | C-CSILL | AmerenIP | 865 | 2006-03-17 |  | 2007-06-01 | Havana | Monmouth | 1 | 138 |  | 280 | Build new river crossing | J9 | IL |  | 0.44 | 100 |  |  |  | Planned | 223700 | Eng | [7 empty] | Y | N | Y
A | 845 | 2006-03-17 | BR | C-CSILL | AmerenIP | 869 | 2005-07-11 |  | 2007-06-01 | Sidney | Mira Tap | 1 | 138 |  | 280 | Reconductor 2 miles of 795 kcmil ACSR | L9 | IL | 2 |  | 100 |  |  |  | Planned | 693800 | Eng | [7 empty] | Y | N | Y
A | 851 | 2006-03-17 | BR | C-CSILL | AmerenIP | 873 | 2005-07-11 |  | 2009-01-31 | Baldwin | Turkey Hill | 1 | 345 |  | 1195 | Replace 345 kV breakers at Baldwin terminal | K11 | IL |  |  |  | 100 |  |  | Planned | 4242100 | Eng | [7 empty] | Y | N | Y
A | 849 | 2006-03-17 | BR | C-CSILL | AmerenIP | 873 | 2005-07-11 |  | 2009-01-31 | Baldwin | W. Mt. Vernon | 1 | 345 |  | 1195 | Replace 345 kV breakers at Baldwin terminal | K11 | IL |  |  |  | 100 |  |  | Planned | 4242100 | Eng | [7 empty] | Y | N | Y
A | 850 | 2006-03-17 | BR | C-CSILL | AmerenIP | 873 | 2005-07-11 |  | 2009-01-31 | Baldwin | Stallings | 1 | 345 |  | 1195 | Replace 345 kV breakers at Baldwin terminal | K11 | IL |  |  |  | 100 |  |  | Planned | 4242100 | Eng | [7 empty] | Y | N | Y
A | 2064 | 2005-07-11 | CAP | C-WUMS | ATC LLC | 1 | 2005-07-11 | 1 | 2008-06-01 | Arpin | Capacitor bank |  | 138 |  | 50 Mvar |  | J6 | WI | [5 empty] | 100 | Planned | 1021496 | Eng | [7 empty] | Y | N | Y
A | 855 | 2006-04-05 | DV | C-WUMS | ATC LLC | 1 | 2005-07-11 | 1 | 2008-06-01 | Stone Lake | Inductor |  | 345 |  | 75 Mvar |  | J6 | WI | [5 empty] | 100 | Planned | 0 | Eng | [7 empty] | Y | N | Y | ATC zone 1
A | 3099 | 2005-07-11 | CAP | C-WUMS | ATC LLC | 1 | 2005-07-11 | 1 | 2008-06-01 | Stone Lake | Capacitor |  | 345 |  | 75 Mvar |  | J6 | WI | [5 empty] | 100 | Planned | 0 | Eng | [7 empty] | Y | N | Y
A | 135 | 2006-07-05 | BR | N-NM | ATC LLC | 1 | 2005-07-11 | 1 | 2008-06-30 | Arrowhead | Gardner Park | 1 | 345 |  | 750 | Gardner Park-Stone Lake 2006, Stone Lake-Arrowhead 2008 | I4 | WI |  | 220 | 50 |  | 25 | 25 | Under Construction | 364645722.88 | Eng | [6 empty] | A191, F009 | Y | N | Y |  |  | Y
A | 121 | 2006-11-02 | LN | West | ATC LLC | 2 | 2005-07-11 | 1 | 2007-06-01 | Dewey Tap | Weston |  | 115 |  | 241 | Phase I increase clearance/ Phase II reconductor 12/31/07 | K6 | WI | 15.4 |  | 50 |  | 25 | 25 | Planned | 5535684.5 | Eng | [6 empty] | G144 | Y | N | Y |  | Network
A | 127 | 2006-11-02 | LN | West | ATC LLC | 2 | 2005-07-11 | 1 | 2007-06-01 | Northpoint | Dewey Tap |  | 115 |  | 241 | Phase I increase clearance/ Phase II reconductor 12/31/07 | K6 | WI | 8.2 |  | 50 |  | 25 | 25 | Planned | 5535684.5 | Eng | [6 empty] | G144 | Y | N | Y |  | Network
A | 119 | 2006-10-27 | LN | West | ATC LLC | 21 | 2005-07-11 | 10 | 2007-06-01 | Venus | Metonga (was Crandon) |  | 115 |  | 175 | new radial line | K5 | WI |  | 14 | 100 |  |  |  | Under Construction | 8745840 | Eng |  | FTR ATC38 | [5 empty] | Y | N | Y | ATC zone 1
A | 132 | 2006-10-04 | BR | C-WUMS | ATC LLC | 22 | 2005-11-18 | 11 | 2007-06-01 | Sprecher | Reiner (conversion to 138 kV) |  | 138 |  | 366 | conversion to 138 | K7 | WI | 10 |  | 75 |  |  | 25 | Under Construction | 1250000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 131 | 2006-10-04 | BR | C-WUMS | ATC LLC | 22 | 2005-11-18 | 11 | 2007-06-01 | Reiner | Sycamore (conversion to 138 kV) |  | 138 |  | 366 | conversion to 138 | K7 | WI | 7 |  | 75 |  |  | 25 | Under Construction | 1250000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 123 | 2006-10-04 | BR | C-WUMS | ATC LLC | 22 | 2005-11-18 | 11 | 2007-06-01 | Femrite | Sprecher (new 138 kV) | 1 | 138 |  | 348 | new 138 kV line | K7 | WI |  | 5 | 50 |  | 50 |  | Under Construction | 8100000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 108 | 2006-07-05 | BR | C-WUMS | ATC LLC | 62 | 2005-11-18 | 44 | 2007-03-01 | Stratford | McMillan |  | 115 |  | 135 |  | J6 | WI | 10 |  | 60 |  | 20 | 20 | Planned | 1750000 | Eng |  | FTR ATC31 | [5 empty] | Y | N | Y | ATC zone 1
A | 86 | 2006-10-04 | BR | C-WUMS | ATC LLC | 64 | 2005-07-11 | 46 | 2007-06-01 | Kegonsa | McFarland (conversion to 138 kV) |  | 138 |  | 348 | conversion to 138 | K7 | WI | 3.7 |  | 75 |  |  | 25 | Under Construction | 2410000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 87 | 2006-10-04 | BR | C-WUMS | ATC LLC | 64 | 2005-07-11 | 46 | 2007-06-01 | McFarland | Femrite (conversion to 138 kV) |  | 138 |  | 438 | conversion to 138 | K7 | WI | 2.1 |  | 75 |  |  | 25 | Under Construction | 1000000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 125 | 2006-04-05 | BR | C-WUMS | ATC LLC | 101 | 2005-07-11 | 82 | 2008-06-01 | Kelly | Whitcomb |  | 115 |  | 121 | uprate clearances to 300F | K6 | WI | 24.3 |  | 50 |  | 25 | 25 | Planned | 1900000 | Eng | [6 empty] | A105, F006 | Y | N | Y | ATC zone 1 |  | Y
A | 468 | 2006-10-27 | LN | West | ATC LLC | 102 | 2006-03-16 | 83 | 2008-06-01 | Pleasant Valley | St. Lawrence |  | 138 |  | 290 | reconductor | K7 | WI | 7 |  |  | 25 |  | 75 | Planned | 4800000 | Eng | [6 empty] | A130 | Y | N | Y |  |  | Y
A | 467 | 2006-10-27 | LN | West | ATC LLC | 102 | 2006-03-16 | 83 | 2008-06-01 | Pleasant Valley | Saukville |  | 138 |  | 290 | reconductor | K7 | WI | 12 |  |  | 25 |  | 75 | Planned | 4800000 | Eng | [6 empty] | A130 | Y | N | Y |  |  | Y
A | 436 | 2006-07-05 | TX | C-WUMS | ATC LLC | 168 | 2005-07-11 |  | 2006-12-31 | Werner West | transformer |  | 345 | 138 | 500 |  | K6 | WI |  |  | 33 |  | 34 | 33 | Under Construction | 14300000 | Eng | [6 empty] | A013,A105,A120,A153,A163, A191,F005,F006,F007,F009 | Y | N | Y |  |  | Y
A | 862 | 2006-10-27 | SUB | West | ATC LLC | 177 | 2006-03-16 | 155 | 2009-06-01 | HWY 22 (formerly Central Wisconsin) | new substation |  | 345 |  |  | new substation | K6 | WI | [6 empty] | Planned | 12200000 | Eng | [6 empty] | G144, F009 | Y | N | Y |  | Network | Y
A | 2456 | 2006-10-27 | LN | West | ATC LLC | 177 | 2006-03-16 |  | 2009-12-01 | Caroline | Belle Plaine | 1 | 115 |  | 290/401 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 2455 | 2006-10-27 | LN | West | ATC LLC | 177 | 2006-03-16 |  | 2009-12-01 | Whitcomb | Caroline | 1 | 115 |  | 138/138 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 2454 | 2006-10-27 | LN | West | ATC LLC | 177 | 2006-03-16 |  | 2009-12-01 | Kelly | Whitcomb | 1 | 115 |  | 174/174 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 607 | 2006-10-27 | LN | West | ATC LLC | 177 | 2006-03-16 | 155 | 2009-12-01 | Gardner Park (new Weston) | HWY 22 (formerly Central Wisconsin) | 1 | 345 |  | 1200 |  | K6 | WI |  | 47 |  | 100 |  |  | Planned | 116700000 | Eng | [6 empty] | G144 | Y | N | Y |  | Network
A | 2457 | 2006-10-27 | LN | West | ATC LLC | 177 | 2006-03-16 |  | 2009-12-01 | Belle Plaine | Badger | 1 | 115 |  | 175/240 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 433 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Rockdale | Lakehead Cambridge |  | 138 |  | 287 | uprate | K7 | WI |  |  | 25 |  | 75 |  | Planned | 200000 | Eng |  | FTR ATC37 | [5 empty] | Y | N | Y | ATC zone 3
A | 434 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Rockdale | Boxelder | 1 | 138 |  | 383 | uprate | K7 | WI |  |  | 50 |  | 50 |  | Planned | 200000 | Eng |  | FTR ATC40 | [5 empty] | Y | N | Y
A | 450 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Lake Mills (provisional) | Stonybrook |  | 138 |  | 290 | construct new | K7 | WI |  | 6 | 100 |  |  |  | Planned | 9850000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 449 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Jefferson | Lake Mills (provisional) |  | 138 |  | 290 | construct new | K7 | WI |  | 6 | 100 |  |  |  | Planned | 9850000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 429 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Lakehead Cambridge | Jefferson |  | 138 |  | 348 | uprate | K7 | WI |  |  | 25 |  | 75 |  | Planned | 150000 | Eng |  | FTR ATC41 | [5 empty] | Y | N | Y | ATC zone 3
A | 892 | 2006-07-05 | BR | C-WUMS | ATC LLC | 339 | 2005-07-11 | newgrp15 | 2008-06-01 | Boxelder | Stonybrook |  | 138 |  | 287 | uprate | K7 | WI |  |  | 50 |  | 50 |  | Planned | 200000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 2459 | 2006-10-27 | LN | West | ATC LLC | 345 | 2006-11-02 |  | 2009-12-01 | Morgan | White Clay | 1 | 138 |  | 293/332 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 2458 | 2006-10-27 | LN | West | ATC LLC | 345 | 2006-11-02 |  | 2009-12-01 | Badger | Clintonville | 1 | 138 |  | 211/238 MVA |  |  | WI | [6 empty] | Planned | 0 | [8 empty] | Y | N
A | 480 | 2006-10-27 | LN | West | ATC LLC | 345 | 2006-11-02 | newgrp20 | 2009-12-01 | Morgan | Werner West |  | 345 |  | 1328 | new line | K6 | WI |  | 47 | 50 |  |  | 50 | Planned | 139778849 | Eng | [6 empty] | A013, F009 | Y | N | Y |  |  | Y
A | 608 | 2006-10-27 | LN | West | ATC LLC | 345 | 2006-11-02 | newgrp20 | 2009-12-01 | Clintonville | Werner West |  | 138 |  | 381/529 MVA |  | K6 | WI | 14 | 2 | 50 |  |  | 50 | Planned | 0 | Eng | [6 empty] | A013 | Y | N | Y |  |  | Y
A | 1247 | 2006-04-05 | BR | C-WUMS | ATC LLC | 350 | 2006-07-05 |  | 2007-06-01 | Gardner Park (was Weston) | Hilltop |  | 115 |  | 285 | new line | K6 | WI | 2.4 |  | 50 |  | 25 | 25 | Planned | 3750000 | Eng | [6 empty] | A122 | Y | N | Y | ATC zone 1 |  | Y
A | 458 | 2006-04-05 | BR | C-WUMS | ATC LLC | 350 | 2006-07-05 | newgrp3 | 2007-06-01 | Weston | Sherman St |  | 115 |  | 239 | rebuild | J6 | WI | 0.2 |  | 50 |  | 25 | 25 | Planned | 250000 | Eng | [6 empty] | A105, A122, F006 | Y | N | Y | ATC zone 1 |  | Y
A | 459 | 2006-04-05 | BR | C-WUMS | ATC LLC | 350 | 2006-07-05 | newgrp3 | 2007-06-01 | Sherman St | Hilltop |  | 115 |  | 239 | rebuild | J6 | WI | 6.9 |  | 50 |  | 25 | 25 | Planned | 3750000 | Eng | [6 empty] | A105, A122, F006 | Y | N | Y | ATC zone 1 |  | Y
A | 1963 | 2006-10-27 | SUB | West | ATC LLC | 352 | 2006-03-16 |  | 2006-06-01 | ER Muni |  |  | 115 |  |  | Construct new SS adjacent to the Cranberry 115-kV SS |  | WI | [6 empty] | Under Construction | 2600000 | [8 empty] | Y | N | Y
A | 446 | 2006-10-27 | BR | West | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2008-01-01 | Eagle River | Lakota Rd (formerly Conover) | 1 | 115 |  | 244 | new line | K5 | WI |  | 14 | 50 |  | 25 | 25 | Planned | 10000000 | Eng | [6 empty] | A105, A215, F006 | Y | N | Y |  |  | Y
A | 447 | 2006-10-27 | TX | West | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2008-01-01 | Lakota Rd (formerly Conover) 138-115 kV | transformer | 1 | 138 | 115 | 150 | cost includes 138/115 and 138/69 transformers at Conover | K5 | WI |  |  | 50 |  | 25 | 25 | Planned | 18500000 | Eng | [6 empty] | A105, A215, F006 | Y | N | Y |  |  | Y
A | 445 | 2006-10-27 | BR | West | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2008-07-31 | Lakota Rd (formerly Conover) | Iron Grove | 1 | 138 |  | 290 | convert 69 to 138 kV | K5 | MI/WI | 73 |  | 50 |  | 25 | 25 | Planned | 69100000 | Eng | [6 empty] | A105, A215, F006 | Y | N | Y | ATC zone 2 |  | Y
A | 2460 | 2006-10-27 | BR | West | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2009-12-31 | Iron Grove | Aspen | 1 | 138 |  | 400 MVA SE |  | K5 | WI |  |  | 100 |  |  |  | Planned | 5850000 | [8 empty] | Y | N | Y | ATC zone 2
A | 896 | 2005-07-11 | SUB | C-WUMS | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2009-12-31 | Iron Grove | Substation relocation |  | 138 |  |  | Iron River rename/relocation | K5 | MI |  |  | 25 |  | 25 | 50 | Planned | 5900000 | Eng | [6 empty] | A215 | Y | N | Y |  |  | Y
A | 1371 | 2006-10-27 | BR | West | ATC LLC | 352 | 2006-03-16 | newgrp4 | 2009-12-31 | Aspen | Plains | 1 | 138 |  | 400 MVA SE |  | K5 | WI |  |  | 100 |  |  |  | Planned | 5850000 | [8 empty] | Y | N | Y | ATC zone 2
A | 2061 | 2006-10-04 | CAP | C-WUMS | ATC LLC | 432 | 2005-07-11 |  | 2006-11-01 | Summit Lake | Capacitor bank |  | 115 |  | 5.6 | upgrade existing 11.3 to 16.9 Mvar | K5 | WI | [5 empty] | 100 | Planned | 1000000 | Eng | [7 empty] | Y | N | Y
A | 2062 | 2006-07-05 | CAP | C-WUMS | ATC LLC | 433 | 2005-07-11 |  | 2007-06-01 | Wautoma | Capacitor bank |  | 138 |  | 2x24.5 Mvar |  | K6 | WI | [5 empty] | 100 | Planned | 1200000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
A | 2082 | 2006-07-05 | CAP | C-WUMS | ATC LLC | 446 | 2005-07-11 |  | 2007-04-30 | Rubicon | Capacitor bank |  | 138 |  | 32 Mvar | was Hartford | K7 | WI | [5 empty] | 100 | Planned | 750000 | Eng | [7 empty] | Y | N | Y | ATC zone 5
A | 1242 | 2006-04-05 | TX | C-WUMS | ATC LLC | 551 | 2005-07-11 |  | 2008-06-01 | Stone Lake 345-161kV | transformer | 1 | 345 | 161 | 300 |  | J6 | WI |  |  | 50 |  | 25 | 25 | Planned | 8100000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
A | 1244 | 2006-10-27 | LN | West | ATC LLC | 566 | 2006-10-04 |  | 2007-06-01 | Plymouth | Forest Junction/Charter Steel | 1 | 138 |  | 277 |  | K6 | WI |  | 1.3 | 100 |  |  |  | Planned | 2500000 | Eng | [7 empty] | Y | N | Y
A | 1259 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | North Shore | Bristol | 1 | 138 |  | 381 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 1610612 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1255 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | La Prairie RCEC | Bradford RCEC | 1 | 138 |  | 381 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 1610612 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1256 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | Bradford RCEC | West Darien | 1 | 138 |  | 381 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 3410708 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1258 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | Southwest Delavan | North Shore | 1 | 138 |  | 381 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 3410708 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1257 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | West Darien | Southwest Delavan | 1 | 138 |  | 381 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 1610612 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1260 | 2006-07-05 | BR | C-WUMS | ATC LLC | 570 | 2005-07-11 |  | 2009-06-01 | Bristol | Elkhorn | 1 | 138 |  | 292 |  | K7 | WI |  |  | 100 |  |  |  | Planned | 3410708 | Eng | [7 empty] | Y | N | Y | ATC zone 3
A | 1992 | 2006-10-27 | LN | West | ATC LLC | 571 | 2005-07-11 |  | 2008-06-01 | North Madison | Huiskamp | 1 | 138 |  | 481 MVA SE |  |  | WI | [6 empty] | Proposed | 8700000 | [8 empty] | Y | N | Y
A | 1263 | 2006-10-27 | LN | West | ATC LLC | 572 | 2006-10-04 |  | 2008-06-01 | West Marinette | Menominee | 1 | 138 |  | 345 |  | K5 | WI |  | 0.45 | 100 |  |  |  | Proposed | 1000000 | Eng | [7 empty] | Y | N | Y | ATC zone 4
A | 1262 | 2006-10-27 | LN | West | ATC LLC | 572 | 2006-10-04 |  | 2008-06-01 | Ingalls/Bay de Doc | Menominee | 1 | 138 |  | 345 |  | K5 | WI |  | 0.45 | 100 |  |  |  | Proposed | 1000000 | Eng | [7 empty] | Y | N | Y | ATC zone 4
A | 863 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Oak Creek | Ramsey |  | 138 |  | 293 | reconductor (need 382 MVA for A035) | L7 | WI | 8.5 |  |  | 100 |  |  | Proposed | 200000 | Eng | [6 empty] | G051, A035 | Y | N | Y | ATC zone 5 | Network | Y
A | 865 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Oak Creek | Relaying replacements |  | 230 |  |  | replace relaying | L7 | WI |  |  |  | 100 |  |  | Proposed | 2500000 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 866 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Pleasant Prairie | replace two circuit breakers |  | 345 |  |  | replace circuit breakers | L7 | WI |  |  |  | 100 |  |  | Proposed | 2357175 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 867 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Oak Creek | Expand 345 kV switchyard to interconnect new generator |  | 345 |  |  | expand switchyard to interconnect new generator | L7 | WI |  |  |  | 100 |  |  | Proposed | 19277005 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 868 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Ramsey | Norwich |  | 138 |  | 288 | loop Ramsey5-Harbor into Norwich and Kansas to form Ramsey-Norwich and Harbor-Kansas | L7 | WI | 3 |  |  | 100 |  |  | Proposed | 200000 | Eng | [6 empty] | G051, A035 | Y | N | Y |  | Interconnection | Y
A | 869 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Harbor | Kansas |  | 138 |  | 157 | loop Ramsey5-Harbor into Norwich and Kansas to form Ramsey-Norwich and Harbor-Kansas | L7 | WI | 2.72 |  |  | 100 |  |  | Proposed | 200000 | Eng | [6 empty] | G051, A035 | Y | N | Y |  | Interconnection | Y
A | 482 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Oak Creek 345/138 #2 | transformer | 2 | 345 | 138 | 500 |  | L7 | WI |  |  | 25 | 75 |  |  | Planned | 6600000 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 864 | 2006-04-05 | BR | C-WUMS | ATC LLC | 877 | 2006-03-16 | new100 | 2009-06-01 | Oak Creek | Allerton |  | 138 |  | 242 | reconductor | L7 | WI | 5.4 |  |  | 100 |  |  | Proposed | 2000000 | Eng | [6 empty] | G051, A035 | Y | N | Y | ATC zone 5 | Network | Y
A | 870 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2010-06-01 | Oak Creek | Expand 345 kV switchyard to interconnect second new generator |  | 345 |  |  | expand switchyard to interconnect second new generator | L7 | WI |  |  |  | 100 |  |  | Proposed | 10600000 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 872 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2010-06-01 | Oak Creek | Root River |  | 138 |  | 293 | uprate | L7 | WI |  |  |  | 100 |  |  | Proposed | 136007 | Eng | [6 empty] | G051 | Y | N | Y | ATC zone 5 | Interconnection
A | 873 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2010-06-01 | Oak Creek | Nicholson |  | 138 |  | 332 | uprate | L7 | WI | 6.8 |  |  | 100 |  |  | Proposed | 136007 | Eng | [6 empty] | G051 | Y | N | Y | ATC zone 5 | Interconnection
A | 871 | 2006-10-27 | BR | West | ATC LLC | 877 | 2006-03-16 | new100 | 2010-06-01 | Kansas | Ramsey6 |  | 138 |  | 290 | uprate | L7 | WI | 5.7 |  |  | 100 |  |  | Proposed | 500000 | Eng | [6 empty] | G051 | Y | N | Y |  | Interconnection
A | 132 | 2006-10-04 | BR | C-WUMS | ATC LLC | 1451 | 2005-11-18 | 11 | 2007-06-01 | Sprecher | Reiner (conversion to 138 kV) |  | 138 |  | 366 | conversion to 138 | K7 | WI | 10 |  | 75 |  |  | 25 | Under Construction | 1250000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 131 | 2006-10-04 | BR | C-WUMS | ATC LLC | 1451 | 2005-11-18 | 11 | 2007-06-01 | Reiner | Sycamore (conversion to 138 kV) |  | 138 |  | 366 | conversion to 138 | K7 | WI | 7 |  | 75 |  |  | 25 | Under Construction | 1250000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 123 | 2006-10-04 | BR | C-WUMS | ATC LLC | 1451 | 2005-11-18 | 11 | 2007-06-01 | Femrite | Sprecher (new 138 kV) | 1 | 138 |  | 348 | new 138 kV line | K7 | WI |  | 5 | 50 |  | 50 |  | Under Construction | 8100000 | Eng | [6 empty] | A130 | Y | N | Y | ATC zone 3 |  | Y
A | 182 | 2005-07-11 | BR | E-MIO | CIN | 42 | 2005-07-11 | 17 | 2007-06-01 | Bedford | Shawswick | 1 | 138 |  | 306 | Reconductor Bedford to Shawswick section of 13829 line. | M10 | IN | 7.1 |  | 100 |  |  |  | Planned | 2110106 | Engr |  | Y | [5 empty] | Y | N | Y
A | 184 | 2005-07-11 | BR | E-MIO | CIN | 42 | 2005-07-11 | 17 | 2009-06-01 | Shawswick | Pleasant Grove | 1 | 138 |  | 306 | Reconductor | M10 | IN | 18.3 |  | 100 |  |  |  | Planned | 4719516 | Engr |  | Y | [5 empty] | Y | N | Y
A | 181 | 2005-07-11 | BR | E-MIO | CIN | 42 | 2005-07-11 | 17 | 2009-06-01 | Airport Road Jct | Seymour | 1 | 138 |  | 306 MVA | Reconductor | M10 | IN | 2.2 | 0 | 100 | 0 | 0 | 0 | Planned | 752906 | Engr |  | Y | [5 empty] | Y | N | Y
A | 183 | 2005-07-11 | BR | E-MIO | CIN | 42 | 2005-07-11 | 17 | 2009-06-01 | Pleasant Grove | Airport Road Jct | 1 | 138 |  | 306 | Reconductor | M10 | IN | 9.3 |  | 100 |  |  |  | Planned | 3388077 | Engr |  | Y | [5 empty] | Y | N | Y
A | 362 | 2005-07-11 | BR | E-MIO | CIN | 91 | 2005-07-11 | 72 | 2008-06-01 | Hillcrest | Eastwood | 1 | 138 |  | 304 | Add new line | N10 | OH |  | 8 | 100 |  |  |  | Planned | 4613151 | Engr |  | Y | [5 empty] | Y | N | Y
A | 358 | 2005-11-28 | TX | E-MIO | CIN | 91 | 2005-07-11 | 72 | 2008-06-01 | Hillcrest 345/138 | transformer | 1 | 345 | 138 | 450 | Add new 345/138 substation | N10 | OH |  |  | 100 |  |  |  | Planned | 5693185.59 | Engr |  | Y | [5 empty] | Y | N | Y
A | 366 | 2005-07-11 | BR | E-MIO | CIN | 115 | 2005-07-11 | 86 | 2007-06-01 | New London | Webster | 1 | 230 |  | 800 | reconductor | M9 | IN | 12 |  | 100 |  |  |  | Planned | 9455194 | Engr |  | Y | [5 empty] | Y | N | Y
A | 357 | 2005-07-11 | TX | E-MIO | CIN | 116 | 2005-07-11 | 87 | 2007-06-01 | Westwood 345/138 | transformer | 2 | 345 | 138 | 336 | Add 2nd 345/138 transformer | L9 | IN |  |  | 100 |  |  |  | Planned | 6093584 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1307 | 2005-07-11 | BR | E-MIO | CIN | 116 | 2005-07-11 |  | 2007-06-01 | West Lafayette | Cumberland | 1 | 138 |  | 179 | replace 600A switches | M9 | IN | 0 | 0 | 100 |  |  |  | Planned | 154757 | Engr |  | Y | [5 empty] | Y | N | Y
A | 367 | 2005-07-11 | BR | E-MIO | CIN | 116 | 2005-07-11 | 87 | 2007-06-01 | Westwood | Dequine | 1 | 345 |  | 1200 | Add 2nd 345kV line | L9 | IN |  | 2 | 100 |  |  |  | Planned | 588366 | Engr |  | Y | [5 empty] | Y | N | Y
A | 356 | 2005-07-11 | TX | E-MIO | CIN | 199 | 2005-07-11 |  | 2007-06-01 | Kokomo 230/138 | transformer | 2 | 230 | 138 | 200 | Add fourth 230/138kV transformer. | M9 | IN |  |  | 100 |  |  |  | Planned | 3278756 | Engr |  | Y | [5 empty] | Y | N | Y
A | 618 | 2005-07-11 | BR | E-MIO | CIN | 200 | 2005-07-11 |  | 2007-06-01 | West Lafayette Purdue | Purdue NW Tap | 1 | 138 |  | 179 | Upgrade switches at West Lafayette Purdue. | L9 | IN | 7.2 |  | 100 |  |  |  | Planned | 9877 | Engr |  | Y | [5 empty] | Y | N | Y
A | 536 | 2005-07-11 | BR | E-MIO | CIN | 201 | 2005-07-11 |  | 2008-06-01 | NW Tap | West Lafayette | 1 | 138 |  | 240 | Changing out switches to achieve conductor rating. | L9 | IN | 0 |  | 100 |  |  |  | Planned | 100000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1292 | 2006-03-27 | BR | E-MIO | CIN | 619 | 2006-03-10 |  | 2006-12-31 | IPL Petersburg | 345kV breaker |  | 345 |  |  | Complete breaker and half scheme at Petersburg Plant. IPL total estimate 1,100,000. 200k is Cinergy share of project. | M10 | IN | 0 | 0 | 100 |  |  |  | Planned | 200000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1300 | 2006-10-10 | BR | E-MIO | CIN | 624 | 2005-07-11 |  | 2007-12-31 | Cloverdale | Plainfield South | 1 | 138 |  | No change | Upgrade static and grounding | L10 | IN | 24.3 | 0 | 100 |  |  |  | Planned | 2387209 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1953 | 2006-03-27 | BR | E-MIO | CIN | 627 | 2005-07-13 | 304D7834 | 2007-06-01 | Crescent | West End |  | 138 |  | 239 | 3 wires of existing 6 wire circuit will be used for the new Kenton to West End circuit, lowering the rating of Crescent to West End. |  |  |  |  | 100 |  |  |  | Planned |  |  |  | Y | [5 empty] | Y | N | Y
A | 1304 | 2006-07-05 | BR | E-MIO | CIN | 627 | 2005-07-13 | 304D7834 | 2009-06-01 | Kenton | West End | 1 | 138 |  | 239 | Add new line | N10 | KY-OH | 4.5 | 4.3 | 100 |  |  |  | Planned | 1980041 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1853 | 2006-10-10 | DV | E-MIO | CIN | 627 | 2005-07-13 |  | 2009-06-01 | Buffington Reactor | Florence |  | 138 |  |  | Remove reactor when Kenton to West End project is completed. |  | KY |  |  | 100 |  |  |  | Planned | [9 empty] | Y | N | Y
A | 1305 | 2005-07-11 | BR | E-MIO | CIN | 628 | 2005-07-11 |  | 2007-06-01 | Kokomo Highland Park | Kokomo Chrysler | 1 | 138 |  | 179 | Kok 13879 Uprate conductor to 100C operating temp | M9 | IN | 3 | 0 | 100 |  |  |  | Planned | 100000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1306 | 2005-07-11 | BR | E-MIO | CIN | 629 | 2005-07-11 | 628A | 2007-06-01 | Kokomo Highland Park | Kokomo Delco | 1 | 138 |  | 179 | Kok 13887 Uprate conductor to 100C operating temp | M9 | IN | 3.78 | 0 | 100 |  |  |  | Planned | 100000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1308 | 2006-03-27 | BR | E-MIO | CIN | 631 | 2005-07-11 |  | 2006-12-31 | Columbus | Seymour | 1 | 138 |  | 179 | replace 600A switches at Columbus, limit becomes 397ACSR30X7 at 179MVA. | M10 | IN | 0 | 0 | 100 |  |  |  | Planned | 65695 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1309 | 2005-07-11 | BR | E-MIO | CIN | 632 | 2005-07-11 |  | 2009-06-01 | Gallagher | HE Georgetown | 1 | 138 |  | 202 | reconducgtor 250CU, 477ACSR already 100C (no cost) | M10 | IN | 2.8 | 0 | 100 |  |  |  | Planned | 1065110 | Engr |  | Y | [5 empty] | Y | N | Y
A | 3058 | 2005-07-11 | CAP | E-MIO | CIN | 765 | 2005-07-11 |  | 2006-12-01 | Cloverdale | Capacitor |  | 138 |  | 43.2 Mvar | Add capacitor | L10 | IN |  |  | 100 |  |  |  | Planned | 524860 | Engr |  | Y | [5 empty] | Y | N | Y
A | 3060 | 2005-07-11 | CAP | E-MIO | CIN | 766 | 2005-07-11 |  | 2007-06-01 | Clarksville | Capacitor |  | 138 |  | 57.6 Mvar | Add capacitor | M10 | IN |  |  | 100 |  |  |  | Planned | 738662 | Engr |  | Y | [5 empty] | Y | N | Y
A | 3062 | 2005-07-11 | CAP | E-MIO | CIN | 767 | 2005-07-11 |  | 2007-06-01 | Greenfield Hastings Park | Capacitor |  | 138 |  | 57.6 Mvar | Add capacitor | M9 | IN |  |  | 100 |  |  |  | Planned | 598722 | Engr |  | Y | [5 empty] | Y | N | Y
A | 813 | 2005-07-11 | TX | E-MIO | CIN | 807 | 2005-07-11 | B | 2009-06-01 | Dresser 345/138 Bk2 | transformer | 2 | 345 | 138 | 543 | Upgrade limiting equipment to achieve full transformer rating | L10 | IN |  |  | 100 |  |  |  | Planned | 429000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
A | 812 | 2005-07-11 | TX | E-MIO | CIN | 807 | 2005-07-11 | B | 2009-06-01 | Dresser 345/138 Bk1 | transformer | 1 | 345 | 138 | 523 | Upgrade limiting equipment to achieve full transformer rating | L10 | IN |  |  | 100 |  |  |  | Planned | 429000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
A | 817 | 2005-07-11 | CAP | E-MIO | CIN | 838 | 2005-07-11 | AG | 2006-12-31 | Speed | Capacitor |  | 138 |  | 57.6 MVAR | Add capacitor | M10 | IN |  |  | 100 |  |  |  | Planned | 500000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 818 | 2006-03-27 | CAP | E-MIO | CIN | 839 | 2005-07-11 | AH | 2007-06-01 | Crawfordsville | Capacitor |  | 138 |  | 28.8 MVAR | Add capacitor | L9 | IN |  |  | 100 |  |  |  | Planned | 500000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 822 | 2006-10-10 | BR | E-MIO | CIN | 842 | 2005-07-11 |  | 2007-04-30 | Blackwell | LGEE Tap |  | 138 |  |  | 138 line for Blackwell 138/69, LGEE circuit | N10 | KY |  |  | 100 |  |  |  | Planned | 589000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
A | 823 | 2005-07-11 | BR | E-MIO | CIN | 849 | 2005-07-11 | AR | 2007-06-01 | Peabody Jct | Jasonville | 1 | 138 |  | 246 | Replace Peabody Jct 600A switches with 1200A towards Jasonville in the 13821 line, 804F6402 | L10 | IN |  |  | 100 |  |  |  | Planned | 159170.5 | Engr |  | Y | [5 empty] | Y | N | Y
A | 824 | 2005-07-11 | BR | E-MIO | CIN | 849 | 2005-07-11 | AR | 2007-06-01 | Peabody Jct | Farmersburg Jct | 1 | 138 |  | 246 | Replace Peabody Jct 600A switches with 1200A towards Farmersburg Jct in the 13821 line, 804F6402 | L10 | IN |  |  | 100 |  |  |  | Planned | 159170.5 | Engr |  | Y | [5 empty] | Y | N | Y
A | 826 | 2005-07-11 | BR | E-MIO | CIN | 851 | 2005-07-11 | AT | 2011-06-01 | Lafayette Cumberland Ave | Laf AE Staley | 1 | 138 |  | 306 | 13806 reconductor with 954ACSR 100C 604F6347 | L9 | IN | 1.3 |  | 100 |  |  |  | Planned | 325000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
A | 1843 | 2005-11-28 | BR | E-MIO | CIN | 1193 | 2006-10-02 | 104F8436 | 2010-06-01 | Nickel |  |  | 138 |  |  | Extend 5680 through new Nickel 138/12 sub to be built on development property |  | OH |  |  | 100 |  |  |  | Planned | 150376.81 | Engr | [7 empty] | Y | N | Y
A | 1845 | 2006-07-05 | BR | E-MIO | CIN | 1195 | 2005-11-28 | 604E6256 | 2007-05-01 | Cloverdale | Cloverdale Ethanol | 1 | 138 |  |  | Construct new 138kV line from Cloverdale to new Putnam Energy ethanol plant. |  | IN |  |  | 100 |  |  |  | Planned | 229811 | Engr | [7 empty] | Y | N | Y
A | 1847 | 2006-07-05 | BR | E-MIO | CIN | 1196 | 2005-11-28 | 602C5687 | 2006-12-31 | Kokomo Highland Park | New London | 1 | 230 |  | 405 | Replace Kokomo Highland Park 23009 800A wave trap with a 1200A wave trap. |  | IN |  |  | 100 |  |  |  | Planned | [9 empty] | Y | N | Y
A | 1846 | 2006-07-05 | BR | E-MIO | CIN | 1196 | 2005-11-28 | 602F6290 | 2006-12-31 | New London | Kokomo Highland Park | 1 | 230 |  | 405 | Replace New London 23009 800A wave trap with a 1200A wave trap. |  | IN |  |  | 100 |  |  |  | Planned | 29671.83 | Engr | [7 empty] | Y | N | Y
A | 1849 | 2005-11-28 | DV | E-MIO | CIN | 1198 | 2005-11-28 | 802F6503 | 2007-06-01 | Bedford |  |  | 345 |  |  | Add motors and automation to the 34506 and 34521 line switches. |  | IN |  |  | 100 |  |  |  | Planned | 152390.14 | Engr | [7 empty] | Y | N | Y
A | 1851 | 2005-11-28 | BR | E-MIO | CIN | 1199 | 2005-11-28 | 804F6505 | 2010-06-01 | Terre Haute South 1st St | Terre Haute Water St | 1 | 138 |  | 287 | Uprate 13868 conductor to 100C operating temperature from South 1st St to Water St. New limit 1200A terminal equipment. |  | IN |  |  | 100 |  |  |  | Planned | 10000 | Engr | [7 empty] | Y | N | Y
A | 1850 | 2005-11-28 | BR | E-MIO | CIN | 1199 | 2005-11-28 | 804F6505 | 2010-06-01 | Dresser | Terre Haute South 1st St | 1 | 138 |  | 287 | Uprate 13868 conductor to 100C operating temperature from Dresser to South 1st St. New limit 1200A terminal equipment. |  | IN |  |  | 100 |  |  |  | Planned | 10000 | Engr | [7 empty] | Y | N | Y
A | 1852 | 2005-11-28 | BR | E-MIO | CIN | 1200 | 2005-11-28 | 702F6501 | 2010-06-01 | Speed |  | 3 | 345 | 138 | 520 | Upgrade 2000A 138kV breaker & switch and any other Bk3 limiting equipment. Replace any equipment that would limit the 345/138 xfr to less than the hot spot rating of 520 MVA. |  | IN |  |  | 100 |  |  |  | Planned | 173193.11 | Engr | [7 empty] | Y | N | Y
A | 1854 | 2006-07-05 | BR | E-MIO | CIN | 1201 | 2005-11-28 | 804C5822 | 2006-12-31 | Oakland City | Princeton | 1 | 138 |  | 287 | Uprate line to 100C operating temperature by adding 3 structures. |  | IN |  |  | 100 |  |  |  | Planned | 111331 | Engr | [7 empty] | Y | N | Y
A | 1946 | 2006-03-27 | BR | E-MIO | CIN | 1244 | 2006-03-27 | 602G6558 | 2011-06-01 | Frankfort 23013 Wave Trap | Cayuga |  | 230 |  | 797 | Replace 1600A wave trap with a 2000A wave trap. Increase line rating of the Cayuga to Frankfort 23013 line. |  | IN |  |  | 100 |  |  |  | Planned | 98827 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1945 | 2006-03-27 | BR | E-MIO | CIN | 1244 | 2006-03-27 | 802G6557 | 2011-06-01 | Cayuga 23013 Wave Trap | Frankfort |  | 230 |  | 797 | Replace 1600A wave trap with a 2000A wave trap. Increase line rating of the Cayuga to Frankfort 23013 line. |  | IN |  |  | 100 |  |  |  | Planned | 68733 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1947 | 2006-03-27 | BR | E-MIO | CIN | 1246 | 2006-03-27 | 602G6548 | 2011-06-01 | Five Points 23030 Wave Trap | Geist |  | 230 |  | 405 | Replace 800A wave trap with a 2000A wave trap. Increase line rating to Geist. |  | IN |  |  | 100 |  |  |  | Planned | 24038 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1948 | 2006-03-27 | BR | E-MIO | CIN | 1247 | 2006-03-27 | 604G6544 | 2011-06-01 | Greentown | Peru SE |  | 230 |  | 478 | Uprate 23021 circuit to 100C operating temp |  | IN |  |  | 100 |  |  |  | Planned | 28403 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1949 | 2006-03-27 | BR | E-MIO | CIN | 1251 | 2006-03-27 | 602C5687 | 2006-12-31 | Kokomo Highland Park 23008 Wave Trap | Carmel 146th St Jct |  | 230 |  | 405 | Replace 800A wave trap with a 2000A wave trap. Increase 230kV line rating to Carmel 146th St Jct. |  | IN |  |  | 100 |  |  |  | Planned | 30000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1950 | 2006-03-27 | BR | E-MIO | CIN | 1251 | 2006-03-27 | 502G6545 | 2011-06-01 | Noblesville 23008 Wave Trap | Carmel 146th St Jct |  | 230 |  | 405 | Replace 800A wave trap with a 2000A wave trap. Increase 230kV line rating to Carmel 146th St Jct. |  | IN |  |  | 100 |  |  |  | Planned | 24038 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1951 | 2006-03-27 | BR | E-MIO | CIN | 1252 | 2006-03-27 | 602C5687 | 2006-12-31 | Kokomo Highland Park 23028 Wave Trap | Thorntown |  | 230 |  | 405 | Replace 800A wave trap with a 2000A wave trap. Increase 230kV line rating to Thorntown. |  | IN |  |  | 100 |  |  |  | Planned | 30000 | Plan |  | Y | [5 empty] | Y | N | Y
A | 1952 | 2006-03-27 | BR | E-MIO | CIN | 1253 | 2006-03-27 | 502G6547 | 2011-06-01 | Noblesville 23007 Wave Trap | Geist |  | 230 |  | 405 | Replace 800A wave trap with a 2000A wave trap. Increase line rating to Geist. |  | IN |  |  | 100 |  |  |  | Planned | 24038 | Engr |  | Y | [5 empty] | Y | N | Y
A | 1955 | 2006-10-10 | BR | E-MIO | CIN | 1254 | 2006-03-27 | 704G6587 | 2009-12-31 | Charlestown | CMC |  | 138 |  | 306 | Construct 8.5 mi. of 138kV line from Charlestown to CMC. |  | IN |  |  | 100 |  |  |  | Planned |  |  |  | Y | [5 empty] | Y | N | Y
A | 1978 | 2006-10-10 | BR | E-MIO | CIN | 1262 | 2006-07-05 | 702G6641 | 2007-12-31 | HE Durgee Rd |  |  | 138 |  |  | HE 138/12 kV substation. |  | IN |  |  | 100 |  |  |  | Planned | 227341 | Engr |  | Y | [5 empty] | Y | N | Y
A | 807 | 2006-10-15 | BR | N-NM | DPC/XEL | 584 | 2005-06-15 |  | 2007-06-01 | Genoa | Coulee | 1 | 161 |  | 375 |  | E13 | WI | 18.7 |  | 100 |  |  |  | Planned | 4057132 | [8 empty] | Y | Y | Y
A | 1283 | 2006-10-03 | BR | E-MIO | FE | 615 | 2006-10-03 |  | 2007-12-01 | Galion 345-138 kV | transformer prep. |  | 345 | 138 |  | Protection upgrades to separate existing transformers, so they don't trip together | O8 | OH |  |  | 100 |  |  |  | Planned | 1815566 | [8 empty] | Y | N | Y
A | 1284 | 2006-10-03 | BR | E-MIO | FE | 616 | 2006-10-03 |  | 2007-06-01 | Crissinger | Tangy | 1 | 138 |  | 275 MVA |  | O8 | OH | 23 |  | 100 |  |  |  | Planned | 2713000 | [8 empty] | Y | N | Y
A | 899 | 2006-10-03 | BR | E-MIO | FE | 890 | 2006-10-03 |  | 2008-06-01 | North Medina new 345-138 kV | substation | 4 | 345 | 138 |  | Add a new 345/138kV substation at the junction of the Star-Carlisle 345kV and Star-West Akron #2 138kV lines | O8 | OH |  |  | 100 |  |  |  | Planned | 8405000 | [8 empty] | Y | N | Y
A | 2186 | 2006-10-09 | DV | East | FE | 1316 | 2006-09-11 | COH-06-060313-125705 | 2007-06-01 | Dale | West Canton | 1 | 138 |  | 208/281 MVA | Add reactor at Dale end of the Dale to West Canton 138 kV line. |  | OH | [6 empty] | Under Construction | 401800 | [8 empty] | Y | N | Y | with MISO
A | 2191 | 2006-10-09 | CAP | East | FE | 1326 | 2006-09-13 | NOH-07-060221-152713 | 2008-06-01 | Harding | capacitor bank |  | 345 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 2727173 | [8 empty] | Y | N | Y | with MISO
A | 2192 | 2006-10-09 | CAP | East | FE | 1326 | 2006-09-13 | NOH-07-060221-152713 | 2009-06-01 | Juniper | capacitor bank |  | 345 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 2727173 | [8 empty] | Y | N | Y | with MISO
A | 2193 | 2006-10-09 | CAP | East | FE | 1327 | 2006-09-13 | COH-06-050519-151858 | 2009-06-01 | Babb | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 488600 | [8 empty] | Y | N | Y | with MISO
A | 2194 | 2006-10-09 | CAP | East | FE | 1328 | 2006-09-13 | COH-07-050622-154415 | 2010-06-01 | Barberton | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 677600 | [8 empty] | Y | N | Y | with MISO
A | 2195 | 2006-10-09 | CAP | East | FE | 1329 | 2006-09-13 | COH-07-050623-094932 | 2009-06-01 | West Akron | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 257000 | [8 empty] | Y | N | Y | with MISO
A | 2196 | 2006-10-09 | CAP | East | FE | 1330 | 2006-09-13 | COH-07-050623-095518 | 2007-06-01 | South Akron | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 426000 | [8 empty] | Y | N | Y | with MISO
A | 2197 | 2006-10-09 | CAP | East | FE | 1331 | 2006-09-13 | COH-06-050519-152347 | 2011-06-01 | East Akron | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 305000 | [8 empty] | Y | N | Y | with MISO
A | 2198 | 2006-10-09 | CAP | East | FE | 1332 | 2006-09-13 | COH-06-060313-125000 | 2009-06-01 | Cloverdale | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 378000 | [8 empty] | Y | N | Y | with MISO
A | 2199 | 2006-10-09 | CAP | East | FE | 1333 | 2006-09-13 | SOH-06-050509-071724 | 2010-06-01 | Brookside | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 1000200 | [8 empty] | Y | N | Y | with MISO
A | 2200 | 2006-10-09 | CAP | East | FE | 1334 | 2006-09-13 | SOH-06-050509-072919 | 2010-06-01 | Longview | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 523800 | [8 empty] | Y | N | Y | with MISO
A | 2201 | 2006-10-09 | CAP | East | FE | 1335 | 2006-09-13 | SOH-07-050509-073659 | 2007-06-01 | Roberts | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Planned | 379285 | [8 empty] | Y | N | Y | with MISO
A | 2202 | 2006-10-09 | BR | East | FE | 1336 | 2006-09-13 | SOH-06-050506-150255 | 2007-12-01 | Gallion | capacitor bank |  | 138 |  |  | Breaker Addition |  | OH | [6 empty] | Under Construction | 1815566 | [8 empty] | Y | N | Y | with MISO
A | 2189 | 2006-10-09 | CB | East | FE | 1350 | 2006-10-03 | COH-06-060313-112229 | 2007-06-01 | Cloverdale | breaker |  | 138 |  |  | Breaker Addition |  | OH | [6 empty] | Under Construction | 630900 | [8 empty] | Y | N | Y | with MISO
A | 1076 | 2005-11-28 | BR | N-NM | GRE | 596 | 2005-06-15 |  | 2007-05-01 | Vermillion River | Empire | 1 | 115 |  | 200 |  | TC detail | MN |  | 6 | 100 |  |  |  | Planned | 2750000 | [8 empty] | Y | Y | Y
A | 641 | 2005-06-30 | BR | N-NM | GRE | 601 | 2005-06-15 |  | 2008-06-01 | Mud Lake | Wilson Lake | 1 | 115 |  | 142 |  | H5 | MN | 12 |  | 100 |  |  |  | Planned | 6000000 | [8 empty] | Y | Y | Y
A | 2121 | 2006-08-24 | BR | N-NM | GRE | 1290 | 2006-08-24 | 12 | 2006-12-31 | WILLMAR4 (63050) | GRANITF4 (66550) | 1 | 230 |  | 382/382 | Replace CTs and Wavetrap |  | MN | 0 | 0 |  |  |  |  | Planned | 250000 | [8 empty] | Y | Y | Y
A | 2171 | 2006-09-08 | SUB | E-MIO | HE | 1318 | 2006-09-08 | 925 | 2007-09-01 | Decatur County Switch Station (DCSS) | 138kV Switching Station w/Capacitor | 1 | 138 |  | 30MVAR | New Construction |  | IN |  |  | 100 |  |  |  | Planned | 3000000 | [8 empty] | Y | N | Y
A | 2172 | 2006-09-08 | TX | E-MIO | HE | 1318 | 2006-09-08 | 925 | 2007-09-01 | Decatur County Switch Station (DCSS) | 161/138kV Transformer | 1 | 161 | 138 | 250MVA | New Construction |  | IN |  |  | 100 |  |  |  | Planned | 1000000 | [8 empty] | Y | N | Y
A | 2173 | 2006-09-08 | CB | E-MIO | HE | 1318 | 2006-09-08 | 925 | 2007-09-01 | Decatur County Switch Station (DCSS) | 138kV 6-Breaker Ringbus | 1 | 138 |  | 2000Amp | New Construction |  | IN |  |  | 100 |  |  |  | Planned | 3000000 | [8 empty] | Y | N | Y
A | 2174 | 2006-09-08 | LN | E-MIO | HE | 1319 | 2006-09-08 | 825 | 2007-09-01 | Decatur County Switch Station (DCSS) | Cinergy 138 (Greensburg to Shelbyville) | 1 | 138 |  | 327MVA | New Construction |  | IN |  | 0.5 | 100 |  |  |  | Planned | 500000 | [8 empty] | Y | N | Y
A | 2178 | 2006-09-08 | LN | E-MIO | HE | 1320 | 2006-09-08 | 826 | 2007-09-01 | Greensburg Honda | DCSS | 1 | 138 |  | 215MVA | New Construction West Loop |  | IN |  | 5.5 | 100 |  |  |  | Planned | 1875000 | [8 empty] | Y | N | Y
A | 2177 | 2006-09-08 | LN | E-MIO | HE | 1320 | 2006-09-08 | 826 | 2007-09-01 | Greensburg Honda | DCSS | 1 | 138 |  | 215MVA | New Construction East Loop |  | IN |  | 5.5 | 100 |  |  |  | Planned | 1875000 | [8 empty] | Y | N | Y
A | 2180 | 2006-09-08 | LN | E-MIO | HE | 1321 | 2006-09-08 | 827 | 2008-09-01 | Napoleon Primary | DCSS | 1 | 161 |  | 338MVA | New Construction |  | IN |  | 25 | 100 |  |  |  | Planned | 7200000 | [8 empty] | Y | N | Y
A | 2179 | 2006-09-08 | sub | E-MIO | HE | 1321 | 2006-09-08 | 927 | 2008-09-01 | Napoleon | Capacitor & CB Addition, and bus upgrades | 1 | 161 |  | 30MVAR | New Construction |  | IN |  |  | 100 |  |  |  | Planned | 800000 | [8 empty] | Y | N | Y
A | 2182 | 2006-09-08 | LN | E-MIO | HE | 1322 | 2006-09-08 | 829 | 2008-04-01 | Owensville Primary Tapline | Cinergy 138 (Gibson to Princeton) | 1 | 138 |  | 215MVA | New Construction |  | IN |  | 0.5 | 100 |  |  |  | Planned | 2500000 | [8 empty] | Y | N | Y
A | 2183 | 2006-09-08 | SUB | E-MIO | HE | 1323 | 2006-09-08 | 930 | 2008-04-01 | Sandborn Primary w/tap | HE 161 Transmission | 1 | 161 |  | 150MVA | New Construction |  | IN |  | 0.1 | 100 |  |  |  | Planned | 6000000 | [8 empty] | Y | N | Y
A | 178 | 2006-10-03 | BR | E-MIO | IPL | 40 | 2006-10-03 | IPL-05 | 2008-06-01 | Cumberland | Julietta | 1 | 138 |  | 286 MVA | New 138kV Line | M9 | IN |  | 4.55 | 100 |  |  |  | Planned | 866172.79 | [8 empty] | Y | N | Y
A | 177 | 2006-10-03 | BR | E-MIO | IPL | 40 | 2006-10-03 | IPL-05 | 2008-06-01 | Indian Creek | Julietta | 1 | 138 |  | 286 MVA | New 138kV Line | M9 | IN |  | 5 | 100 |  |  |  | Planned | 951838.23 | [8 empty] | Y | N | Y
A | 902 | 2006-10-03 | CAP | E-MIO | IPL | 893 | 2006-10-03 | IPL-02 | 2008-06-01 | North | Capacitor |  | 138 |  | 150 MVAR | Increase Capacitor Size To 150 MVAR | M9 | IN |  |  | 100 |  |  |  | Planned | 300000 | [8 empty] | Y | N | Y
A | 905 | 2006-10-03 | DV | E-MIO | IPL | 895 | 2006-10-03 | IPL-04 | 2007-07-01 | North | Breaker |  | 138 |  | 245 MVA | New 2000 Amp Breaker | M9 | IN |  |  | 100 |  |  |  | Under Construction | 1500000 | [8 empty] | Y | N | Y
A | 904 | 2006-10-03 | DV | E-MIO | IPL | 895 | 2006-10-03 | IPL-04 | 2007-07-01 | North | Breaker |  | 138 |  | 245 MVA | New 2000 Amp Breaker | M9 | IN |  |  | 100 |  |  |  | Under Construction | 1500000 | [8 empty] | Y | N | Y
A | 758 | 2006-03-06 | TX | E-MIO | ITC | 503 | 2005-08-10 | 503 | 2006-12-31 | Wixom 345/230 | transformer | 1 | 345 | 230 | 782 |  | M9 | MI | 0 | 0 |  |  | 50 | 50 | Planned | 5000000 | [8 empty] | Y | N | Y
A | 757 | 2006-03-06 | BR | E-MIO | ITC | 503 | 2005-08-10 | 503 | 2006-12-31 | Wixom 230 | Quaker 230 | 1 | 230 |  | 657 |  | M9 | MI | 5 | 4.3 |  |  | 50 | 50 | Planned | 2300000 | [8 empty] | Y | N | Y
A | 759 | 2006-03-06 | TX | E-MIO | ITC | 503 | 2005-08-10 | 503 | 2006-12-31 | Quaker 230-120 kV | transformer | 1 | 230 | 120 | 634 |  | M9 | MI | 0 | 0 |  |  | 50 | 50 | Planned | 1500000 | [8 empty] | Y | N | Y
A | 760 | 2005-07-08 | BR | E-MIO | ITC | 503 | 2005-08-10 | 503 | 2007-05-30 | Hancock 120 | Southfield 120 | 1 | 120 |  | 244 |  | N7 | MI | 3.7 |  |  |  | 50 | 50 | Planned | 1200000 | [8 empty] | Y | N | Y
A | 763 | 2006-03-06 | TX | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 345-120 kV | transformer | 1 | 345 | 120 | 500 |  | O7 | MI |  | 0 |  |  |  | 100 | Planned | 5000000 | [8 empty] | Y | N | Y
A | 766 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 120 | Augusta Tap 120 | 1 | 120 |  | 343 |  | O7 | MI | 4.98 |  |  |  |  | 100 | Planned | 1300000 | [8 empty] | Y | N | Y
A | 767 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 120 | Grayling 2 120 | 1 | 120 |  | 313 |  | O7 | MI | 10.8 |  |  |  |  | 100 | Planned | 1300000 | [8 empty] | Y | N | Y
A | 768 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 120 | Grayling 1 120 | 1 | 120 |  | 313 |  | O7 | MI | 10.8 |  |  |  |  | 100 | Planned | 1300000 | [8 empty] | Y | N | Y
A | 765 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 120 | Victor 120 | 1 | 120 |  | 313 |  | O7 | MI | 1.08 |  |  |  |  | 100 | Planned | 1300000 | [8 empty] | Y | N | Y
A | 762 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 345 | Belle River 345 | 1 | 345 |  | 2002 |  | O7 | MI | 19.1 |  |  |  |  | 100 | Planned | 1750000 | [8 empty] | Y | N | Y
A | 761 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 345 | Jewel 345 | 1 | 345 |  | 2007 |  | O7 | MI | 8.7 |  |  |  |  | 100 | Planned | 1750000 | [8 empty] | Y | N | Y
A | 764 | 2006-03-06 | BR | E-MIO | ITC | 509 | 2005-08-10 | 509 | 2006-12-31 | Lenox 120 | St Clair 120 | 1 | 120 |  | 312.8 |  | O7 | MI | 19.5 |  |  |  |  | 100 | Planned | 1300000 | [8 empty] | Y | N | Y
A | 771 | 2005-07-08 | BR | E-MIO | ITC | 518 | 2005-08-10 | 518 | 2007-05-30 | Golf 120 | Houston 2 120 | 1 | 120 |  | 313 |  | O7 | MI | 17.3 |  |  |  |  | 100 | Planned | 1200000 | [8 empty] | Y | N | Y
A | 770 | 2005-07-08 | BR | E-MIO | ITC | 518 | 2005-08-10 | 518 | 2007-05-30 | Golf 120 | Boyne 120 | 1 | 120 |  | 290 |  | O7 | MI | 4.2 | 0.64 |  |  |  | 100 | Planned | 1200000 | [8 empty] | Y | N | Y
A | 773 | 2005-07-08 | BR | E-MIO | ITC | 518 | 2005-08-10 | 518 | 2007-05-30 | Golf 120 | Macomb 120 #2 | 2 | 120 |  | 291 |  | O7 | MI | 3.2 |  |  |  |  | 100 | Planned | 1600000 | [8 empty] | Y | N | Y
A | 2100 | 2005-11-28 | DV | E-MIO | ITC | 578 | 2005-08-10 | 578 | 2006-12-31 | Wyatt | DVAR |  | 120 |  | 30 Mvar |  | N9 | MI |  |  | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | N | Y
A | 774 | 2006-07-05 | BR | E-MIO | ITC | 586 | 2005-08-10 |  | 2007-12-31 | Stephens 120 | Erin 120 | 3 | 120 |  | 290 |  | O7 | MI | 4.7 |  | 100 |  |  |  | Planned | 34000000 | [8 empty] | Y | N | Y
A | 1377 | 2006-07-05 | BR | E-MIO | ITC | 686 | 2005-08-10 | ITC7 | 2006-12-31 | Majestic 120 kV | Madrid 120 kV | 2 | 120 |  | 445 |  | N7 | MI | 15.9 |  | 100 |  |  |  | Planned | 1800000 | [8 empty] | Y | N | Y
A | 1378 | 2006-07-05 | TX | E-MIO | ITC | 686 | 2005-08-10 | ITC7 | 2006-12-31 | Majestic 345/120 kV | transformer | 1 | 345 | 120 | 681 |  | N7 | MI | 0 | 0 | 100 |  |  |  | Planned | 5000000 | [8 empty] | Y | N | Y
A | 1381 | 2006-07-05 | BR | E-MIO | ITC | 686 | 2005-08-10 | ITC7 | 2007-12-31 | Majestic 120 kV | Lark 120 kV | 1 | 120 |  | 313 |  | N7 | MI | 2.6 | 9.2 | 100 |  |  |  | Planned | 2700000 | [8 empty] | Y | N | Y
A | 1382 | 2006-07-05 | BR | E-MIO | ITC | 686 | 2005-08-10 | ITC7 | 2007-12-31 | Majestic 120 kV | Phoenix 120 kV | 1 | 120 |  | 313 |  | N7 | MI | 7.4 | 9.2 | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | N | Y
A | 1383 | 2005-08-10 | BR | E-MIO | ITC | 692 | 2005-08-10 | ITC8 | 2008-05-31 | Bismarck 345 kV | Troy 345 kV | 1 | 345 |  | 700 |  | N7 | MI |  | 15.4 | 100 |  |  |  | Planned | 45000000 | [8 empty] | Y | N | Y
A | 1384 | 2005-08-10 | TX | E-MIO | ITC | 692 | 2005-08-10 | ITC8 | 2008-05-31 | Troy 345/120 kV | transformer | 1 | 345 | 120 | 700 |  | N7 | MI |  |  | 100 |  |  |  | Planned | 5000000 | [8 empty] | Y | N | Y
A | 929 | 2006-07-05 | BR | E-MIO | ITC | 905 | 2005-08-10 | ITC15 | 2006-12-31 | Bunce Creek 120 kV | Wabash 120 kV 2 | 2 | 120 |  | 299 |  | N9 | MI | 0.1 | 0 | 50 |  |  | 50 | Planned | 1166666 | [8 empty] | Y | N | Y
A | 931 | 2006-07-05 | BR | E-MIO | ITC | 905 | 2005-08-10 | ITC15 | 2006-12-31 | Bunce Creek 120 kV | Cypress 120 kV | 1 | 120 |  | 313 |  | N9 | MI | 0.1 | 0 | 50 |  |  | 50 | Planned | 1166668 | [8 empty] | Y | N | Y
A | 930 | 2006-07-05 | BR | E-MIO | ITC | 905 | 2005-08-10 | ITC15 | 2006-12-31 | Bunce Creek 120 kV | Menlo 120 kV | 1 | 120 |  | 152 |  | N9 | MI | 0.1 | 0 | 50 |  |  | 50 | Planned | 1166666 | [8 empty] | Y | N | Y
A | 911 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 345 kV | Pontiac 345 | 1 | 345 |  | 2002 |  | N7 | MI | 6.3 |  | 100 |  |  |  | Planned | 6000000 | [8 empty] | Y | N | Y
A | 912 | 2006-07-05 | TX | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 345/120 kV | transformer | 1 | 345 | 120 | 700 |  | N7 | MI |  |  | 100 |  |  |  | Planned | 5000000 | [8 empty] | Y | N | Y
A | 916 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Spokane 120 kV | Tienken 120 kV | 1 | 120 |  | 343 |  | N7 | MI | 0.1 |  | 100 |  |  |  | Planned | 5500000 | [8 empty] | Y | N | Y
A | 910 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 345 kV | Belle River 345 | 1 | 345 |  | 2151 |  | N7 | MI | 35.2 |  | 100 |  |  |  | Planned | 6000000 | [8 empty] | Y | N | Y
A | 915 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 120 kV | Tienken 120 kV | 1 | 120 |  | 343 |  | N7 | MI | 2.78 | 2.34 | 100 |  |  |  | Planned | 5500000 | [8 empty] | Y | N | Y
A | 914 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 120 kV | Sunbird 120 kV | 1 | 120 |  | 229 |  | N7 | MI | 3.55 | 2.87 | 100 |  |  |  | Planned | 11000000 | [8 empty] | Y | N | Y
A | 913 | 2006-07-05 | BR | E-MIO | ITC | 907 | 2005-08-10 | ITC17 | 2008-05-31 | Goodison 120 kV | Pontiac 120 kV | 1 | 120 |  | 343 |  | N7 | MI |  | 6.3 | 100 |  |  |  | Planned | 11000000 | [8 empty] | Y | N | Y
A | 953 | 2006-07-05 | TX | E-MIO | ITC | 911 | 2005-08-10 | ITC21 | 2007-05-30 | Placid 345 kV | transformer | 2 | 345 | 120 | 700 |  | M9 | MI |  |  | 100 |  |  |  | Planned | 10000000 | [8 empty] | Y | N | Y
A | 2131 | 2006-08-16 | BR | E-MIO | ITC | 1300 | 2006-08-16 | ITC22 | 2007-05-30 | Walton 120 kV | Joslyn 120 kV | 1 | 120 |  | 445 | line termination | N6 | MI | 1.75 | [5 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2130 | 2006-08-16 | BR | E-MIO | ITC | 1300 | 2006-08-16 | ITC22 | 2007-05-30 | Pontiac 120 kV | Joslyn 120 kV | 1 | 120 |  | 445 | line termination | N6 | MI | 2.28 | [5 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2132 | 2006-08-16 | CB | E-MIO | ITC | 1301 | 2006-08-16 | ITC23 | 2007-12-31 | Yost 120 kV | Polaris 120 kV | 1 | 120 |  | 349 | line breaker | N7 | MI | 0.9 | [5 empty] | Planned | 300000 | [8 empty] | Y | N | Y
A | 2136 | 2006-08-16 | CB | E-MIO | ITC | 1304 | 2006-08-16 | ITC26 | 2007-12-31 | Monroe 345 kV | Monroe 120 kV | 1 | 345 | 120 | 321 | Adds a new breaker on the 120 kV side of Monroe Xfmr 303 | N7 | MI | [6 empty] | Planned | 300000 | [8 empty] | Y | N | Y
A | 2137 | 2006-08-16 | SUB | E-MIO | ITC | 1305 | 2006-08-16 | ITC27 | 2007-05-31 | Caniff 120 and 345 kV | substation equipment |  | 345 | 120 |  | replace breakers and switchgear | N7 | MI | [6 empty] | Planned | 14400000 | [8 empty] | Y | N | Y
A | 2138 | 2006-08-16 |  | E-MIO | ITC | 1306 | 2006-08-16 | ITC28 | 2007-12-31 | Midtown 120 kV |  |  | 120 |  |  |  | N7 | MI | [6 empty] | Planned | 6000000 | [8 empty] | Y | N | Y
A | 2139 | 2006-08-16 |  | E-MIO | ITC | 1307 | 2006-08-16 | ITC29 | 2007-05-01 | Catalina 120 kV |  |  | 120 |  |  |  | N7 | MI | [6 empty] | Planned | 1000000 | [8 empty] | Y | N | Y
A | 2146 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. LM | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2150 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. FT | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2149 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. FM | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2147 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. LT | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2145 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. LF | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2142 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. CF | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2143 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. CM | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2151 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. BF | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2153 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. BT | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2144 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. CT | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2152 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. BM | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y
A | 2148 | 2006-08-16 | CB | E-MIO | ITC | 1309 | 2006-08-16 | ITC31 | 2007-12-31 | Monroe 345 kV pos. FF | circuit breaker |  | 345 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 250000 | [8 empty] | Y | N | Y |  |  |  | 3000000
A | 2156 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Warren 230 kV pos. CF | circuit breaker |  | 230 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 200000 | [8 empty] | Y | N | Y
A | 2155 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Waterman 230 kV pos. CF | circuit breaker |  | 230 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 200000 | [8 empty] | Y | N | Y
A | 2163 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Polaris 120 kV pos. HG | circuit breaker |  | 120 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2157 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | St. Clair 120 kV pos. JD | circuit breaker |  | 120 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 200000 | [8 empty] | Y | N | Y
A | 2158 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | St. Clair 120 kV pos. KB | circuit breaker |  | 120 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2159 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | St. Clair 120 kV pos. HS | circuit breaker |  | 120 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2160 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Trenton Ch. 120 kV Pos. KG | circuit breaker |  | 120 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2161 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Trenton Ch. 120 kV Pos. KP | circuit breaker |  | 120 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2162 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Wabash 120 kV pos. HL | circuit breaker |  | 120 |  |  | CB replacement | N6 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2165 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Brock 120 kV pos. HP | circuit breaker |  | 120 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2164 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Atlanta 120 kV pos. HD | circuit breaker |  | 120 |  |  | CB replacement | N7 | MI | [6 empty] | Planned | 150000 | [8 empty] | Y | N | Y
A | 2154 | 2006-08-16 | CB | E-MIO | ITC | 1310 | 2006-08-16 | ITC31 | 2007-12-31 | Waterman 230 kV pos. BF | circuit breaker |  | 230 |  |  | CB replacement | O7 | MI | [6 empty] | Planned | 200000 | [8 empty] | Y | N | Y |  |  |  | 2000000
A | 193 | 2005-07-13 | BR | N-Nebraska | LES | 246 | 2005-06-15 | TRN.410.02 | 2008-12-31 | NW68th & Holdrege | NW 12th & Arbor | 1 | 115 |  | 373 | New Line | F9 | NE |  | 10 | 100 |  |  |  | Planned | 1712000 | Planning |  | Y | [5 empty] | Y | Y | Y
A | 806 | 2005-07-08 | BR | N-Nebraska | LES | 804 | 2006-09-29 | TRN.440.07 | 2008-12-31 | 19th & Alvo | 70th & Bluff | 1 | 115 |  | 363 | Rebuilt Line | F9 | NE | 1.5 |  |  |  |  | 100 | Planned | 300000 | Planning |  | Y | [5 empty] | Y | Y | Y
A | 1576 | 2005-08-02 | BR | N-NM | MDU | 548 | 2005-08-02 |  | 2007-11-01 | Bismarck Downtown | East Bismarck |  | 115 |  | 160 | Rebuild | D4 | ND |  |  | 100 |  |  |  | Planned | 363000 | Planning MISO | [7 empty] | Y | Y | Y
A | 1577 | 2005-08-02 | BR | N-NM | MDU | 1008 | 2005-08-02 |  | 2009-11-01 | Heskett | NW Bismarck |  | 115 |  | 180 | Memorial Bridge circuit replacement | D4 | ND |  |  | 100 |  |  |  | Planned | 3692000 | Planning MISO | [7 empty] | Y | Y | Y
A | 1578 | 2005-08-02 | BR | N-NM | MDU | 1008 | 2005-08-02 |  | 2009-11-01 | S Mandan | Bismarck Downtown |  | 115 |  | 180 | Memorial Bridge circuit replacement | D4 | ND |  |  | 100 |  |  |  | Planned | 2868000 | Planning MISO | [7 empty] | Y | Y | Y
A | 1332 | 2006-09-29 | TX | E-MIO | METC | 481 | 2006-09-29 | 74 | 2007-05-01 | Tallmadge 3rd 345/138 kV | transformer | 3 | 345 | 138 |  |  | M7 | MI | 0 |  | 100 |  |  |  | Planned | 13500000 | [8 empty] | Y | N | Y
A | 1534 | 2006-10-26 | IND | E-MIO | METC | 493 | 2005-07-27 | 123 | 2007-05-01 | Tallmadge Remove Reactors | Tallmadge Remove Reactors | 1&2 | 345 |  |  |  |  | MI | [6 empty] | Planned | 20000 | Planning MISO | [7 empty] | Y | N | Y
A | 1322 | 2006-10-26 | LN | E-MIO | METC | 497 | 2006-09-29 | 23 | 2007-06-01 | Tallmadge | Wealthy | 2 | 138 |  |  |  | M7 | MI | 0 |  | 100 |  |  |  | Planned | 40000 | [8 empty] | Y | N | Y
A | 1327 | 2006-09-29 | BR | E-MIO | METC | 644 | 2005-07-27 | 64 | 2007-06-15 | Rogue River J. - METC | Rogue River | 1 | 138 |  |  |  | M7 | MI |  | 0.1 | 100 |  |  |  | Planned | 160000 | [8 empty] | Y | N | Y
A | 1328 | 2006-09-29 | BR | E-MIO | METC | 645 | 2006-09-29 | 56 | 2007-06-01 | American Bumper | David | 1 | 138 |  |  |  | M7 | MI | 8 |  | 100 |  |  |  | Planned | 2500000 | [8 empty] | Y | N | Y
A | 1345 | 2006-10-26 | LN | E-MIO | METC | 658 | 2006-09-29 | 82 | 2008-05-01 | Gaylord | Livingston | 1 | 138 |  |  |  | M5 | MI | 1.5 |  | 100 |  |  |  | Planned | 500000 | [8 empty] | Y | N | Y
A | 1347 | 2006-10-26 | BR | E-MIO | METC | 660 | 2005-07-27 | 101 | 2009-05-01 | Keystone | Clearwater | 1 | 138 |  |  |  | M5 | MI | 23.2 |  | 100 |  |  |  | Planned | 10200000 | [8 empty] | Y | N | Y
A | 3082 | 2006-09-29 | CAP | East | METC | 774 | 2006-09-29 | 61 | 2006-12-01 | Gaylord | Capacitors | 1 | 138 |  | 36 Mvar |  | M6 | MI | 0 |  | 100 |  |  |  | Under Construction | 900000 | [8 empty] | Y | N | Y | METC_2011Sum_U2_8-12-2005_29.idv
A | 3083 | 2006-09-29 | CAP | East | METC | 775 | 2006-09-29 | 62 | 2006-12-01 | Iosco | Capacitors | 1 | 138 |  | 18 Mvar |  | N6 | MI | 0 |  | 100 |  |  |  | Under Construction | 800000 | [8 empty] | Y | N | Y | METC_2011Sum_U2_8-12-2005_29.idv
A | 1539 | 2006-07-05 | BR | East | METC | 976 | 2005-07-27 | 48 | 2007-06-01 | Alpine | Add one line switch |  | 138 |  |  | Add One switch |  | MI | [6 empty] | Planned | 80000 | [8 empty] | Y | N | Y
A | 1540 | 2006-10-26 | RLY | East | METC | 977 | 2005-07-27 | 49 | 2006-05-01 | Marquette Station | Replace breaker failure scheme |  | 138 |  |  | Replace breaker failure scheme |  | MI | [6 empty] | Under Construction | 200000 | [8 empty] | Y | N | Y
A | 1544 | 2006-07-05 | BR | East | METC | 981 | 2005-07-27 | 63 | 2009-06-01 | Wabasis J. - N. Belding - Vergennes | Wabasis | 1 | 138 |  |  | Install aTap Pole and Switches |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 1545 | 2006-07-05 | BR | East | METC | 982 | 2005-07-27 | 65 | 2007-06-01 | Crahen J. -Spaudling - Race Street | Crahen | 1 | 138 |  |  | Install a Tap Pole and one switch |  | MI | [6 empty] | Planned | 80000 | [8 empty] | Y | N | Y
A | 1587 | 2006-10-26 | CAP | East | METC | 1015 | 2005-08-12 | 131 | 2008-06-01 | Oden | Oden - New Capacitor | 1 | 138 |  | 21.6 Mvar | Oden - New 21.6 Mvar Capacitor |  | MI |  |  | 100 |  |  |  | Planned | 510000 | Planning MISO | [7 empty] | Y | N | Y
A | 1588 | 2006-10-26 | CAP | E-MIO | METC | 1016 | 2005-08-12 | 132 | 2007-06-01 | Bard Road | Bard Road - New Capacitor | 1 | 138 |  | 36 Mvar | Bard Road - New 36 Mvar Capacitor |  | MI |  |  | 100 |  |  |  | Planned | 596000 | Planning MISO | [7 empty] | Y | N | Y
A | 1589 | 2006-10-26 | CAP | E-MIO | METC | 1017 | 2005-08-12 | 133 | 2007-06-01 | Croton | Croton - New Capacitor | 1 | 138 |  | 36 Mvar | Croton - New 36 Mvar Capacitor |  | MI |  |  | 100 |  |  |  | Planned | 596000 | Planning MISO | [7 empty] | Y | N | Y
A | 2393 | 2006-10-25 | CB | East | METC | 1390 | 2006-10-25 | 140 | 2007-12-01 | Goss 345kV | 345kV GIS bus and breakers |  | 345 |  |  | Replace old, leaking 345kV GIS bus & breakers with open-air type. Patchwork repairs haven't been successful. |  | MI | [6 empty] | Planned | 5800000 | [8 empty] | Y | N | Y
A | 2394 | 2006-10-25 | CB | East | METC | 1391 | 2006-10-25 | 141 | 2007-12-31 | Campbell 138kV | Breaker 148 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2395 | 2006-10-25 | CB | East | METC | 1392 | 2006-10-25 | 142 | 2007-12-31 | Campbell 138kV | Breaker 188 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2396 | 2006-10-25 | CB | East | METC | 1393 | 2006-10-25 | 143 | 2007-12-31 | Campbell 138kV | Breaker 288 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2397 | 2006-10-25 | CB | East | METC | 1394 | 2006-10-25 | 144 | 2007-12-31 | Campbell 138kV | Breaker 388 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2398 | 2006-10-25 | CB | East | METC | 1395 | 2006-10-25 | 145 | 2007-12-31 | Campbell 138kV | Breaker 500 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2399 | 2006-10-25 | CB | East | METC | 1396 | 2006-10-25 | 146 | 2007-12-31 | Campbell 138kV | Breaker 588 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2400 | 2006-10-25 | CB | East | METC | 1397 | 2006-10-25 | 147 | 2007-12-31 | Spaulding 138kV | Breaker 36M9 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2401 | 2006-10-25 | CB | East | METC | 1398 | 2006-10-25 | 148 | 2007-12-31 | Spaulding 138kV | Breaker 36B7 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2402 | 2006-10-25 | CB | East | METC | 1399 | 2006-10-25 | 149 | 2007-12-31 | Morrow 138kV | Breaker 377 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2403 | 2006-10-25 | CB | East | METC | 1400 | 2006-10-25 | 150 | 2007-12-31 | Claremont 138kV | Breaker 288 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2404 | 2006-10-25 | CB | East | METC | 1401 | 2006-10-25 | 151 | 2007-12-31 | Claremont 138kV | Breaker 388 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2405 | 2006-10-25 | CB | East | METC | 1402 | 2006-10-25 | 152 | 2007-12-31 | Goss 138kV | Breaker 13B7 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2406 | 2006-10-25 | CB | East | METC | 1403 | 2006-10-25 | 153 | 2007-12-31 | Goss 138kV | Breaker 13M9 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2407 | 2006-10-25 | CB | East | METC | 1404 | 2006-10-25 | 154 | 2007-12-31 | Argenta 138kV | Breaker 6W8 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2408 | 2006-10-25 | CB | East | METC | 1405 | 2006-10-25 | 155 | 2007-12-31 | Hemphill 138kV | Breaker 499 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y |  |  |  | 2400000
A | 2409 | 2006-10-25 | CB | East | METC | 1406 | 2006-10-25 | 156 | 2008-12-31 | Alpena 138kV | Breaker 188 |  | 138 |  |  | Replace overdutied breaker with higher capacity breaker. |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2410 | 2006-10-25 | IND | East | METC | 1407 | 2006-10-25 | 157 | 2007-12-01 | Ludington 345kV | Reactor |  | 345 |  |  | Repair or replace existing 100MVAR reactor and replace circuit switcher with a breaker |  | MI | [6 empty] | Planned | 1500000 | [8 empty] | Y | N | Y
A | 2411 | 2006-10-25 | RTU | East | METC | 1408 | 2006-10-25 | 158 | 2007-05-01 | RTU/SCADA upgrades | Throughtout System |  | 345 | 138 |  | Install and/or upgrade numerous RTU/SCADA points |  | MI | [6 empty] | Planned | 801000 | [8 empty] | Y | N | Y
A | 2413 | 2006-10-25 | CAP | East | METC | 1410 | 2006-10-25 | 160 | 2008-12-01 | Mobile 138kV Capacitor |  |  | 138 |  | 14.4 - 36MVAR | Purchase a mobile 138kV capacitor for use where needed during outages, heavy transfers, etc. |  | MI | [6 empty] | Planned | 700000 | [8 empty] | Y | N | Y
A | 2414 | 2006-10-25 | SPS | East | METC | 1411 | 2006-10-25 | 161 | 2007-03-01 | Campbell 345kV | Relay Runback SPS on Unit 3 |  | 345 |  |  | Install auto relay runback SPS for Campell Unit 3 per MISO G479 Study |  | MI | [6 empty] | Planned | 75000 | [7 empty] | MISO G479 | Y | N | Y
A | 2415 | 2006-10-26 | TEQ | East | METC | 1412 | 2006-10-25 | 162 | 2007-06-01 | Palisades 345kV | Argenta 345kV | 1or2 | 345 |  |  | Modify phase connections at the Palisades and Argenta ends of the 345kV line for Covert project |  | MI | [6 empty] | Planned | 170000 | [8 empty] | Y | N | Y
A | 2416 | 2006-10-25 | TEQ | East | METC | 1412 | 2006-10-25 | 162 | 2007-06-01 | Palisades 345kV | Cook 345kV | 2 | 345 |  |  | Modify phase connections at the Palisades and Cook ends of the 345kV line for Covert project |  | MI | [6 empty] | Planned | 735000 | [8 empty] | Y | N | Y
A | 2417 | 2006-10-25 | LN | East | METC | 1413 | 2006-10-25 | 163 | 2009-05-01 | Bagley 138kV | Gaylord 138kV | 1 | 138 |  |  | Rebuild line to 795 ACSS |  | MI | [6 empty] | Planned | 350000 | [8 empty] | Y | N | Y
A | 2418 | 2006-10-25 | TEQ | East | METC | 1414 | 2006-10-25 | 164 | 2007-12-31 | Thetford 345kV | Line Relaying |  | 345 |  |  | Upgrade 345kV line relaying. |  | MI | [6 empty] | Planned | 300000 | [8 empty] | Y | N | Y
A | 2419 | 2006-10-25 | TAP | East | METC | 1415 | 2006-10-25 | 165 | 2007-10-01 | HSC 138kV | Tittabawasee 138kV & Lawndale 138kV | 1 | 138 |  |  | Install a tap pole and one switch on each of the Tittabawassee-HSC and Lawndale-HSC 138kV lines. (Solar Project) |  | MI | [6 empty] | Planned | 160000 | [8 empty] | Y | N | Y
A | 2420 | 2006-10-25 | LN | East | METC | 1416 | 2006-10-25 | 166 | 2007-10-01 | HSC 138kV | Tittabawasee 138kV & Lawndale 138kV | 1 | 138 |  |  | Install a new 2-mile 138kV double circuit to swap the existing 138kV Tittabawasee and Lawndale line connections into HSC. (HSC Project) |  | MI | [6 empty] | Planned | 1300000 | [8 empty] | Y | N | Y
A | 2421 | 2006-10-25 | LN | East | METC | 1416 | 2006-10-25 | 166 | 2007-10-01 | HSC 138kV | Tittabawasee 138kV | 2 | 138 |  |  | Install new,second 138kV Tittabawasee-HSC line and 5 total 138kV breakers for connecting the line at each end. (HSC Project) |  | MI | [6 empty] | Planned | 4500000 | [8 empty] | Y | N | Y
A | 2422 | 2006-10-25 | CB | East | METC | 1417 | 2006-10-25 | 167 | 2007-06-01 | Race Street 138kV | 138kV Tie Breaker |  | 138 |  |  | Install a 138kV tie-breaker to loop the Spaulding-Four Mile 138kV Line (Race St) |  | MI | [6 empty] | Planned | 2200000 | [8 empty] | Y | N | Y
A | 562 | 2006-06-28 | BR | N-NM | MH | 264 | 2006-03-24 | 264 | 2007-03-31 | Birchtree | Wuskwatim | 1 | 230 |  | 390 | New generation transmission | Manitoba | Manitoba |  | 28 |  | 100 |  |  | Planned | 13495431.77 | Engineering | [7 empty] | Y | Y | Y
A | 1090 | 2006-06-28 | BR | N-NM | MH | 264 | 2006-03-24 | 264 | 2010-11-30 | Herblet Lake | Wuskwatim | 1 | 230 |  | 390 | New generation transmission | Manitoba | Manitoba |  | 86 |  | 100 |  |  | Planned | 31106922.56 | Engineering | [7 empty] | Y | Y | Y
A | 1091 | 2006-06-28 | BR | N-NM | MH | 264 | 2006-03-24 | 264 | 2010-11-30 | Herblet Lake | Wuskwatim | 2 | 230 |  | 390 | New generation transmission | Manitoba | Manitoba |  | 86 |  | 100 |  |  | Planned | 31106922.56 | Engineering | [7 empty] | Y | Y | Y
A | 2089 | 2006-06-28 | DV | N-NM | MH | 264 | 2006-03-24 | 264 | 2011-08-31 | Thompson Birchtree | SVC |  | 230 |  | 150/-20 | New generation transmission |  | Manitoba |  |  |  | 100 |  |  | Planned | 16538691.05 | Engineering | [7 empty] | Y | Y | Y
A | 1092 | 2006-06-28 | BR | N-NM | MH | 264 | 2006-03-24 | 264 | 2011-10-31 | Herblet Lake | Ralls Island | 1 | 230 |  | 390 | New generation transmission | Manitoba | Manitoba |  | 103 | 50 | 50 |  |  | Planned | 36924629.44 | Engineering | [7 empty] | Y | Y | Y
A | 2078 | 2006-03-24 | CAP | N-NM | MH | 442 | 2006-03-24 | 442 | 2010-10-31 | Brandon | Capacitor |  | 115 |  | 54 |  | F2 | Manitoba |  |  | 40 | 20 | 40 |  | Planned | 472909.3548 | Engineering | [7 empty] | Y | Y | Y
A | 319 | 2003-06-03 | TX | N-NM | MP | 1 | 2005-07-11 | 1 | 2008-06-30 | Arrowhead 345/230 kV | transformer | 1 | 345 | 230 | 800 |  | I4 | MN |  |  | 50 |  | 25 | 25 | Planned | 10400000 | [8 empty] | Y | Y | Y
A | 318 | 2003-06-03 | BR | N-NM | MP | 1 | 2005-07-11 | 1 | 2008-06-30 | Arrowhead 230-230 kV | Phase-Shifter | 1 | 230 | 230 | 800 |  | I4 | MN |  |  | 50 |  | 25 | 25 | Planned | 13741772.8 | [8 empty] | Y | Y | Y
A | 2039 | 2003-06-03 | CAP | N-NM | MP | 1 | 2005-07-11 | 1 | 2008-06-30 | Arrowhead | Capacitor |  | 230 |  | 4 x 40 Mvar |  | I4 | MN |  |  | 100 |  |  |  | Planned | 1858227.2 | [8 empty] | Y | Y | Y
A | 2258 | 2006-10-15 | CAP | N-NM | MP | 1358 | 2006-10-15 | b11 | 2006-12-30 | Grand Rapids | Capacitor |  | 115 |  | 1x27 Mvar | add new | b11 | MN |  |  | 100 |  |  |  | Planned | 320000 | Planning | [7 empty] | Y | Y | Y
A | 1098 | 2005-07-29 | BR | N-NM | MPC/XEL/OTP/MP | 279 | 2005-07-29 | CAPX Group 1 | 2010-07-01 | Boswell | Wilton | 1 | 230 |  | 390 | Add a new 230 kV line between Boswell and Wilton | H4 | MN |  | 85 | 100 |  |  |  | Proposed | 35963293 | Planning | [7 empty] | Y | Y | Y
A | 3034 | 2006-10-03 | CAP | E-MIO | NIPS | 757 | 2006-10-03 | 9320027 | 2007-02-01 | Dune Acres | Capacitor |  | 138 |  |  | Add Capacitor - (1) 100 MVAR step | L8 | IN |  |  | 100 |  |  |  | Planned | 1083600 | Engineering w AFUDC | [7 empty] | Y | N | Y
A | 970 | 2006-10-03 | BR | E-MIO | NIPS | 925 | 2006-10-03 | 71C6613 | 2006-12-01 | ISG2 | Marktown | 1 | 138 |  | 316 | Upgrade Connections and Circuit |  | IN | 0.6 |  |  |  |  | 100 | Planned | 240500 | Engineering w AFUDC | [7 empty] | Y | N | Y
A | 2128 | 2006-10-03 | BR | East | NIPS | 1298 | 2006-10-03 | 71C6805 | 2008-05-01 | Inland #5 | Marktown | 1 | 138 |  | 316/380 | Upgrade Connections and Circuit |  |  | 2.2 | [5 empty] | Planned | 750000 | [8 empty] | Y | N | Y
A | 377 | 2006-10-15 | BR | N-NM | OTP | 274 | 2005-07-29 |  | 2008-08-01 | Appleton | Louisburg | 1 | 115 |  | 96 | Convert an existing 41.6 kV line to 115 kV | G5 | MN | 6.9 |  | 100 |  |  |  | Planned | 474000 | Planning | [7 empty] | Y | Y | Y
A | 378 | 2006-10-15 | BR | N-NM | OTP | 275 | 2005-07-29 |  | 2008-08-01 | Dawson | Canby | 1 | 115 |  | 96 | Convert an existing 41.6 kV line to 115 kV | G8 | MN | 21.1 |  | 100 |  |  |  | Planned | 538000 | Planning | [7 empty] | Y | Y | Y
A | 1523 | 2006-10-15 | TX | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2009-04-01 | Canby 230/115 kV | transformer |  | 230 | 115 | 336 | Install a 230/115 kV Transformer for Big Stone II Generation Outlet (Alternative 1 and 2) | F6 | MN |  |  |  | 100 |  |  | Planned | 6100000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 1516 | 2006-10-15 | BR | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2010-06-01 | Ortonville 230 | Johnson Jct. 230 | 1 | 230 |  | 520 | Convert existing 115 kV line to 230 kV with 1272 ACSR for Big Stone II Generation Outlet (Alternative 1) | F6 | MN | 24.6 |  |  | 100 |  |  | Planned | 15100000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 1524 | 2005-11-01 | BR | N-NM | OTP | 973 | 2005-11-01 |  | 2010-07-01 | Big Stone 230 | Browns Valley 230 kV |  | 230 |  | 390 | Upgrade substation equipment at Browns Valley to achieve rating equal to thermal rating of line (Required Int. upgrade for Alts 1 and 2) | F6 | SD | 38.7 |  |  | 100 |  |  | Planned | 2000000 | Planning | [6 empty] | G392 | Y | Y |  | Interconnection
A | 1518 | 2005-11-01 | TX | N-NM | OTP | 973 | 2005-11-01 |  | 2010-07-01 | Johnson Jct. 230/115 kV | transformer | 1 | 230 | 115 | 112 | Install a 230/115 kV Transformer for Big Stone II Generation Outlet (Alternative 1) | F6 | MN |  |  |  | 100 |  |  | Planned | 3000000 | Planning | [6 empty] | G392 | Y | Y |  | Network
A | 1525 | 2006-10-15 | TX | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2011-06-01 | Morris 230/115 kV | transformer |  | 230 | 115 | 336 | Replace existing transformer at Morris with 336 MVA unit (Required Int. upgrade for Alternative 1) | F6 | MN |  |  |  | 100 |  |  | Planned | 6100000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Interconnection
A | 1521 | 2006-10-15 | BR | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2011-06-01 | Big Stone 230 | Canby 230 | 1 | 230 |  | 1145 | Build new 230 kV line with 2-1272 ACSR for Big Stone II Generation Outlet (Alternative 1 and 2) | F6 | MN/SD |  | 55 |  | 100 |  |  | Planned | 41250000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 1515 | 2006-10-15 | BR | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2011-06-01 | Big Stone 230 | Ortonville 230 | 1 | 230 |  | 520 | Build new 230 kV line with 1272 ACSR for Big Stone II Generation Outlet (Alternative 1) | F6 | MN/SD |  | 6.5 |  | 100 |  |  | Planned | 2400000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 1517 | 2006-10-15 | BR | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2011-06-01 | Johnson Jct. 230 | Morris 230 | 1 | 230 |  | 520 | Convert existing 115 kV line to 230 kV with 1272 ACSR for Big Stone II Generation Outlet (Alternative 1) | F6 | MN | 15.4 |  |  | 100 |  |  | Planned | 9400000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 1522 | 2006-10-15 | BR | N-NM | OTP | 973 | 2005-11-01 | Big Stone 2 | 2011-06-01 | Canby 230 | Granite Falls 230 | 1 | 230 |  | 1145 | Build new 230 kV line with 2-1272 ACSR for Big Stone II Generation Outlet (Alternative 1 and 2) | F6 | MN | 39.2 |  |  | 100 |  |  | Planned | 29400000 | Planning | [6 empty] | G392 | Y | Y | Y |  | Network
A | 2266 | 2006-10-15 | BR | N-NM | OTP | 1362 | 2006-10-15 |  | 2008-08-01 | Louisurg | Dawson | 1 | 115 |  | 96 | Convert an existing 41.6 kV line to 115 kV | G6 | MN | 14.4 |  | 100 |  |  |  | Planned | 988000 | Planning | [7 empty] | Y | Y | Y
A | 3032 | 2006-03-27 | CAP | N-NM | OTP/MRES/GRE | 755 | 2005-07-29 |  | 2007-06-01 | Alexandria Switching Station | Capacitors |  | 115 |  | 25 Mvar | Add a 1 x 25 MVAr capacitor bank at the Alexandria Switching Station | G5 | MN |  |  | 100 |  |  |  | Planned | 530000 | Planning | [7 empty] | Y | Y | Y
A | 60 | 2005-11-28 | BR | C-CSILL | SIPC | 81 | 2005-06-15 | 57 | 2007-06-01 | Marion | CarrierMills | 1 | 161 |  | 286 |  | K11 | IL |  | 27 | 100 |  |  |  | Planned | 7083000 | [8 empty] | Y | N
A | 1567 | 2006-10-31 | BR | E-IOK | Vectren | 1002 | 2006-06-29 | 6.2 | 2008-05-31 | Oak Grove | Culley | 77 | 138 |  | 287/287 | new line | L11 | IN |  | 10 | 100 |  |  |  | Planned | 5700000 | Budgetary | [7 empty] | Y | N | Y
A | 1566 | 2006-10-31 | BR | E-IOK | Vectren | 1002 | 2006-06-29 | 6.3 | 2008-12-31 | Northeast | Oak Grove | 77 | 138 |  | 287/287 | new line | L11 | IN |  | 5 | 100 |  |  |  | Planned | 2800000 | Budgetary | [7 empty] | Y | N | Y
A | 1569 | 2006-10-31 | BR | E-IOK | Vectren | 1004 | 2006-06-29 | 2.1 2.2 2.5 2.6 | 2007-05-31 | Francisco 345/138 kV | Substation | 1 | 345 | 138 | 896/940 | new substation with two 345/138 transformers and 345 kV interconnection with Cinergy on Gibson-Duff line | L11 | IN |  |  | 25 |  | 25 | 50 | Planned | 19630000 | Budgetary | [7 empty] | Y | N | Y
A | 1570 | 2006-10-31 | BR | E-IOK | Vectren | 1005 | 2006-06-29 | 2.4 3.2 3.4 3.6 | 2009-05-31 | Francisco | Northeast | 76 | 138 |  | 287/287 | new line | L11 | IN |  | 31 | 25 |  | 25 | 50 | Planned | 9500000 | Budgetary | [7 empty] | Y | N | Y
A | 1571 | 2006-10-31 | BR | E-IOK | Vectren | 1005 | 2006-06-29 | 2.3 3..3 3.5 3.6 | 2009-05-31 | Francisco | Northwest | 75 | 138 |  | 287/287 | new line | L11 | IN |  | 31 | 25 |  | 25 | 50 | Planned | 9500000 | Budgetary | [7 empty] | Y | N | Y
A | 1971 | 2006-10-31 | BR | E-IOK | Vectren | 1257 | 2006-06-29 | 8.3 | 2011-05-31 | AB Brown 345/138 kV | transformer | 1 | 345 | 138 | 448/470 | New 345 bus & transformer | L11 | IN |  |  |  |  | 50 | 50 | Planned | 8400000 | Budgetary | [7 empty] | Y | N | Y
A | 1973 | 2006-10-31 | BR | E-IOK | Vectren | 1257 | 2006-06-29 | 8.4 8.5 | 2011-05-31 | AB Brown | Reid (BREC) | 17 | 345 |  | 1430/1430 | new line | L11 | IN/KY |  | 24 |  |  | 50 | 50 | Planned | 26050000 | Budgetary | [7 empty] | Y | N | Y
A | 1972 | 2006-10-31 | BR | E-IOK | Vectren | 1257 | 2006-06-29 | 8.1 8.2 | 2011-05-31 | AB Brown | Gibson (Duke) | 15 | 345 |  | 1430/1430 | new line | L11 | IN |  | 40 |  |  | 50 | 50 | Planned | 40125000 | Budgetary | [7 empty] | Y | N | Y
A | 1975 | 2006-10-31 | BR | E-IOK | Vectren | 1259 | 2006-06-29 | 1.1 1.2 1.3 | 2007-05-31 | Dubois | Newtonville | 78 | 138 |  | 287/287 | new line | M11 | IN |  | 28 | 100 |  |  |  | Planned | 14400000 | Budgetary | [7 empty] | Y | N | Y
A | 1900 | 2006-02-10 | CB | E-MIO | WPSC | 1205 | 2006-02-10 | 2006-01 | 2006-08-01 | Cheboygan II | Breaker |  | 69 |  |  | Add Breaker at Cheboygan II |  | MI |  |  | 100 |  |  |  | Planned | 550000 | Planning | [7 empty] | Y | N | Y
A | 1901 | 2006-02-10 | BR | E-MIO | WPSC | 1206 | 2006-02-10 | 2006-02 | 2006-08-01 | Lake County | Bass Lake |  | 69 |  | 102.4 MVA | Rebuild Overloaded Line |  | MI | 8.35 |  | 100 |  |  |  | Planned | 1800000 | Planning | [7 empty] | Y | N | Y
A | 1902 | 2006-02-10 | BR | E-MIO | WPSC | 1207 | 2006-02-10 | 2006-03 | 2006-08-01 | Hersey | Osceola |  | 69 |  | 35.9 MVA | Rerate Overloaded Line |  | MI | 4.02 |  | 100 |  |  |  | Planned | 200000 | Planning | [7 empty] | Y | N | Y
A | 1903 | 2006-02-10 | DV | E-MIO | WPSC | 1208 | 2006-02-10 | 2006-04 | 2006-08-01 | Oden | 12MVAR cap. Bank |  | 69 |  |  | Add 12MVAR at Oden Sub. |  | MI |  |  | 100 |  |  |  | Planned | 300000 | Planning | [7 empty] | Y | N | Y
A | 1926 | 2006-03-15 | BR | East | WPSC | 1226 | 2006-03-15 | TL06-01 | 2008-02-01 | Kalkaska Generation | Westwood | 1 | 69 |  | 102.4 | Rebuild 69 kV Line |  | MI | 11.62 | 0 | 100 | 0 | 0 | 0 | Planned | 2905000 | Planning | [6 empty] | ANR El Paso 06 Summer | Y | N | Y
A | 1927 | 2006-03-15 | BR | East | WPSC | 1227 | 2006-03-15 | TL06-02 | 2008-02-01 | Gaylord Generation | Bagley Junction | 1 | 69 |  | 102.4 | Rebuild 69 kV Line |  | MI | 4 | 0 | 100 | 0 | 0 | 0 | Planned | 1000000 | Planning | [6 empty] | ANR El Paso 06 Summer | Y | N | Y
A | 1928 | 2006-03-16 | Tap | East | WPSC | 1228 | 2006-03-16 | 2008-05 | 2008-08-01 | Westwood | New Load |  | 69 |  |  | Add 14MW Load to Westwood |  | MI |  |  | 100 |  |  |  | Planned | 1800000 | Planning | [7 empty] | Y | N | Y
A | 1929 | 2006-03-16 | Bus | East | WPSC | 1229 | 2006-03-16 | 2006-05 | 2006-11-01 | Plains X | Bus Upgrade |  | 69 |  |  | Upgrade exsisting 69KV bus |  | MI |  |  | 100 |  |  |  | Planned | 625000 | Planning | [7 empty] | Y | N | Y
A | 1930 | 2006-03-16 | Bus | East | WPSC | 1230 | 2006-03-16 | 2006-06 | 2006-09-01 | White Cloud | Bus Upgrade |  | 69 |  |  | Upgrade exsisting 69KV bus |  | MI |  |  | 100 |  |  |  | Planned | 625000 | Planning | [7 empty] | Y | N | Y
A | 1931 | 2006-03-16 | Tap | East | WPSC | 1231 | 2006-03-16 | 2006-07 | 2006-06-01 | Superior | New Load |  | 69 |  |  | Add new load tap off 69KV line |  | MI |  |  | 100 |  |  |  | Planned | 550000 | Planning | [7 empty] | Y | N | Y
A | 1994 | 2006-07-13 | BR | East | WPSC | 1272 | 2006-07-13 | 2010-03 | 2010-08-01 | Redwood 138 | Redwood 69 |  | 138 | 69 | 75MVA | Add 75MV transformer |  | MI | 0 |  | 100 |  |  |  | Planned | 1900000 | Planning | [7 empty] | Y | N | Y
A | 303 | 2006-03-27 | BR | N-NM | XEL | 56 | 2006-03-27 | 41 | 2010-12-31 | Lawrence Creek | St Croix Falls | 1 | 161 |  | 371 | New 161 kV line | Q4 | MN |  | 2.05 | 100 |  |  |  | Planned | 9080000 | [8 empty] | Y | Y | Y
A | 310 | 2006-03-27 | BR | N-NM | XEL | 56 | 2006-03-27 | 41 | 2010-12-31 | Shafer | Lawrence Creek | 1 | 115 |  | 310 | New line | Q4 | MN | 6.2 |  | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | Y | Y
A | 304 | 2006-03-27 | TX | N-NM | XEL | 56 | 2006-03-27 | 41 | 2010-12-31 | Lawrence Creek 161-115 kV | transformer | 1 | 161 | 115 | 336 | New substation with 161-115 kV transformer | Q4 | MN |  |  | 100 |  |  |  | Planned | 6000000 | [8 empty] | Y | Y | Y
A | 301 | 2006-03-27 | BR | N-NM | XEL | 56 | 2006-03-27 | 41 | 2010-12-31 | Chisago | Lindstrom | 1 | 115 |  | 310 | New 115 kV line | Q4 | MN | 7 |  | 100 |  |  |  | Planned | 10100000 | [8 empty] | Y | Y | Y
A | 306 | 2006-03-27 | BR | N-NM | XEL | 56 | 2006-03-27 | 41 | 2010-12-31 | Lindstrom | Shafer | 1 | 115 |  | 310 | New line | Q4 | MN | 2.8 |  | 100 |  |  |  | Planned | 5800000 | [8 empty] | Y | Y | Y
A | 561 | 2006-07-12 | BR | N-NM | XEL | 265 | 2006-07-12 |  | 2006-07-31 | Glencoe | McLeod | 1 | 115 |  | 300 | New line | H6 | MN |  | 9.5 | 100 |  |  |  | Planned | 4282860 | [8 empty] | Y | Y | Y
A | 563 | 2006-07-12 | BR | N-NM | XEL | 267 | 2006-07-12 |  | 2007-05-01 | Lawrence | Minnehaha | 1 | 115 |  | 310 | Upgrade existing line | G7 | SD | 5.2 |  | 100 |  |  |  | Planned | 829667 | [8 empty] | Y | Y | Y
A | 564 | 2006-07-12 | BR | N-NM | XEL | 268 | 2006-07-12 |  | 2007-05-01 | Minnehaha | Lincoln County | 1 | 115 |  | 310 | Upgrade existing line | G7 | SD | 5.8 |  | 100 |  |  |  | Planned | 925398 | [8 empty] | Y | Y | Y
A | 1137 | 2006-07-12 | BR | N-NM | XEL | 269 | 2006-07-12 |  | 2007-06-01 | Prairie Island | Red Rock | 2 | 345 |  | 1198 | Upgrade existing line | Q6 | MN | 32 |  | 100 |  |  |  | Planned | 807000 | [8 empty] | Y | Y | Y
A | 1138 | 2006-07-12 | BR | N-NM | XEL | 270 | 2006-07-12 |  | 2007-06-01 | Champlin | Champlin Tap | 1 | 115 |  | 310 | Upgrade existing line | O4 | MN | 2.4 |  | 100 |  |  |  | Planned | 382923 | [8 empty] | Y | Y | Y
A | 565 | 2006-07-12 | BR | N-NM | XEL | 271 | 2006-07-12 |  | 2008-09-01 | Hungry Hollow | Ballard Corner | 1 | 115 |  |  | Upgrade 69 kV to 115 kV | H6 | MN |  |  | 100 |  |  |  | Planned | 1333975 | [8 empty] | Y | Y | Y
A | 277 | 2005-07-19 | BR | N-NM | XEL | 272 | 2006-03-27 |  | 2007-06-01 | Air Lake | Vermillion River | 1 | 115 |  | 200 | New line | TC detail | MN |  | 4.2 | 100 |  |  |  | Planned | 3359095.21 | [7 empty] | HBR RIV | Y | Y | Y |  | Net?
A | 576 | 2006-10-15 | BR | N-NM | XEL | 276 | 2006-07-12 |  | 2006-12-31 | Inver Hills | Koch | 1 | 115 |  | 620 | Line reconductor |  | MN | [6 empty] | Planned | [9 empty] | Y | Y | Y
A | 571 | 2006-03-27 | BR | N-NM | XEL | 366 | 2006-03-27 | St Cloud | 2007-06-01 | Salida Crossing | Sherco | 1 | 115 |  | 310 | Upgrade existing line | H5 | MN | 2.5 | 1 | 100 |  |  |  | Planned | 765368 | [8 empty] | Y | Y | Y
A | 569 | 2006-03-27 | BR | N-NM | XEL | 366 | 2006-03-27 | St Cloud | 2007-06-01 | I94 Industrial Park tap | Salida Crossing | 1 | 115 |  | 310 | Upgrade existing line | H5 | MN | 14.3 |  | 100 |  |  |  | Planned | 2432170 | [8 empty] | Y | Y | Y
A | 574 | 2006-03-27 | BR | N-NM | XEL | 366 | 2006-03-27 | St Cloud | 2007-06-01 | St Cloud | I94 Industrial Park tap | 1 | 115 |  | 310 | Upgrade existing line | H5 | MN | 5 |  | 100 |  |  |  | Planned | 850409 | [8 empty] | Y | Y | Y
A | 572 | 2006-03-27 | BR | N-NM | XEL | 366 | 2006-03-27 | St Cloud | 2007-06-01 | Sherco | Monticello | 1 | 115 |  | 310 | Upgrade existing line | H5 | MN | 2.2 | 1 | 100 |  |  |  | Planned | 714344 | [8 empty] | Y | Y | Y
A | 573 | 2006-03-27 | TX | N-NM | XEL | 366 | 2006-03-27 | St Cloud | 2007-06-01 | Sherco 345-115 kV | transformer | 1 | 345 | 115 | 448 | New transformer | H5 | MN |  |  | 100 |  |  |  | Planned | 3001443 | [8 empty] | Y | Y | Y
A | 268 | 2006-07-12 | BR | N-NM | XEL | 377 | 2006-07-12 | Wind 425 | 2007-01-01 | Minn Valley | Redwood Falls Tap | 1 | 115 |  | 310 | Upgrade existing 115 kV line | G6 | MN | 27.2 |  |  | 100 |  |  | Planned | 9380127.53 | [7 empty] | A046, A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 307 | 2006-03-27 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-10-01 | Nobles Co | Lakefield Jct | 1 | 345 |  | 2085 | New line | G7 | MN |  | 42 |  | 100 |  |  | Planned | 37070397.4058 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 309 | 2006-03-27 | TX | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-10-01 | Nobles Co 345-115 kV | transformer | 1 | 345 | 115 | 600 | New transformer | G7 | MN |  |  |  | 100 |  |  | Planned | 5792804.9564 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 272 | 2006-03-27 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-10-01 | Redwood Falls Tap | Franklin | 1 | 115 |  | 310 | Upgrade existing 115 kV line | H6 | MN | 13 |  |  | 100 |  |  | Planned | 3185000 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 308 | 2006-03-27 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-10-01 | Nobles Co | Fenton | 1 | 115 |  | 600 | New line | G7 | MN |  | 12 |  | 100 |  |  | Planned | 7913905.0642 | [7 empty] | G162, A053, A055, A058, A059, A102 | Y | Y | Y |  | Network | Y
A | 2041 | 2005-11-28 | CAP | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Nobles Co | Capacitor |  | 115 |  | 40 Mvar | New capacitor | G7 | MN |  |  |  | 100 |  |  | Planned | 634038.2211 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 2315 | 2006-10-15 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Yankee | Brookings County | 1 | 115 |  | 620 | New 115 kV line |  | MN |  |  |  | 100 |  |  | Planned | [8 empty] | SW MN SE SD Electric transmission study | Y | Y | Y
A | 311 | 2006-03-27 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Split Rock | Nobles Co | 1 | 345 |  | 2085 | New line | G7 | MN |  | 52 |  | 100 |  |  | Planned | 44966947.415 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 537 | 2006-10-15 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Buffalo Ridge | Yankee | 1 | 115 |  | 620 | New 115 kV line |  | MN |  |  |  | 100 |  |  | Planned | [8 empty] | SW MN SE SD Electric transmission study | Y | Y | Y
A | 302 | 2006-03-27 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Fenton | Chanarambie | 1 | 115 |  | 600 | New 115 kV line | G6 | MN |  | 14 |  | 100 |  |  | Planned | 7412392.6347 | [7 empty] | G162, A053, A055, A058, A059, A102 | Y | Y | Y |  | Network | Y
A | 2283 | 2006-10-15 | BR | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2008-11-01 | Brookings Co | White | 1 | 345 |  | 2085 | New 345 kV line | G7 | SD/MN |  |  |  | 100 |  |  | Planned | [8 empty] | G349, BRIGO, SW MN SE SD Elec trans study | Y | Y | Y |  | Network
A | 975 | 2006-10-15 | TX | N-NM | XEL | 385 | 2006-07-12 | Wind 825 | 2010-06-01 | Nobles Co 345-115 kV | transformer | 2 | 345 | 115 | 672 | New transformer | G7 | MN |  |  |  | 100 |  |  | Planned | 5792804.96 | [7 empty] | BRIGO, G287 | Y | Y | Y |  | Network
A | 2038 | 2006-07-12 | CAP | N-NM | XEL | 417 | 2006-07-12 |  | 2007-06-01 | Westgate | Capacitor |  | 115 |  | 80 Mvar | New capacitor | H6 | MN |  |  | 100 |  |  |  | Planned | 1500000 | [8 empty] | Y | Y | Y
A | 800 | 2006-07-12 | BR | N-NM | XEL | 609 | 2006-07-12 |  | 2007-06-01 | Long Lake | Oakdale (from Woodbury) | 1 | 115 |  | 310 | Upgrade existing line | P5 | MN | 3.7 |  | 100 |  |  |  | Planned | 760000 | [8 empty] | Y | Y | Y
A | 1359 | 2006-07-12 | BR | N-NM | XEL | 671 | 2006-07-12 |  | 2007-06-01 | Oakdale | Tanners Lake | 1 | 115 |  | 223 | Upgrade existing line | P5 | MN | 5.2 |  | 100 |  |  |  | Planned | 800000 | [8 empty] | Y | Y | Y
A | 1361 | 2006-07-12 | BR | N-NM | XEL | 673 | 2006-07-12 |  | 2008-06-01 | Champlin Tap | Crooked Lake | 1 | 115 |  | 223 | Upgrade existing line | TC detail | MN | 3.1 |  | 100 |  |  |  | Planned | 310000 | MISO planning | [7 empty] | Y | Y | Y
A | 1362 | 2006-07-12 | BR | N-NM | XEL | 674 | 2006-07-12 |  | 2008-05-01 | High Bridge | Rogers Lake | 1 | 115 |  | 585 | Upgrade existing line | TC detail | MN | 4.2 |  |  | 100 |  |  | Planned | 2400000 | [7 empty] | G043, G237 | Y | Y | Y |  | Network
A | 3088 | 2006-07-12 | DV | N-NM | XEL | 780 | 2006-07-12 | Wind 825 | 2007-11-01 | Fieldon Township | Series Capacitor |  | 345 |  | 20 ohms | New series capacitor on LGS-Wilmarth 345 | H6 | MN |  |  |  | 100 |  |  | Planned | 10100000 | [7 empty] | A046, A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 2274 | 2006-10-15 | BR | N-NM | XEL | 1364 | 2006-10-15 |  | 2007-05-01 | Lakefield Jct | Lakefield Generation | 1 | 345 |  | 1165 | Raise the structures to increase the thermal rating |  | MN |  |  |  |  | 100 |  | Planned | [8 empty] | A102 | Y | Y | Y |  |  | Y
A | 2277 | 2006-10-15 | TX | N-NM | XEL | 1366 | 2006-10-15 | CNF Gen | 2008-05-01 | Cannon Falls Generating station | Transformer | 1 | 161 | 115 | 187 | Transformer relocated from Cannon Falls substation |  | MN | [6 empty] | Planned | 13940000 | IA | [7 empty] | Y | Y | Y |  | Network
A | 2278 | 2006-10-15 | BR | N-NM | XEL | 1366 | 2006-10-15 | CNF Gen | 2008-05-01 | Cannon Falls Generating station | Cannon Falls | 1 | 115 |  | 140 | Build in and out of the Cannon Falls generating station from Cannon Falls - Empire 115 kV line |  | MN | [6 empty] | Planned | 1 | [8 empty] | Y | Y | Y |  | Network
A | 2280 | 2006-10-15 | BR | N-NM | XEL | 1366 | 2006-10-15 | CNF Gen | 2008-05-01 | Cannon Falls Generating station | Empire | 1 | 115 |  | 200 | Build in and out of the Cannon Falls generating station from Cannon Falls - Empire 115 kV line |  | MN | [6 empty] | Planned | 1 | [8 empty] | Y | Y | Y |  | Network
A | 2281 | 2006-10-15 | BR | N-NM | XEL | 1366 | 2006-10-15 | CNF Gen | 2008-05-01 | Cannon Falls Generating station | Spring Creek | 1 | 161 |  | 234 | Build in and out of the Cannon Falls generating station from Cannon Falls - spring Creek line |  | MN | [6 empty] | Planned | 1 | [8 empty] | Y | Y | Y |  | Network
A | 2279 | 2006-10-15 | BR | N-NM | XEL | 1366 | 2006-10-15 | CNF Gen | 2008-05-01 | Cannon Falls Generating station | Cannon Falls | 2 | 115 |  | 167 | Build in and out of the Cannon Falls generating station from Cannon Falls - spring Creek line |  | MN | [6 empty] | Planned | 1 | [8 empty] | Y | Y | Y |  | Network
A | 266 | 2006-07-12 | BR | N-NM | XEL/ALT | 377 | 2006-07-12 | Wind 425 | 2006-11-01 | Lakefield Jct | Fox Lake | 2 | 161 |  | 434 | new line | G7 | MN |  | 24 |  | 100 |  |  | Planned | 6000000 | [7 empty] | A053, A055, A058, A059, A102 | Y | Y | Y |  |  | Y
A | 645 | 2006-03-27 | BR | N-NM | XEL/WAPA | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Brookings Co | White | 1 | 345 |  | 600 |  | G6 | SD |  | 2 |  |  | 100 |  | Planned | [9 empty] | Y | Y | Y
A | 646 | 2006-01-25 | BR | N-NM | XEL/WAPA | 385 | 2006-07-12 | Wind 825 | 2007-11-01 | Brookings Co | 345/115 transformer | 1 | 345 | 115 | 672 |  | G6 | SD |  |  |  |  | 100 |  | Planned | 12179190 | [8 empty] | Y | Y | Y
B | 2122 | 2006-08-24 | BR | N-ITWG | ALTW | 1291 | 2006-08-24 | 13 | 2011-06-01 | Grand Mound | Grand Mound tap | 1 | 161 |  | 326/326 | New |  | IA | 0 | 2 |  |  |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2204 | 2006-10-06 | BR | N-ITWG | ALTW | 1340 | 2006-10-06 | 1 | 2011-06-01 | Hazleton | Salem | 1 | 345 |  | 2000 | new line |  | IA |  | 74 | 100 |  |  |  | Proposed | 55500000 | [8 empty] | Y | Y | Y
B | 2205 | 2006-10-06 | TX | N-ITWG | ALTW | 1340 | 2006-10-06 | 1 | 2011-06-01 | Lore | transformer | 1 | 345 | 161 | 335 | new transformer |  | IA |  |  | 100 |  |  |  | Proposed | 4000000 | [8 empty] | Y | Y | Y
B | 2213 | 2006-10-06 | BR | N-ITWG | ALTW | 1345 | 2006-10-06 | 6 | 2011-06-01 | Quad Cities | Salem | 1 | 345 |  | 1246 | upgrade limiting equipment |  | IA |  |  | 100 |  |  |  | Proposed | 150000 | [8 empty] | Y | Y | Y
B | 2214 | 2006-10-06 | TX | N-ITWG | ALTW | 1346 | 2006-10-06 | 7 | 2011-06-01 | Rock Creek | transformer | 1 | 345 | 161 | 448 | upgrade limiting equipment |  | IA |  |  | 100 |  |  |  | Proposed | 100000 | [8 empty] | Y | Y | Y
B | 2222 | 2006-10-12 | BR | N-ITWG | ALTW | 1374 | 2006-10-12 |  | 2010-06-01 | Marshalltown | Stoney Point | 1 | 115 |  | 233 |  |  | IA | 61 |  | 100 |  |  |  | Planned | 6100000 | [8 empty] | Y | Y | Y
B | 59 | 2006-03-17 | BR | C-CSILL | Ameren | 78 | 2006-10-04 | 55 | 2008-06-01 | Loose Creek | Jefferson City | 1 | 345 |  | 1606 | new 345 kV line | I11 | MO |  | 15 | 100 |  |  |  | Planned | 10210700 | Eng | [7 empty] | Y | N | Y
B | 65 | 2006-03-17 | TX | C-CSILL | Ameren | 78 | 2006-10-04 | 55 | 2008-06-01 | Jefferson City 345/161 | transformer | 1 | 345 | 161 | 450 | new 345/161 kV transformer | I11 | MO |  |  | 100 |  |  |  | Planned | 6256900 | Eng | [7 empty] | Y | N | Y
B | 58 | 2006-03-17 | BR | C-CSILL | Ameren | 151 | 2005-07-11 |  | 2009-06-01 | Dupo Ferry | Buck Knob | 1 | 138 |  | 240 | reconductor | J11 | IL | 22 |  | 100 |  |  |  | Proposed | 5170600 | Eng | [7 empty] | Y | N | Y
B | 399 | 2006-03-17 | BR | C-CSILL | Ameren | 152 | 2006-10-04 |  | 2010-06-01 | Big River | Rockwood | 1 | 138 |  | 370 | new line | J11 | MO |  | 10 | 100 |  |  |  | Proposed | 12794000 | Eng | [7 empty] | Y | N | Y
B | 1401 | 2006-03-17 | BR | C-CSILL | Ameren | 710 | 2006-10-04 |  | 2007-06-01 | Kinmundy | Salem | 1 | 138 |  | 240 | increase ground clearance | K10 | IL | 10.3 |  | 100 |  |  |  | Proposed | 661200 | Eng | [7 empty] | Y | N | Y
B | 1406 | 2006-03-17 | BR | C-CSILL | Ameren | 715 | 2006-10-04 |  | 2008-06-01 | Wildwood | Gray Summit | 1 | 138 |  | 415 | reconductor | J11 | MO | 0.14 |  | 100 |  |  |  | Proposed | 64250 | Eng | [7 empty] | Y | N | Y
B | 1407 | 2006-03-17 | BR | C-CSILL | Ameren | 716 | 2006-10-04 |  | 2008-06-01 | Wildwood | Gray Summit | 2 | 138 |  | 415 | reconductor | J11 | MO | 0.14 |  | 100 |  |  |  | Proposed | 64250 | Eng | [7 empty] | Y | N | Y
B | 1408 | 2006-03-17 | BR | C-CSILL | Ameren | 717 | 2005-07-11 |  | 2008-06-01 | Conway | Orchard Gardens | 1 | 138 |  | 240 | increase ground clearance | J11 | MO |  |  | 100 |  |  |  | Proposed | 100000 | [8 empty] | Y | N | Y
B | 1409 | 2006-03-17 | BR | C-CSILL | Ameren | 718 | 2005-07-11 |  | 2008-06-01 | Conway | Orchard Gardens | 2 | 138 |  | 240 | increase ground clearance | J11 | MO |  |  | 100 |  |  |  | Proposed | 100000 | [8 empty] | Y | N | Y
B | 1411 | 2006-03-17 | BR | C-CSILL | Ameren | 720 | 2006-10-04 |  | 2008-12-01 | Page Substation | Replace 3-138 kV Breakers |  | 138 |  |  | replace existing 138 kV breakers | J10 | MO |  |  | 100 |  |  |  | Proposed | 539400 | Eng | [7 empty] | Y | N | Y
B | 1412 | 2006-03-17 | BR | C-CSILL | Ameren | 721 | 2005-07-11 |  | 2009-06-01 | Wildwood Sub. | Add 2-345 kV Breakers |  | 345 |  |  | install new 345 kV breakers | J11 | MO |  |  | 100 |  |  |  | Proposed | 1873200 | Eng | [7 empty] | Y | N | Y
B | 3094 | 2006-03-17 | DV | C-CSILL | Ameren | 783 | 2005-07-11 |  | 2007-06-01 | Robinson-Marathon | Cap. - Increase 18 Mvar to 36 Mvar |  | 138 |  | 36 Mvar | increase size of existing 138 kV capacitor | L10 | IL |  |  | 100 |  |  |  | Proposed | 151900 | Eng | [7 empty] | Y | N | Y
B | 1932 | 2006-03-17 | BR | C-CSILL | Ameren | 1233 | 2006-03-17 |  | 2009-06-01 | Cahokia | Ashley | 1 | 138 |  | 318 | Replace bus conductor and retap CTs at Cahokia terminal | J11 | MO |  |  | 100 |  |  |  | Proposed | 116300 | Eng | [7 empty] | Y | N | Y
B | 1934 | 2006-03-17 | BR | C-CSILL | Ameren | 1235 | 2006-03-17 |  | 2009-06-01 | Fredericktown | AECI Fredericktown Tap | 1 | 161 |  | 250 | Increase ground clearance | K11 | MO | 12 |  | 100 |  |  |  | Proposed | 970500 | Eng | [7 empty] | Y | N | Y
B | 1936 | 2006-03-17 | BR | C-CSILL | Ameren | 1237 | 2006-03-17 |  | 2010-06-01 | Campbell | Euclid-Page | 1 | 138 |  | 415 | Rebuild dbl. ckt. 138 kV | J11 | MO | 5.25 |  | 100 |  |  |  | Proposed | 15254100 | Eng | [7 empty] | Y | N | Y
B | 1937 | 2006-03-17 | BR | C-CSILL | Ameren | 1238 | 2006-03-17 |  | 2010-06-01 | GM-Point Prairie 161 kV Line | AECI Enon Substation | 1 | 161 |  | 280 | Extend 1 mile of line to AECI Enon Substation | J10 | MO |  | 1 | 100 |  |  |  | Proposed | 1303500 | Eng | [7 empty] | Y | N | Y
B | 1940 | 2006-03-17 | BR | C-CSILL | Ameren | 1240 | 2006-03-17 |  | 2010-12-01 | Sioux | Huster | 3 | 138 |  | 370 | Reconductor 13 miles | J10 | MO | 13 |  | 100 |  |  |  | Proposed | 941050 | Eng | [7 empty] | Y | N | Y
B | 1939 | 2006-03-17 | BR | C-CSILL | Ameren | 1240 | 2006-03-17 |  | 2010-12-01 | Sioux | Huster | 1 | 138 |  | 370 | Reconductor 15 miles | J10 | MO | 15 |  | 100 |  |  |  | Proposed | 941050 | Eng | [7 empty] | Y | N | Y
B | 386 | 2006-03-17 | BR | C-CSILL | AmerenCILCO | 141 | 2006-03-17 |  | 2009-06-01 | Duck Creek | Tazewell | 1 | 345 |  |  | convert bus duct to OH | K9 | IL | [5 empty] | 100 | Proposed | 119500 | Eng | [7 empty] | Y | N | Y
B | 852 | 2006-03-17 | BR | C-CSILL | AmerenCILCO | 874 | 2005-07-11 |  | 2009-06-01 | East Springfield | Eastdale |  | 138 |  | 299 | Replace terminal equipment at East Springfield | K10 | IL |  |  | 100 |  |  |  | Proposed | 344300 | Eng | [7 empty] | Y | N | Y
B | 1428 | 2006-03-17 | BR | C-CSILL | AmerenIP | 734 | 2006-03-17 |  | 2009-06-01 | Washington St. Line 1364 | S. Bloomington | 1 | 138 |  | 266 | reconductor Line 1364 from S. Bloomington to Tower 512 | K9 | IL | 3.3 |  | 100 |  |  |  | Proposed | 1693800 | Eng | [7 empty] | Y | N | Y
B | 1427 | 2006-03-17 | BR | C-CSILL | AmerenIP | 734 | 2006-03-17 |  | 2009-06-01 | Line 1364 (new tap) | Washington Street Sub | 2 | 138 |  | 266 | install ring bus and split S.Bloomington to Raab Rd. | K9 | IL |  | 0.17 | 100 |  |  |  | Proposed | 4066500 | Eng | [6 empty] | A109 | Y | N | Y |  |  | Y
B | 1430 | 2006-03-17 | BR | C-CSILL | AmerenIP | 737 | 2006-03-17 |  | 2009-06-01 | B luff City | W. Salem |  | 138 |  |  | new 138 kV breaker addition at Bluff City | K10 | IL |  |  | 100 |  |  |  | Proposed | 1756400 | Eng | [7 empty] | Y | N | Y
B | 842 | 2005-07-11 | BR | C-CSILL | AmerenIP | 866 | 2005-07-11 |  | 2007-06-01 | Latham 345/138 kV Substation | Mason City-Decatur Line 1342 | 1 | 138 |  | 160 | Install 138 kV breaker for 'in-out' taps to Line 1342, construct 0.38 mile 138 kV line | K9 | IL |  | 0.38 | 100 |  |  |  | Proposed | 1658000 | Planning MISO | [7 empty] | Y | N | Y
B | 846 | 2006-03-17 | BR | C-CSILL | AmerenIP | 870 | 2005-07-11 |  | 2008-06-01 | Sidney | Paxton | 1 | 138 |  | 399 | Reconductor 18 miles of 350 kcmil Cu | L9 | IL | 18 |  | 100 |  |  |  | Planned | 5690300 | Eng | [7 empty] | Y | N | Y
B | 848 | 2006-03-17 | BR | C-CSILL | AmerenIP | 872 | 2005-07-11 |  | 2008-06-01 | Mahomet | Champaign | 1 | 138 |  | 240 | Reconductor 1.55 mile 477 kcmil ACSR from Mahomet Sub. To Twr. 29 | K9 | IL | 1.55 |  | 100 |  |  |  | Proposed | 725500 | Eng | [7 empty] | Y | N | Y
B | 1933 | 2006-03-17 | BR | C-CSILL | AmerenIP | 1234 | 2006-03-17 |  | 2009-06-01 | Havana, South | Mason City, West | 1 | 138 |  | 155 | Increase ground clearance on 18.4 miles | J9 | IL | 18.4 |  | 100 |  |  |  | Proposed | 642300 | Eng | [7 empty] | Y | N | Y
B | 1935 | 2006-03-17 | BR | C-CSILL | AmerenIP | 1236 | 2006-03-17 |  | 2009-06-01 | Stallings | Prairie State Power Plant | 1 | 345 |  | 1297 | Replace 2000 A terminal equipment with 3000 A equipment at Stallings | K11 | IL |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | N | Y
B | 1938 | 2006-03-17 | BR | C-CSILL | AmerenIP | 1239 | 2006-03-17 |  | 2010-06-01 | Normal East | Brokaw | 1 | 138 |  | 280 | Replace 600 A terminal equipment to 1200 A at Normal, East | K9 | IL |  |  | 100 |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 1941 | 2006-03-17 | BR | C-CSILL | AmerenIP | 1351 | 2006-03-17 |  | 2010-06-01 | Pana, North | Decatur Rt. 51 L1462 | 1 | 138 |  | 280 | Replace 1200 A terminal equipment with 1600 A equipment at Pana | K10 | IL |  |  | 100 |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 463 | 2006-10-27 | LN | West | ATC LLC | 175 | 2005-07-11 |  | 2007-06-01 | Ellinwood | Sunset Point |  | 138 |  | 289 MVA SE |  | K6 | WI | 3.6 |  | 100 |  |  |  | Planned | 2500000 | Eng | [7 empty] | Y | N | Y
B | 891 | 2006-07-05 | BR | C-WUMS | ATC LLC | 333 | 2006-03-16 | newgrp12 | 2007-06-01 | Mackinac | Substation relocation |  | 138 |  |  | Straits substation rename/relocation | M5 | MI |  |  | 50 |  |  | 50 | Proposed | 5800000 | Eng | [7 empty] | Y | N | Y | ATC zone 2
B | 596 | 2006-10-04 | BR | C-WUMS | ATC LLC | 333 | 2006-03-16 | newgrp12 | 2009-05-01 | Hiawatha | Indian Lake (string second 138 kV circuit) | 2 | 138 |  | 279 | string 2nd 138 kV circuit | L5 | WI |  | 40 | 30 |  | 30 | 40 | Proposed | 200000 | Eng | [7 empty] | Y | N | Y | ATC zone 2
B | 474 | 2006-10-04 | BR | C-WUMS | ATC LLC | 333 | 2006-03-16 | newgrp12 | 2009-05-01 | Hiawatha | Indian Lake (convert double circuit 138 kV from 69 kV operation to 138 kV o | 2 | 138 |  | 279 | rebuild in 2006 and convert in 2009 | L5 | MI | 40 |  | 30 |  | 30 | 40 | Proposed | 200000 | Eng | [7 empty] | Y | N | Y | ATC zone 2
B | 598 | 2006-07-05 | BR | C-WUMS | ATC LLC | 347 | 2005-07-11 | newgrp21 | 2008-06-01 | Hustisford | Hubbard (convert) |  | 138 |  | 348 | convert | K7 | WI | 8 |  | 100 |  |  |  | Proposed | 2400000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
B | 597 | 2006-07-05 | BR | C-WUMS | ATC LLC | 347 | 2005-07-11 | newgrp21 | 2008-06-01 | Rubicon | Hustisford |  | 138 |  | 348 |  | K7 | WI |  | 5 | 100 |  |  |  | Proposed | 4800000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
B | 897 | 2005-07-11 | SUB | C-WUMS | ATC LLC | 356 | 2006-03-16 | newgrp6 | 2011-06-01 | Rockdale | substation expansion |  | 345 |  |  | expand 345 kV substation | K7 | WI |  |  | 100 |  |  |  | Proposed | 1506733 | Eng | [7 empty] | Y | N | Y
B | 486 | 2005-07-11 | BR | C-WUMS | ATC LLC | 356 | 2006-03-16 | newgrp6 | 2011-06-01 | West Middleton | Rockdale | 1 | 345 |  | 1200 |  | K7 | WI |  | 35 | 50 |  | 50 |  | Proposed | 63249004 | Eng | [7 empty] | Y | N | Y
B | 488 | 2006-03-16 | TX | C-WUMS | ATC LLC | 356 | 2006-03-16 | newgrp6 | 2011-06-01 | West Middleton 345/138 | transformer | 1 | 345 | 138 | 500 |  | K7 | WI |  |  | 100 |  |  |  | Proposed | 7888517 | Eng | [7 empty] | Y | N | Y
B | 898 | 2006-07-05 | CAP | C-WUMS | ATC LLC | 544 | 2005-07-11 | p2-104 | 2008-06-01 | Bluemound | Capacitor bank |  | 138 |  | 200 Mvar |  | L7 | WI |  |  | 100 |  |  |  | Proposed | 3300000 | Eng | [7 empty] | Y | N | Y | ATC zone 5
B | 1246 | 2006-10-27 | LN | West | ATC LLC | 567 | 2005-07-11 | 567 | 2007-06-01 | Lawn Road | White Clay | 1 | 138 |  | 287 |  | K6 | WI | 15 |  |  |  | 100 |  | Planned | 300000 | Eng | [7 empty] | Y | N | Y
B | 1245 | 2006-10-27 | LN | West | ATC LLC | 567 | 2005-07-11 | 567 | 2007-06-01 | North Appleton | Lawn Road | 1 | 138 |  | 287 |  | K6 | WI | 15 |  |  |  | 100 |  | Planned | 300000 | Eng | [7 empty] | Y | N | Y
B | 1269 | 2006-07-05 | BR | C-WUMS | ATC LLC | 574 | 2005-07-11 | 574 | 2010-06-01 | Monroe County (XEL) | Council Creek (ATC) | 1 | 161 |  | 530 |  | J6 | WI | 20 |  | 100 |  |  |  | Proposed | 16700000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
B | 1370 | 2006-07-05 | TX | C-WUMS | ATC LLC | 574 | 2005-07-11 | 574 | 2010-06-01 | Council Creek 161-138 kV | transformer |  | 161 | 138 | 280 |  | J6 | WI |  |  | 100 |  |  |  | Proposed | 2500000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
B | 859 | 2006-07-05 | BR | C-WUMS | ATC LLC | 574 | 2005-07-11 | 574 | 2010-06-01 | Petenwell | Saratoga |  | 138 |  |  | rebuild/reconductor | J6 | WI | 23 |  | 50 |  |  | 50 | Proposed | 14800000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
B | 858 | 2006-07-05 | BR | C-WUMS | ATC LLC | 574 | 2005-07-11 | 574 | 2010-06-01 | Council Creek | Petenwell |  | 138 |  |  | uprate | J6 | WI | 32 |  | 50 |  |  | 50 | Proposed | 200000 | Eng | [7 empty] | Y | N | Y | ATC zone 1
B | 878 | 2005-07-11 | BR | C-WUMS | ATC LLC | 880 | 2005-07-11 | new103 | 2008-06-01 | North Appleton | Mason Street | 1 | 138 |  | 229 | uprate 138 kV line | K5 | WI | 21 |  | 50 |  |  | 50 | Proposed | 1700000 | Eng | [6 empty] | A191, A215 | Y | N | Y |  |  | Y
B | 879 | 2005-07-11 | BR | C-WUMS | ATC LLC | 880 | 2005-07-11 | new103 | 2008-06-01 | North Appleton | Lost Dauphin | 1 | 138 |  | 288 | uprate 138 kV line | K5 | WI | 12 |  | 50 |  |  | 50 | Proposed | 1600000 | Eng | [6 empty] | A191, A215 | Y | N | Y |  |  | Y
B | 882 | 2005-07-11 | CAP | C-WUMS | ATC LLC | 882 | 2006-07-05 | new105 | 2007-06-01 | Ontonagon | Capacitor bank |  | 138 |  | 16.32 Mvar | add 2x8.16 Mvar Capacitors |  | MI |  |  | 100 |  |  | 100 | Proposed | 1200000 | Eng | [7 empty] | Y | N | Y
B | 886 | 2006-07-05 | SUB | C-WUMS | ATC LLC | 886 | 2005-07-11 | new109 | 2008-06-01 | North Lake | Substation relocation |  | 138 |  |  | Cedar substation rename/relocation | K4 | MI |  |  | 50 |  |  | 50 | Planned | 7300000 | Eng | [7 empty] | Y | N | Y
B | 887 | 2006-07-05 | BR | C-WUMS | ATC LLC | 887 | 2005-07-11 | new110 | 2009-06-01 | Bain | New 345 kV bus |  | 345 |  |  | construct 345 kV bus | L7 | WI | [6 empty] | Proposed | 2100000 | Eng | [7 empty] | Y | N | Y
B | 888 | 2005-07-11 | TX | C-WUMS | ATC LLC | 888 | 2005-07-11 | new111 | 2008-06-01 | Plains 345-138 kV | transformer | 2 | 345 | 138 | 500 | second 500 MVA transformer | K5 | MI | [5 empty] | 100 | Proposed | 5400000 | Eng | [7 empty] | Y | N | Y
B | 2462 | 2006-10-27 | SUB | West | ATC LLC | 1256 | 2006-05-08 |  | 2010-04-01 | Christiana |  |  | 138 |  |  | replace five overdutied 138 kV breakers | [8 empty] | Proposed | 1100000 | [8 empty] | Y | N | Y
B | 1964 | 2006-10-27 | LN | West | ATC LLC | 1256 | 2006-05-08 | 1256 | 2010-04-01 | Paddock | Rockdale | 2 | 345 |  | 1430 | add a second circuit (new line) between the existing 345 kV substations Paddock and Rockdale. | K7 | WI | 22.7 | 7.6 |  |  |  | 100 | Proposed | 112800000 | [7 empty] | ATC Access Initiative | Y | N | Y
B | 2461 | 2006-10-27 | SUB | West | ATC LLC | 1256 | 2006-05-08 |  | 2010-04-01 | Rockdale |  |  | 345 |  |  | convert to a modifed breaker and a half configuration, replace 5 overdutied 138 kV breakers and replace existing transformer with 500MVA | [8 empty] | Proposed | 12300000 | [8 empty] | Y | N | Y
B | 2643 | 2006-10-27 | SUB | West | ATC LLC | 1256 | 2006-05-08 |  | 2010-04-01 | Paddock |  |  | 345 |  |  | upgrade protection system | [8 empty] | Proposed | 300000 | [8 empty] | Y | N | Y
B | 1985 | 2006-10-27 | LN | West | ATC LLC | 1267 | 2006-07-05 | new1 | 2009-06-01 | Verona | Oak Ridge | 1 | 138 |  |  | line to new T-D substation |  | WI | [6 empty] | Proposed | 17900000 | [8 empty] | Y | N | Y
B | 1988 | 2006-07-05 | TX | C-WUMS | ATC LLC | 1269 | 2006-07-05 | new3 | 2011-06-01 | Arcadian 345-138kV | transformer | 1 | 345 | 138 | 500 | replace Arcadian 345/138kV transformer #3 |  | WI | [6 empty] | Proposed | 3500000 | [8 empty] | Y | N | Y
B | 1990 | 2006-07-05 | LN | C-WUMS | ATC LLC | 1270 | 2006-07-05 | new4 | 2011-06-01 | Arcadian | Waukesha | 1 | 138 |  | 426 | Increase line clearance |  | WI | 4 | 0 |  |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 1989 | 2006-07-05 | LN | C-WUMS | ATC LLC | 1270 | 2006-07-05 | new4 | 2011-06-01 | Arcadian | Waukesha | 2 | 138 |  | 426 | Increase line clearance |  | WI | 4 | 0 |  |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 1991 | 2006-07-05 | LN | C-WUMS | ATC LLC | 1271 | 2006-07-05 | new5 | 2011-06-01 | Oak Creek | Pennsylvania | 1 | 138 |  | 293 | Increase line clearance |  | WI |  | 0 |  |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 2105 | 2006-08-31 | DV | WUMS | ATC LLC | 1279 | 2006-08-31 | 1 | 2009-06-01 | North Beaver Dam 138 |  |  | 138 |  | 49 Mvar |  |  | WI | [6 empty] | Proposed | 1800000 | [8 empty] | Y | N | Y
B | 2108 | 2006-08-31 | BR | WUMS | ATC LLC | 1281 | 2006-08-31 | 3 | 2008-06-01 | Portage | Trienda | 1 | 138 |  | 293/339 |  |  | WI | 3.4 | [5 empty] | Proposed | 1031249 | [8 empty] | Y | N | Y
B | 2113 | 2006-08-24 | BR | WUMS | ATC LLC | 1284 | 2006-08-31 | 6 | 2010-06-01 | Albers | Somers | 1 | 138 |  | 345/477 |  |  | WI | [6 empty] | Proposed | [9 empty] | Y | N | Y
B | 2112 | 2006-08-24 | BR | WUMS | ATC LLC | 1284 | 2006-08-31 | 6 | 2010-06-01 | Racine | Somers | 1 | 138 |  | 345/477 |  |  | WI | [6 empty] | Proposed | [9 empty] | Y | N | Y
B | 2110 | 2006-08-31 | BR | WUMS | ATC LLC | 1284 | 2006-08-31 | 5 | 2010-06-01 | Albers | Tie | 1 | 138 |  |  |  |  | WI | [6 empty] | Proposed | 0 | [8 empty] | Y | N | Y
B | 2111 | 2006-08-31 | BR | WUMS | ATC LLC | 1284 | 2006-08-31 | 5 | 2010-06-01 | Racine | Albers | 1 | 138 |  | 345/477 |  |  | WI | 8 | [5 empty] | Proposed | 4181904 | [8 empty] | Y | N | Y
B | 1453 | 2006-10-27 | IND | West | ATC LLC | 1450 | 2006-10-27 | 1 | 2008-06-01 | Cornell (4.5 ohm reactor) | Fiebrantz |  | 138 |  |  |  | K6 | WI | [5 empty] | 100 | Proposed | 4651493 | Eng | [6 empty] | A130 | Y | N | Y |  |  | Y
B | 1290 | 2006-07-05 | BR | E-MIO | CIN | 618 | 2005-07-11 | X02C7985 | 2009-12-31 | Beckjord | (rebuild substation) |  | 138 |  |  | rebuild substation so it can be tied together under normal conditions | N10 | OH | 0 | 0 | 100 |  |  |  | Proposed | 1738266 | Engr |  | N | [5 empty] | Y | N | Y
B | 1301 | 2006-10-10 | TX | E-MIO | CIN | 625 | 2006-07-05 | X02C7959 | 2008-06-01 | Pierce/Beckjord 345/138 kV | transformer | C | 345 | 138 | 172 | Add third 345/138kV xfr 400 MVA connected to Beckjord 138kV North Bus. | N10 | OH |  |  | 100 |  |  |  | Proposed | 2527029 | Plan |  | N | [5 empty] | Y | N | Y
B | 827 | 2006-03-27 | BR | E-MIO | CIN | 852 | 2006-07-05 | 604F6351 | 2009-12-31 | Lafayette Southeast | Tipmont Concord Jct | 1 | 138 |  | 306 | 13819 reconductor with 954ACSR 100C 604F6351 | L9 | IN | 8 |  | 100 |  |  |  | Planned | 2425000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
B | 1979 | 2006-07-05 | BR | E-MIO | CIN | 852 | 2006-07-05 | 604F6348 | 2009-12-31 | Crawfordsville | Tipmont Concord Jct |  | 138 |  | 306 | 13819 reconductor with 954ACSR 100C | L9 | IN | 17.4 |  | 100 |  |  |  | Planned | 6142189 | Engr |  | Y | [5 empty] | Y | N | Y
B | 1981 | 2006-07-05 | BR | E-MIO | CIN | 1264 | 2006-07-05 | 702G6714 | 2011-06-01 | Speed |  |  | 345 | 138 | 717 | Replace existing 345/138 transformer at Speed with a new transformer rated at 3,000A or higher. |  | IN |  |  | 100 |  |  |  | Proposed | 5000000 | Plan |  | N | [5 empty] | Y | N | Y
B | 647 | 2006-10-15 | BR | N-NM | EEI (MP) | 1025 | 2005-08-31 | Mesaba Energy | 2010-05-01 | Mesaba Plant Site | Blackberry | 1 | 230 |  | 600 | double circuit structures | I4 | MN | 4 | 5 |  | 100 |  |  | Proposed |  | Planning MISO | [6 empty] | G519 | Y | Y | Y |  | Network
B | 648 | 2006-10-15 | BR | N-NM | EEI (MP) | 1025 | 2005-08-31 | Mesaba Energy | 2010-05-01 | Mesaba Plant Site | Blackberry | 1 | 230 |  | 600 | double circuit structures | I4 | MN | 4 | 5 |  | 100 |  |  | Proposed |  | Planning MISO | [6 empty] | G519 | Y | Y | Y |  | Network
B | 2187 | 2006-10-09 | BR | East | FE | 1317 | 2006-09-11 | COH-05-050318-152342 | 2009-06-01 | Hayes | Hayes | 1 | 345 | 138 | 444/466 MVA | New Hayes Transformer |  | OH | [6 empty] | Proposed | 1600000 | [8 empty] | Y | N | Y | with MISO
B | 2188 | 2006-10-09 | BR | East | FE | 1317 | 2006-09-11 | COH-05-050318-152342 | 2009-06-01 | Hayes | Hayes |  | 345 | 138 |  | New Hayes Substation | [8 empty] | Proposed | 9400000 | [8 empty] | Y | N | Y | with MISO
B | 2190 | 2006-10-09 | BR | East | FE | 1324 | 2006-09-13 | N/A yet | 2009-06-01 | Wallbridge Junction | Maclean | 1 | 138 |  | 308/375 MVA | Line Reconductor |  | OH | 0.5 | [5 empty] | Proposed | 247900 | [8 empty] | Y | N | Y | with MISO
B | 2203 | 2006-10-09 | CAP | East | FE | 1339 | 2006-10-05 | EOH-06-050805-134827 | 2010-06-01 | Maysville | capacitor bank |  | 138 |  |  | Capacitor Bank Addition |  | OH | [6 empty] | Proposed | 451700 | [8 empty] | Y | N | Y | with MISO
B | 2386 | 2006-10-25 | LN | East | FE | 1383 | 2006-10-25 |  | 2009-06-01 | Richland 138 kV | Naomi Jct 138 kV | 1 | 138 |  | 208 | Reconductor one of two circuits on a 10 mile stretch of double circuit tower line between Ridgeville Jct and Naomi Jct | N8 | OH | 10 | [5 empty] | Proposed | 1500000 | [7 empty] | MTEP06 | Y | N | Y
B | 2385 | 2006-10-25 | LN | East | FE | 1383 | 2006-10-25 |  | 2009-06-01 | Richland 138 kV | Ridgeville Jct 138 kV | 1 | 138 |  | 208 | Reconductor 12 mile portion of double circuit tower line between Richland and Ridgeville Jct | M7 | OH | 12 | [5 empty] | Proposed | 3500000 | [7 empty] | MTEP06 | Y | N | Y
B | 753 | 2005-11-28 | BR | N-NM | GRE | 599 | 2005-06-15 |  | 2009-06-01 | Crooked Lake | Enterprise Park | 1 | 115 |  | 142 |  | TC detail | MN |  | 3.5 | 100 |  |  |  | Planned | 3600000 | [8 empty] | Y | Y | Y
B | 1078 | 2006-10-15 | BR | N-NM | GRE | 600 | 2005-06-15 |  | 2008-06-30 | Baxter | Southdale | 1 | 115 |  | 224 |  | H5 | MN |  | 9 | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | Y | Y
B | 640 | 2004-12-23 | BR | N-NM | GRE | 1018 | 2004-12-23 |  | 2011-06-01 | Little Falls | Pierz (operated 34 kV) | 1 | 115 |  | 196 |  | H5 | MN | 9 |  | 100 |  |  |  | Proposed | 900000 | Planning MISO | [7 empty] | Y | Y | Y
B | 2236 | 2006-10-15 | BR | N-NM | GRE | 1354 | 2006-10-15 | Dotson | 2010-05-01 | Dotson | Searles | 1 | 161 |  | 434 |  |  |  |  | 25 | 50 | 25 | 25 |  | proposed | [9 empty] | Y | Y | Y
B | 2235 | 2006-10-15 | BR | N-NM | GRE | 1354 | 2006-10-15 | Dotson | 2010-05-01 | Dotson | Storden | 1 | 161 |  | 434 |  |  |  |  | 24 | 50 | 25 | 25 |  | proposed | [9 empty] | Y | Y | Y
B | 2239 | 2006-10-15 | TX | N-NM | GRE | 1354 | 2006-10-15 | Dotson | 2010-05-01 | Searles | transformer | 1 | 161 | 115 | 448 | [5 empty] | 50 | 25 | 25 |  | proposed | [9 empty] | Y | Y | Y
B | 801 | 2005-07-19 | BR | N-NM | GRE/XEL | 603 | 2005-06-15 |  | 2011-06-01 | Alexandria | West St. Cloud | 1 | 115 |  | 310 |  | G5-H5 | MN |  | 75 | 100 |  |  |  | Proposed | 36954688 | [8 empty] | Y | Y | Y
B | 1886 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Helena | Lake Marion | 1 | 345 |  | 2066 |  |  | MN |  | 16 |  |  |  |  | Proposed | 12800000 | [8 empty] | Y | Y | Y
B | 1896 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Hazel | Transfomer | 2 | 345 | 230 | 336 |  |  | MN | [6 empty] | Proposed | 4000000 | [8 empty] | Y | Y | Y
B | 1894 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lake Marion | Transfomer | 1 | 345 | 115 | 448 |  |  | MN | [6 empty] | Proposed | 6000000 | [8 empty] | Y | Y | Y
B | 1892 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Brookings County | Transfomer | 2 | 345 | 115 | 448 |  |  | SD | [6 empty] | Proposed | 6000000 | [8 empty] | Y | Y | Y
B | 1891 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Brookings County | Toronto | 1 | 345 |  | 2066 |  |  | SD |  | 20 |  |  |  |  | Proposed | 7000000 | [8 empty] | Y | Y | Y
B | 1890 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Brookings County | Yankee | 2 | 115 |  | 310 |  |  | SD |  | 14 |  |  |  |  | Proposed | 7000000 | [8 empty] | Y | Y | Y
B | 1889 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Hazel | Minnesota Valley | 1 | 345 |  | 2066 |  |  | MN |  | 8 |  |  |  |  | Proposed | 3600000 | [8 empty] | Y | Y | Y
B | 1883 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lyon County | Franklin | 2 | 345 |  | 2066 |  |  | MN |  | 44 |  |  |  |  | Proposed | 17600000 | [8 empty] | Y | Y | Y
B | 1887 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lake Marion | Hampton Corner | 1 | 345 |  | 2066 |  |  | MN |  | 18 |  |  |  |  | Proposed | 14400000 | [8 empty] | Y | Y | Y
B | 1885 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Franklin | Helena | 2 | 345 |  | 2066 |  |  | MN |  | 67 |  |  |  |  | Proposed | 26800000 | [8 empty] | Y | Y | Y
B | 1884 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Franklin | Helena | 1 | 345 |  | 2066 |  |  | MN |  | 67 |  |  |  |  | Proposed | 53600000 | [8 empty] | Y | Y | Y
B | 1898 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Morris | Transfomer | 2 | 230 | 115 | 150 | Upgrade 100 MVA to 150 MVA |  | MN | [6 empty] | Proposed | 4000000 | [8 empty] | Y | Y | Y
B | 1895 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Hazel | Transfomer | 1 | 345 | 230 | 336 |  |  | MN | [6 empty] | Proposed | 6000000 | [8 empty] | Y | Y | Y
B | 1882 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lyon County | Franklin | 1 | 345 |  | 2066 |  |  | MN |  | 44 |  |  |  |  | Proposed | 35200000 | [8 empty] | Y | Y | Y
B | 1881 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Brookings County | Lyon County 345 kV | 1 | 345 |  | 2066 |  |  | SD |  | 49 |  |  |  |  | Proposed | 39200000 | [8 empty] | Y | Y | Y
B | 1888 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lyon County | Hazel | 1 | 345 |  | 2066 |  |  | MN |  | 22 |  |  |  |  | Proposed | 18480000 | [8 empty] | Y | Y | Y
B | 1893 | 2006-01-25 | BR | N-NM | GRE/XEL | 1203 | 2006-01-25 | SW MN - TC EHV | 2011-06-01 | Lyon County | Transfomer | 1 | 345 | 115 | 448 |  |  | MN | [6 empty] | Proposed | 6000000 | [8 empty] | Y | Y | Y
B | 179 | 2003-06-03 | BR | E-MIO | HE | 204 | 2005-06-15 |  | 2009-06-01 | North Charleston | Tapline w/ substation | 1 | 138 |  |  |  | M10 | IN |  | 0.1 | 100 |  |  |  | Proposed | 900000 | [8 empty] | Y | N | Y
B | 171 | 2003-06-03 | BR | E-MIO | HE | 204 | 2005-06-15 |  | 2009-06-01 | Batesville | Tapline w/ substation | 1 | 138 |  |  |  | M10 | IN |  | 0.5 | 100 |  |  |  | Proposed | 950000 | [8 empty] | Y | N | Y
B | 1385 | 2005-01-14 | TX | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345/120 kV (sw sta provisions) | transformer |  | 345 | 120 |  |  | N6 | MI |  |  | 100 |  |  |  | Proposed | 1100000 | [8 empty] | Y | N | Y
B | 1394 | 2005-01-14 | TX | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345/120 kV | transformer | 1 | 345 | 120 | 700 |  | N6 | MI |  |  | 100 |  |  |  | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 1393 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345 kV | Belle River 345 | 1 | 345 |  | 2259 |  | N7 | MI | 16.5 | 4.2 | 100 |  |  |  | Proposed | 6000000 | [8 empty] | Y | N | Y
B | 1392 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345 kV | Pontiac 345 kV | 1 | 345 |  | 1769 |  | N7 | MI | 42.9 |  | 100 |  |  |  | Proposed | 600000 | [8 empty] | Y | N | Y
B | 1391 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345 kV | Greenwood 345 kV | 2 | 345 |  | 2552 |  | N6 | MI |  | 13.4 | 100 |  |  |  | Proposed | 13500000 | [8 empty] | Y | N | Y
B | 1390 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 345 kV | Greenwood 345 kV | 1 | 345 |  | 2241 |  | N6 | MI | 13.4 |  | 100 |  |  |  | Proposed | 600000 | [8 empty] | Y | N | Y
B | 1389 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 120 kV | Burns 2 120 kV | 1 | 120 |  | 313 |  | N7 | MI | 17.7 | 0.6 | 100 |  |  |  | Proposed | 700000 | [8 empty] | Y | N | Y
B | 1388 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 120 kV | Bunce Creek 120 kV | 1 | 120 |  | 313 |  | N6 | MI | 12.5 | 0.6 | 100 |  |  |  | Proposed | 700000 | [8 empty] | Y | N | Y
B | 1386 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 120 kV | Robin 120 kV | 1 | 120 |  | 444 |  | N6 | MI | 23.3 | 0.6 | 100 |  |  |  | Proposed | 700000 | [8 empty] | Y | N | Y
B | 1387 | 2005-01-14 | BR | E-MIO | ITC | 694 | 2005-06-15 | ITC9 | 2009-12-31 | Saratoga 120 kV | Wabash 120 kV | 1 | 120 |  | 299 |  | N6 | MI | 13.6 | 0.6 | 100 |  |  |  | Proposed | 700000 | [8 empty] | Y | N | Y
B | 917 | 2005-07-08 | BR | E-MIO | ITC | 900 | 2005-08-10 | aa | 2008-05-30 | Hager 120 kV | Hines 120 kV | 1 | 120 |  | 347 |  | N7 | MI | 5.4 |  | 100 |  |  |  | Proposed | 1100000 | [8 empty] | Y | N | Y
B | 1379 | 2005-11-28 | BR | E-MIO | ITC | 900 | 2005-08-10 | aa | 2008-12-31 | Coventry 120 kV | Duvall 120 kV | 1 | 120 |  | 200 |  | N7 | MI | 9.1 |  | 100 |  |  |  | Proposed | 750000 | [8 empty] | Y | N | Y
B | 1380 | 2005-11-28 | BR | E-MIO | ITC | 900 | 2005-08-10 | aa | 2008-12-31 | Duvall 120 kV | Hager 120 kV | 1 | 120 |  | 347 |  | N7 | MI | 4.6 |  | 100 |  |  |  | Proposed | 750000 | [8 empty] | Y | N | Y
B | 920 | 2006-07-05 | BR | E-MIO | ITC | 902 | 2005-08-10 | ITC12 | 2008-12-31 | Greenwood 120 kV | Wabash 120 kV | 1 | 120 |  |  |  | N6 | MI | 10.9 | 11.8 | 100 |  |  |  | Proposed | 4000000 | [8 empty] | Y | N | Y
B | 919 | 2006-07-05 | TX | E-MIO | ITC | 902 | 2005-08-10 | ITC12 | 2008-12-31 | Greenwood 345/120 kV | transformer | 2 | 345 | 120 | 700 |  | N6 | MI |  |  | 50 | 50 |  |  | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 921 | 2006-07-05 | BR | E-MIO | ITC | 902 | 2005-08-10 | ITC12 | 2008-12-31 | Greenwood 120 kV | Adams 120 kV | 1 | 120 |  | 222 |  | N6 | MI | 15.7 | 12.7 | 100 |  |  |  | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 924 | 2006-07-05 | BR | E-MIO | ITC | 903 | 2005-08-10 | ITC13 | 2008-12-31 | Stephens 120 kV | Redrun 120 kV | 1 | 120 |  | 343 |  | N7 | MI |  | 5.4 | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 922 | 2006-07-05 | BR | E-MIO | ITC | 903 | 2005-08-10 | ITC13 | 2008-12-31 | Bismark 230 kV | Stephens 230 | 1 | 230 |  | 657 |  | N7 | MI |  | 8.2 | 100 |  |  |  | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 923 | 2006-07-05 | TX | E-MIO | ITC | 903 | 2005-08-10 | ITC13 | 2008-12-31 | Stephens 230/120 kV | Transformer | 1 | 230 | 120 | 693 |  | N7 | MI |  |  | 100 |  |  |  | Proposed | 4000000 | [8 empty] | Y | N | Y
B | 938 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Allen Junction | 1 | 345 |  | 1793 |  |  | MI | 19 | [5 empty] | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 936 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Monroe 3-4 | 1 | 345 |  | 2008 |  |  | MI | 15 | [5 empty] | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 934 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Majestic | 1 | 345 |  | 1195 |  |  | MI | 51 | [5 empty] | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 935 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Milan | 1 | 345 |  | 2241 |  |  | MI | 16 | [5 empty] | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 937 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Lemoyne | 1 | 345 |  | 1536 |  |  | MI | 42 | [5 empty] | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 1579 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lulu | Monroe 1-2 | 1 | 345 |  | 2000 |  |  | MI | 12.1 | 3 |  |  |  |  | Proposed | 4500000 | [8 empty] | Y | N | Y
B | 1580 | 2005-08-10 | BR | E-MIO | ITC | 908 | 2005-08-10 | ii | 2008-05-30 | Lemoyne | Monroe 3-4 | 1 | 345 |  | 2000 |  |  | MI | 33.1 | 3 |  |  |  |  | Proposed | 4500000 | [8 empty] | Y | N | Y
B | 941 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Atlanta Junct. | Atlanta 345 | 1 | 345 |  | 1553 |  |  | MI |  | 2.3 |  |  |  |  | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 945 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Tuscola 230 | Hunters Creek 230 | 1 | 230 |  | 657 |  |  | MI |  | 22.5 |  |  |  |  | Proposed | 500000 | [8 empty] | Y | N | Y
B | 946 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Hunters Creek 345 | Blackfoot 345 | 1 | 345 |  | 2002 |  |  | MI | 20 | [5 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 944 | 2005-07-08 | TX | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Tuscola 230-120 kV | transformer | 1 | 230 | 120 | 557 |  |  | MI | [6 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 947 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Hunters Creek 345 | Belle River 345 | 1 | 345 |  | 2002 |  |  | MI | 45 | [5 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 948 | 2005-07-08 | TX | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Hunters Creek 345-230 kV | transformer | 1 | 345 | 230 | 665 |  |  | MI | [6 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 949 | 2005-07-08 | TX | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Hunters Creek 230-120 kV | transformer | 1 | 230 | 120 | 557 |  |  | MI | [6 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 942 | 2005-07-08 | TX | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Atlanta 345-230 kV | transformer | 1 | 345 | 230 | 665 |  |  | MI | [6 empty] | Proposed | 5000000 | [8 empty] | Y | N | Y
B | 939 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Atlanta Junct. | Hampton | 1 | 345 |  | 1554 |  |  | MI | 16 | [5 empty] | Proposed | 500000 | [8 empty] | Y | N | Y
B | 940 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Atlanta Junct. | Thetford | 1 | 345 |  | 1554 |  |  | MI | 22 | [5 empty] | Proposed | 500000 | [8 empty] | Y | N | Y
B | 943 | 2005-07-08 | BR | E-MIO | ITC | 909 | 2005-08-10 | jj | 2010-05-30 | Atlanta 230 | Tuscola 230 | 1 | 230 |  | 657 |  |  | MI |  | 13.6 |  |  |  |  | Proposed | 13500000 | [8 empty] | Y | N | Y
B | 951 | 2006-07-05 | TX | E-MIO | ITC | 910 | 2005-08-10 | ITC20 | 2007-12-31 | Cody 230/120 kV | transformer | 1 | 230 | 120 | 693 |  | N7 | MI |  |  | 100 |  |  |  | Planned | 4000000 | [8 empty] | Y | N | Y
B | 950 | 2006-07-05 | TX | E-MIO | ITC | 910 | 2005-08-10 | ITC20 | 2007-12-31 | Coventry 345/230 | transformer | 1 | 345 | 230 | 782 |  | N7 | MI |  |  | 100 |  |  |  | Planned | 5000000 | [8 empty] | Y | N | Y
B | 1581 | 2006-07-05 | BR | E-MIO | ITC | 910 | 2005-08-10 | ITC20 | 2007-12-31 | Madrid 345 kV | Blackfoot 345 kV | 1 | 345 |  | 1793 |  | N7 | MI | [6 empty] | Planned | 3000000 | Planning MISO | [7 empty] | Y | N | Y
B | 952 | 2006-07-05 | BR | E-MIO | ITC | 910 | 2005-08-10 | ITC20 | 2007-12-31 | Coventry 230 kV | Cody 230kV | 1 | 230 |  | 657 |  | N7 | MI | 6.6 |  | 100 |  |  |  | Planned | 8000000 | [8 empty] | Y | N | Y
B | 1584 | 2006-07-05 | BR | E-MIO | ITC | 1011 | 2006-07-05 | ITC22 | 2006-12-31 | Placid 120 kV | Durant 120 kV | 1 | 120 |  | 343 |  | N7 | MI | 16.7 |  | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | N | Y
B | 1583 | 2006-07-05 | BR | E-MIO | ITC | 1011 | 2006-07-05 | ITC22 | 2006-12-31 | Genoa 120 kV | Durant 120 kV | 1 | 120 |  | 343 |  | N7 | MI |  | 8.5 | 100 |  |  |  | Planned | 5500000 | [8 empty] | Y | N | Y
B | 1585 | 2006-07-05 | BR | E-MIO | ITC | 1011 | 2006-07-05 | ITC22 | 2006-12-31 | Placid 120 kV | Proud 120 kV | 1 | 120 |  | 343 |  | N7 | MI | 14.3 |  | 100 |  |  |  | Planned | 3500000 | [8 empty] | Y | N | Y
B | 1582 | 2005-08-10 | BR | E-MIO | ITC | 1012 | 2005-08-10 | zz | 2007-05-30 | Wayne 120 kV | Newburg 120 kV | 3 | 120 | 120 | 343 |  |  | MI |  | 2.8 |  |  |  |  | Proposed | 1200000 | [8 empty] | Y | N | Y
B | 2124 | 2006-08-28 | BR | East | ITC | 1295 | 2006-08-28 |  | 2010-06-30 | Quaker 120 | Southfield 120 | 1 | 120 |  | 183/232 | new line |  | MI |  | 7.35 | 100 |  |  |  | Proposed | [9 empty] | Y | N | Y
B | 2133 | 2006-08-16 | SUB | E-MIO | ITC | 1302 | 2006-08-16 | ITC24 | 2007-05-31 | Hines 120 kV | substation equipment |  | 120 |  | 642 | station equipment replacement | N7 | MI | [6 empty] | Planned | 750000 | [8 empty] | Y | N | Y
B | 2134 | 2006-08-16 | SUB | E-MIO | ITC | 1302 | 2006-08-16 | ITC24 | 2007-05-31 | Walton 120 kV | substation equipment |  | 120 |  | 635 | station equipment replacement | N6 | MI | [6 empty] | Planned | 750000 | [8 empty] | Y | N | Y
B | 2135 | 2006-08-16 | BUS | E-MIO | ITC | 1303 | 2006-08-16 | ITC25 | 2007-05-31 | Arrowhead 120 kV | ring bus |  | 120 |  |  | new ring bus configuration | N7 | MI | [6 empty] | Planned | 4000000 | [8 empty] | Y | N | Y
B | 2140 | 2006-08-16 |  | E-MIO | ITC | 1308 | 2006-08-16 | ITC30 | 2006-12-31 | Bunce Creek 220 kV | Scott 220 kV | 1 | 220 |  |  |  | N7 | MI | 4.5 | [5 empty] | Planned | 500000 | [8 empty] | Y | N | Y
B | 2141 | 2006-08-16 |  | E-MIO | ITC | 1308 | 2006-08-16 | ITC30 | 2007-12-31 | Bunce Creek PAR |  | 1 | 220 |  |  |  | N7 | MI | [6 empty] | Planned | 25000000 | [8 empty] | Y | N | Y
B | 541 | 2005-08-31 | BR | N-Nebraska | LES | 247 | 2005-06-15 | TRN.610.06 | 2008-12-31 | Wagener | NW68th & Holdrege | 1 | 345 |  | 956 | New Line | F9 | NE |  | 26 | 100 |  |  |  | Planned | 28077000 | Planning |  | Y | [5 empty] | Y | Y | Y
B | 805 | 2005-07-08 | TX | N-Nebraska | LES | 805 | 2006-09-29 | TRN.601.03 | 2010-05-01 | NW68th & Holdrege 345/115 kV | transformer | 2 | 345 | 115 | 336 MVA | New Transformer | F9 | NE |  |  | 100 |  |  |  | Proposed | 3300000 | Planning |  | N | [5 empty] | Y | Y | Y
B | 2317 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | Sheldon | SW7th & Old Cheney | 2 | 115 |  | 145 MVA |  | F9 | NE | 0 |  |  |  |  | 100 | Planned | 0 | MISO planning |  | N | [5 empty] | Y | Y | Y
B | 2321 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | 20th & Pioneers | 3rd & Van Dorn | 1 | 115 |  | 145 MVA |  | F9 | NE | 1.3 |  |  |  |  | 100 | Planned | 260000 | MISO planning |  | N | [5 empty] | Y | Y | Y
B | 2316 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | Sheldon | SW7th & Old Cheney | 1 | 115 |  | 363 MVA |  | F9 | NE | 16.5 |  |  |  |  | 100 | Planned | 3300001 | Planning |  | N | [5 empty] | Y | Y | Y
B | 2318 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | SW7th & Old Cheney | Rokeby | 1 | 115 |  | 373 MVA |  | F9 | NE | 0.6 |  |  |  |  | 100 | Planned | 120000 | MISO planning |  | N | [5 empty] | Y | Y | Y
B | 2319 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | SW7th & Old Cheney | 20th & Pioneers | 1 | 115 |  | 373 MVA |  | F9 | NE | 3 |  |  |  |  | 100 | Planned | 600000 | MISO planning |  | N | [5 empty] | Y | Y | Y
B | 2320 | 2006-10-10 | BR | N-Nebraska | LES | 1381 | 2006-10-10 | TRN.450.00 | 2011-05-01 | 20th & Pioneers | 2nd & N | 1 | 115 |  | 145 MVA |  | F9 | NE | 1.3 |  |  |  |  | 100 | Planned | 260000 | MISO planning |  | N | [5 empty] | Y | Y | Y
B | 2242 | 2006-10-15 | BR | N-NM | MDU | 1355 | 2006-10-15 |  | 2009-11-01 | Heskett | Additional 230/115 kV Switchyard |  | 230 | 115 | 200 MVA | Switchyard in parallel w/ existing Heskett switchyard |  | ND | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 2241 | 2006-10-15 | CAP | N-NM | MDU | 1355 | 2006-10-15 |  | 2009-11-01 | Heskett | Capacitor |  | 115 |  | 30 MVAr |  |  | ND | [6 empty] | Planned | [9 empty] | Y | Y | Y
B | 2243 | 2006-10-15 | DV | N-NM | MDU | 1356 | 2006-10-15 |  | 2009-11-01 | Glenham | Reactors |  | 230 | 115 | TBD | Control high voltage on WAPA Bismarck - Oahe 230 kV line |  | ND | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 336 | 2006-03-16 | BR | E-MIO | METC | 240 | 2005-07-27 | 87 | 2011-06-01 | Garfiled | Hemphill | 1 | 138 |  | 521 |  | N7 | MI | 9.2 |  | 100 |  |  |  | Proposed | 1900000 | [8 empty] | Y | N | Y | METC_2011Sum_U2_8-12-2005_29.idv
B | 1317 | 2006-09-29 | BR | E-MIO | METC | 494 | 2006-09-29 | 58 | 2007-12-01 | Battle Creek | Verona(Sag) | 2 | 138 |  |  |  | M7 | MI | 1 |  | 100 |  |  |  | Proposed | 50000 | [8 empty] | Y | N | Y
B | 1326 | 2006-09-29 | BR | East | METC | 643 | 2006-09-29 | 60 | 2007-03-01 | Gaines | Thompson Road | 1 | 138 |  |  |  | M7 | MI | 15 |  | 100 |  |  |  | Under Construction | 1425000 | [8 empty] | Y | N | Y
B | 1333 | 2005-07-27 | BR | E-MIO | METC | 648 | 2005-07-27 | 75 | 2007-06-01 | METC | Various Distribution Connections | 1 | 138 |  |  |  | Various | MI |  | 1 | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 1339 | 2005-07-27 | BR | E-MIO | METC | 653 | 2005-07-27 | 88 | 2008-06-01 | METC | Various Distribution Connections | 1 | 138 |  |  |  | Various | MI |  | 1 | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 1351 | 2005-07-27 | BR | E-MIO | METC | 663 | 2005-07-27 | 105 | 2009-06-01 | METC | Various Distribution Connections | 1 | 138 |  |  |  | Various | MI |  | 1 | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 1435 | 2006-07-05 | BR | East | METC | 740 | 2006-07-05 | 45 | 2007-03-01 | Keystone | Livingston | 1 | 345 |  |  | relaying & communications | M5 | MI | 0 |  |  |  |  | 100 | Planned | 1000000 | [8 empty] | Y | N | Y
B | 1436 | 2006-07-05 | BR | East | METC | 740 | 2006-07-05 | 46 | 2007-03-01 | Livingston | Gallagher | 1 | 345 |  |  | relaying & communications | M5 | MI | 0 |  |  |  |  | 100 | Planned | 794000 | [8 empty] | Y | N | Y
B | 1434 | 2006-07-05 | BR | East | METC | 740 | 2006-07-05 | 44 | 2007-03-01 | Gallagher | Tittabawassee | 1 | 345 |  |  | relaying & communications | M5 | MI | 0 |  |  |  |  | 100 | Planned | 1000000 | [8 empty] | Y | N | Y
B | 3084 | 2005-07-27 | CAP | E-MIO | METC | 776 | 2005-07-27 | 76 | 2007-06-01 | Various | Capacitors |  | 138 |  | 72 Mvar |  | various | MI | 0 |  | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 3085 | 2005-07-27 | CAP | E-MIO | METC | 777 | 2005-07-27 | 89 | 2008-06-01 | Various | Capacitors |  | 138 |  | 72 Mvar |  | various | MI | 0 |  | 100 |  |  |  | Proposed | 2000000 | [8 empty] | Y | N | Y
B | 1547 | 2005-07-27 | BR | E-MIO | METC | 984 | 2005-07-27 | 114 | 2011-06-01 | Denver Station | New Station |  | 345 |  |  | New Station |  | MI | [6 empty] | Proposed | 77132000 | Planning MISO | [7 empty] | Y | N | Y
B | 1551 | 2006-10-26 | LN | E-MIO | METC | 988 | 2005-07-27 | 120 | 2011-06-01 | Simpson | Batavia | 1 | 138 |  |  |  |  | MI |  | 30 |  |  |  |  | Planned | 13000000 | [8 empty] | Y | N | Y
B | 2412 | 2006-10-25 | TX | East | METC | 1409 | 2006-10-25 | 159 | 2007-06-01 | Tittabawasee 345kV | System Spare Transformer |  | 345 | 138 |  | Install spare system 345/138kV transformer |  | MI | [6 empty] | Planned | 2600000 | [8 empty] | Y | N | Y
B | 2437 | 2006-10-25 | SUB | East | METC | 1433 | 2006-10-25 | 181 | 2008-06-01 | Beals 138kV | Hazelwood 138kV | 1 | 138 |  |  | Install bulk substation served from the Beals-Hazelwood 138kV Line (Buskirk) |  | MI | [6 empty] | Proposed | 2200000 | [8 empty] | Y | N | Y
B | 2438 | 2006-10-25 | SUB | East | METC | 1434 | 2006-10-25 | 182 | 2008-06-01 | Spaulding 138kV |  |  | 138 |  |  | Install bulk substation served from the Spaulding 138kV ring bus (Five Mile) |  | MI | [6 empty] | Proposed | 750000 | [8 empty] | Y | N | Y
B | 2445 | 2006-10-25 | SUB | East | METC | 1441 | 2006-10-25 | 189 | 2009-06-01 | Sternberg 138kV |  |  | 138 |  |  | Install bulk substation served from a new Ellis spur from Sternberg (Ellis/Hile Rd) |  | MI | [6 empty] | Proposed | 3250000 | [8 empty] | Y | N | Y
B | 2449 | 2006-10-25 | Dist | East | METC | 1445 | 2006-10-25 | 193 | 2010-06-01 | Emmet 138kV | distribution |  | 138 |  |  | Install a second distribution transformer at Emmet (Emmet) |  | MI | [6 empty] | Proposed | 2750000 | [8 empty] | Y | N | Y
B | 2451 | 2006-10-25 | SUB | East | METC | 1447 | 2006-10-25 | 195 | 2010-06-01 | Eureka 138kV | Vestaburg 138kV | 1 | 138 |  |  | Install bulk substation served from the Eureka-Deja-Vestaburg 138kV Line (Horseshoe Creek/Deja) |  | MI | [6 empty] | Proposed | 2200000 | [8 empty] | Y | N | Y
B | 1100 | 2005-07-11 | BR | N-NM | MH | 291 | 2006-03-24 | 291 | 2011-11-01 | Loon Straights | Bloodvein | 1 | 115 |  | 93 | Replacement/new of existing 66 kV to 115 kV | Manitoba | Manitoba | 54.9 | 34 | 100 |  |  |  | Proposed | 18665777.6452 | Engineering | [7 empty] | Y | Y | Y
B | 1101 | 2005-07-11 | BR | N-NM | MH | 291 | 2006-03-24 | 291 | 2011-11-01 | Pine Falls | Loon Straights | 1 | 115 |  | 93 | Replacement/new of existing 66 kV to 115 kV | Manitoba | Manitoba |  | 10.7 |  | 100 |  |  | Proposed | 4441382.3732 | Engineering | [7 empty] | Y | Y | Y
B | 239 | 2006-03-24 | BR | N-NM | MH | 604 | 2006-03-24 | 604 | 2006-11-01 | Herblet Lake | Sherridon | 1 | 115 |  | 63 | Upgrade of old line | Manitoba | Manitoba | 45.3 |  |  |  |  | 100 | Proposed | 7835115.4839 | Engineering | [7 empty] | Y | Y | Y
B | 1240 | 2006-03-24 | BR | N-NM | MH | 604 | 2006-03-24 | 604 | 2008-03-01 | Herblet Lake | Chisel Lake | 1 | 115 |  | 98 | New transmission to feed load | Manitoba | Manitoba |  | 3.7 | 100 |  |  |  | Proposed | 3628560.1755 | Engineering | [7 empty] | Y | Y | Y
B | 959 | 2005-07-11 | BR | N-NM | MH | 912 | 2006-06-28 | 2 | 2010-05-01 | Point du Bois | Rover | 1 | 115 |  | 125 | replacing two existing old 66 kV lines | Manitoba | Manitoba | 75 |  |  | 100 |  |  | Proposed | 24803532.3607 | Engineering | [7 empty] | Y | Y | Y
B | 958 | 2006-10-15 | TX | N-NM | MH | 915 | 2006-06-28 | 5 | 2007-04-30 | Rosser 230-115 kV | transformer | 2 | 230 | 115 | 250 | transformer upgrade 176 to 250 mva | F2 | Manitoba |  |  | 100 |  |  |  | Proposed | 2464590.26 | Engineering | [7 empty] | Y | Y | Y
B | 963 | 2006-10-15 | BR | N-NM | MH | 917 | 2006-06-28 | 7 | 2007-03-31 | Mohawk | Harrow | 1 | 115 |  | 80 | Reconfigure line (originally XS49) | Manitoba | Manitoba | 0 |  | 100 |  |  |  | Proposed | 286288.45 | Engineering | [7 empty] | Y | Y | Y
B | 961 | 2006-06-28 | BR | N-NM | MH | 917 | 2006-06-28 | 7 | 2007-03-31 | LaVerendrye(YV5) | St Vital | 1 | 115 |  | 178.9 | Reconductor section of line | Manitoba | Manitoba |  | 1.88 | 100 |  |  |  | Proposed | 198176.12 | Engineering | [7 empty] | Y | Y | Y
B | 962 | 2006-10-15 | BR | N-NM | MH | 917 | 2006-06-28 | 7 | 2007-03-31 | St Vital | Scotland | 1 | 115 |  | 110 | Reconfigure line (originally VH2) | Manitoba | Manitoba | 0 |  | 100 |  |  |  | Proposed | 198176.12 | Engineering | [7 empty] | Y | Y | Y
B | 955 | 2005-07-11 | BR | N-NM | MH | 1013 | 2006-06-28 | 1 | 2011-10-31 | Neepawa | Dorsey | 1 | 230 |  | 432 | Sectionalize line to feed new 230 - 66 kV station | Manitoba | Manitoba | 0 |  | 100 |  |  |  | Proposed | 16462591.9541 | Engineering | [7 empty] | Y | Y | Y
B | 954 | 2005-07-11 | BR | N-NM | MH | 1013 | 2006-06-28 | 1 | 2011-10-31 | Neepawa | Cornwallis | 1 | 230 |  | 432 | Sectionalize line to feed new 230 - 66 kV station | Manitoba | Manitoba | 0 |  | 100 |  |  |  | Proposed | 16462591.9541 | Engineering | [7 empty] | Y | Y | Y
B | 2115 | 2006-08-24 | DV | N-NM | MP | 1286 | 2006-08-24 | 8 | 2007-06-01 | Two Harbors |  |  | 115 |  | 15 Mvar |  |  | MN | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 2123 | 2006-08-24 | BR | N-NM | MP | 1292 | 2006-08-24 | 14 | 2011-06-01 | ETCO | Forbes | 1 | 115 |  | 122/134 | Increase ground clearance |  | MN | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 2260 | 2006-10-15 | CAP | N-NM | MP | 1359 | 2006-10-15 | a11 | 2007-06-30 | International Falls | Capacitor |  | 115 |  | 1x20 Mvar | add new | a11 | MN |  |  | 100 |  |  |  | Proposed | 245000 | Planning | [7 empty] | Y | Y | Y
B | 2261 | 2006-10-15 | CAP | N-NM | MP | 1360 | 2006-10-15 | b12 | 2007-12-30 | Two Harbors | Capacitor |  | 115 |  | 1x27 Mvar | add new | b12 | MN |  |  | 100 |  |  |  | Proposed | 350000 | Planning | [7 empty] | Y | Y | Y
B | 579 | 2006-10-15 | BR | N-NM | MP/GRE | 277 | 2005-06-15 |  | 2008-06-30 | Pine River | Pequot Lakes | 1 | 115 |  | 182 |  | H4 | MN |  | 8.9 | 100 |  |  |  | Planned | [9 empty] | Y | Y | Y
B | 1590 | 2005-08-29 | BR | N-NM | MP/GRE | 1021 | 2005-08-29 |  | 2008-11-01 | Embarrass 115 | Tower 115 | 1 | 115 |  | 182 | New 115 kV line |  | MN |  | 15 | 100 |  |  |  | Proposed | 7314000 | Planning MISO | [7 empty] | Y | Y | Y
B | 1591 | 2005-08-29 | BR | N-NM | MP/GRE | 1022 | 2005-08-29 |  | 2009-11-01 | Badoura 115 | Long Lake 115 | 1 | 115 |  | 182 | New 115 kV line |  | MN |  | 17 | 100 |  |  |  | Proposed | 8621000 | Planning MISO | [7 empty] | Y | Y | Y
B | 2263 | 2006-10-15 | BR | N-NM | MP/GRE | 1361 | 2006-10-15 |  | 2008-06-30 | Badoura | Pine River | 1 | 115 |  | 182 |  | H4 | MN |  | 19.8 | 100 |  |  |  | Planned | [9 empty] | Y | Y | Y
B | 2264 | 2006-10-15 | BR | N-NM | MP/GRE | 1361 | 2006-10-15 |  | 2009-06-30 | Badoura | Birch Lake | 1 | 115 |  | 182 |  | H4 | MN |  | 16.03 | 100 |  |  |  | Planned | [9 empty] | Y | Y | Y
B | 1279 | 2006-10-03 | TX | E-MIO | NIPS | 612 | 2006-10-03 | 9325101 | 2008-05-01 | Hiple | transformer | 2 | 345 | 138 | 560 | Add 2nd 345/138 kV Transformer | M8 | IN |  |  | 100 |  |  |  | Proposed | 3992400 | Planning w AFUDC | [7 empty] | Y | N | Y
B | 971 | 2006-10-03 | BR | E-MIO | NIPS | 922 | 2006-10-03 | 71C6331 | 2007-05-01 | Michigan City | Luchtman Road | 1 | 138 |  | 316 | Upgrade circuit capacity |  | IN | 5 |  | 100 |  |  |  | Proposed | 1705400 | Engineering w AFUDC | [7 empty] | Y | N | Y
B | 1530 | 2006-10-15 | DV | N-NM | OTP | 549 | 2005-07-29 |  | 2008-01-01 | Jamestown | Reactor |  | 115 |  | 25 Mvar | Add a 1 x 25 MVAr reactor at OTP Jamestown substation | E4 | ND |  |  | 100 |  |  |  | Proposed | 436672 | Planning | [7 empty] | Y | Y | Y
B | 235 | 2006-03-27 | TX | N-NM | OTP/MPC | 971 | 2005-07-29 | OTP1 | 2010-12-31 | Winger 230-115 kV | transformer | 1 | 230 | 115 | 187 | Final Design not yet complete - Either add a 2nd 230/115 kV TX or else replace existing 187 MVA transformer with something larger | G4 | MN |  |  | 100 |  |  |  | Proposed | 3715350.8388 | Planning | [7 empty] | Y | Y | Y
B | 1970 | 2006-10-31 | BR | E-IOK | Vectren | 1007 | 2006-06-29 | 5.1 5.2 | 2009-12-31 | Culley | Duff | 11 | 345 |  | 1430/1430 | new line | L11 | IN |  | 33 |  |  | 50 | 50 | Planned | 24750000 | Budgetary | [7 empty] | Y | N | Y
B | 1575 | 2006-10-31 | BR | E-IOK | Vectren | 1007 | 2006-06-29 | 5.3 | 2009-12-31 | Culley 345/138 kV | transformer | 1 | 345 | 138 | 448/470 | New 345 bus & transformer | L11 | IN |  |  |  |  | 50 | 50 | Planned | 8400000 | Budgetary | [7 empty] | Y | N | Y
B | 1574 | 2006-10-31 | BR | E-IOK | Vectren | 1007 | 2006-06-29 | 5.4 5.5 | 2009-12-31 | Culley | Smith (OMU) | 12 | 345 |  | 1430/1430 | New interconnection to new Owensboro Municipal Station | M11 | IN/KY |  | 20 |  |  | 50 | 50 | Planned | 21750000 | Budgetary | [7 empty] | Y | N | Y
B | 1969 | 2006-10-31 | BR | E-IOK | Vectren | 1023 | 2006-06-29 | 3.7 | 2009-05-31 | Blue Grass | Elliott | 74 | 138 |  | 287/287 | new line | L11 | IN |  | 6 | 50 |  |  | 50 | Planned | 3900000 | Budgetary | [7 empty] | Y | N | Y
B | 1904 | 2006-02-10 | Bus | E-MIO | WPSC | 1209 | 2006-02-10 | 2007-01 | 2007-08-01 | Hersey | Bus Upgrade |  | 69 |  |  | Convert Single Bus to Ring Bus |  | MI |  |  | 100 |  |  |  | Proposed | 2300000 | Planning | [7 empty] | Y | N | Y
B | 1905 | 2006-02-10 | CB | E-MIO | WPSC | 1210 | 2006-02-10 | 2007-02 | 2007-08-01 | Lewiston | Breaker |  | 69 |  |  | Add Breaker at Lewistion |  | MI |  |  | 100 |  |  |  | Proposed | 520000 | Planning | [7 empty] | Y | N | Y
B | 1906 | 2006-02-10 | BR | E-MIO | WPSC | 1211 | 2006-02-10 | 2007-03 | 2007-08-01 | Grand Traverse | Grawn |  | 69 |  | 102.4 MVA | Rebuild Overloaded Line |  | MI | 5.21 |  | 100 |  |  |  | Proposed | 1200000 | Planning | [7 empty] | Y | N | Y
B | 1907 | 2006-02-10 | BR | E-MIO | WPSC | 1212 | 2006-02-10 | 2007-04 | 2007-08-01 | Alpine | Gaylord |  | 69 |  | 41.2 MVA | Rerate Overloaded Line |  | MI | 3.41 |  | 100 |  |  |  | Proposed | 400000 | Planning | [7 empty] | Y | N | Y
B | 1908 | 2006-02-10 | DV | E-MIO | WPSC | 1213 | 2006-02-10 | 2007-05 | 2007-08-01 | Vestaburg | 6MVAR cap. Bank |  | 69 |  |  | Add 6MVAR at Vestaburg Sub. |  | MI |  |  | 100 |  |  |  | Proposed | 3000 | Planning | [7 empty] | Y | N | Y
B | 1909 | 2006-02-10 | BR | E-MIO | WPSC | 1214 | 2006-02-10 | 2008-01 | 2008-08-01 | Garfield | Grawn |  | 69 |  | 102.4 MVA | Rebuild Overloaded Line |  | MI | 7.68 |  | 100 |  |  |  | Proposed | 1700000 | Planning | [7 empty] | Y | N | Y
B | 1910 | 2006-02-10 | BR | E-MIO | WPSC | 1215 | 2006-02-10 | 2008-02 | 2008-08-01 | Advance | Wilson |  | 69 |  | 41.2 MVA | Rerate Overloaded Line |  | MI | 4.7 |  | 100 |  |  |  | Proposed | 200000 | Planning | [7 empty] | Y | N | Y
B | 1911 | 2006-02-10 | BR | E-MIO | WPSC | 1216 | 2006-02-10 | 2008-03 | 2008-08-01 | Garfield | Hall Street |  | 69 |  | 41.2 MVA | Rerate Overloaded Line |  | MI | 3.72 |  | 100 |  |  |  | Proposed | 150000 | Planning | [7 empty] | Y | N | Y
B | 1912 | 2006-02-10 | Bus | E-MIO | WPSC | 1217 | 2006-02-10 | 2008-04 | 2008-08-01 | Grawn | Bus Upgrade |  | 69 |  |  | Convert Single Bus to Ring Bus |  | MI |  |  | 100 |  |  |  | Proposed | 1900000 | Planning | [7 empty] | Y | N | Y
B | 1913 | 2006-02-10 | Bus | E-MIO | WPSC | 1218 | 2006-02-10 | 2009-01 | 2009-08-01 | Atlanta | Bus Upgrade |  | 69 |  |  | Convert Single Bus to Ring Bus |  | MI |  |  | 100 |  |  |  | Proposed | 1900000 | Planning | [7 empty] | Y | N | Y
B | 1914 | 2006-02-10 | BR | E-MIO | WPSC | 1219 | 2006-02-10 | 2009-02 | 2009-08-01 | Lake County | Star Lake |  | 69 |  | 102.4 MVA | Rebuild Overloaded Line |  | MI | 7.72 |  | 100 |  |  |  | Proposed | 1800000 | Planning | [7 empty] | Y | N | Y
B | 1915 | 2006-02-10 | BR | E-MIO | WPSC | 1220 | 2006-02-10 | 2009-03 | 2009-08-01 | Copemish | Bass Lake |  | 69 |  | 41.2 MVA | Rerate Overloaded Line |  | MI | 28.92 |  | 100 |  |  |  | Proposed | 1200000 | Planning | [7 empty] | Y | N | Y
B | 1916 | 2006-02-10 | BR | E-MIO | WPSC | 1221 | 2006-02-10 | 2010-01 | 2010-08-01 | Redwood | New Era |  | 69 |  | 102.4MVA | Rebuild Overloaded Line |  | MI | 7.54 |  | 100 |  |  |  | Proposed | 1500000 | Planning | [7 empty] | Y | N | Y
B | 1917 | 2006-02-10 | Bus | E-MIO | WPSC | 1222 | 2006-02-10 | 2010-02 | 2010-08-01 | Lake County | Bus Upgrade |  | 69 |  |  | Convert Single Bus to Ring Bus |  | MI |  |  | 100 |  |  |  | Proposed | 3800000 | Planning | [7 empty] | Y | N | Y
B | 1995 | 2006-07-27 | BR | East | WPSC | 1273 | 2006-07-27 | 2007-09 | 2007-10-01 | Alpine | Elmira |  | 69 |  | 43.4/56.4MVA | Rerate overloaded line |  | MI | 3.61 |  | 100 |  |  |  | Proposed | 200000 | Planning | [7 empty] | Y | N | Y
B | 1996 | 2006-07-27 | BR | East | WPSC | 1274 | 2006-07-27 | 2007-10 | 2007-10-01 | Allendale | Blendon |  | 69 |  | 63.2/82.2MVA | Rerate overloaded line |  | MI | 2.11 |  | 100 |  |  |  | Proposed | 150000 | Planning | [7 empty] | Y | N | Y
B | 1997 | 2006-07-27 | BR | East | WPSC | 1275 | 2006-07-27 | 2007-11 | 2007-10-01 | Boyne City | Wilson |  | 69 |  | 43.4/56.4MVA | Rerate overloaded line |  | MI | 3.04 |  | 100 |  |  |  | Proposed | 200000 | Planning | [7 empty] | Y | N | Y
B | 1998 | 2006-07-27 | BR | East | WPSC | 1276 | 2006-07-27 | 2010-04 | 2010-10-01 | Burnips | Goodwin |  | 69 |  | 43.4/56.4MVA | Rerate overloaded line |  | MI | 13.09 |  | 100 |  |  |  | Proposed | 900000 | Planning | [7 empty] | Y | N | Y
B | 1999 | 2006-07-27 | BR | East | WPSC | 1277 | 2006-07-27 | 2011-01 | 2011-10-01 | Wayland | Goodwin |  | 69 |  | 43.4/56.4MVA | Rerate overloaded line |  | MI | 4.58 |  | 100 |  |  |  | Proposed | 350000 | Planning | [7 empty] | Y | N | Y
B | 2000 | 2006-08-04 | CAP | East | WPSC | 1278 | 2006-08-04 | 2007-12 | 2007-10-01 | North Shade | capacitor |  | 69 |  | 6 Mvar | Fix Undervoltage Problem |  | MI |  |  | 100 |  |  |  | Proposed | 150000 | Planning | [7 empty] | Y | N | Y
B | 2129 | 2006-09-01 | BR | East | WPSC | 1299 | 2006-09-01 | 2011-02 | 2011-08-01 | Lake County 138 | Lake County 69 |  | 69 |  | 168MVA | Add 168MV transformer |  | MI | 0 |  | 100 |  |  |  | Proposed | 2600000 | Planning | [7 empty] | Y | N | Y
B | 2166 | 2006-09-07 | BR | East | WPSC | 1311 | 2006-09-07 | 2011-05 | 2011-08-01 | Copemish | Karlin |  | 69 |  | 43.4/56.4 | Rerate overloaded line |  | MI | 0 |  | 100 |  |  |  | Proposed | 1400000 | Planning | [7 empty] | Y | N | Y | Y
B | 2167 | 2006-09-07 | BR | East | WPSC | 1312 | 2006-09-07 | 2011-06 | 2011-08-02 | Grawn | Karlin |  | 69 |  | 43.4/56.4 | Rerate overloaded line |  | MI | 0 |  | 100 |  |  |  | Proposed | 650000 | Planning | [7 empty] | Y | N | Y | Y
B | 2168 | 2006-09-07 | BR | East | WPSC | 1313 | 2006-09-07 | 2011-07 | 2011-08-03 | Baldwin | Plains X |  | 69 |  | 37.8/49.1 | Rerate overloaded line |  | MI | 0 |  | 100 |  |  |  | Proposed | 700000 | Planning | [7 empty] | Y | N | Y | Y
B | 2169 | 2006-09-07 | BR | East | WPSC | 1314 | 2006-09-07 | 2011-08 | 2011-08-04 | Plains X | Star Lake |  | 69 |  | 43.4/56.4 | Rerate overloaded line |  | MI | 0 |  | 100 |  |  |  | Proposed | 700000 | Planning | [7 empty] | Y | N | Y | Y
B | 2170 | 2006-09-07 | BR | East | WPSC | 1315 | 2006-09-07 | 2011-09 | 2011-08-05 | Potter | Grand Traverse |  | 69 |  | 43.4/56.4 | Rerate overloaded line |  | MI | 0 |  | 100 |  |  |  | Proposed | 225000 | Planning | [7 empty] | Y | N | Y | Y
B | 1364 | 2006-07-12 | BR | N-NM | XEL | 675 | 2006-07-12 |  | 2009-06-01 | Westgate | Scott County | 1 | 115 |  | 310 | Upgrade 69 kV to 115 kV | TC detail | MN | 20.1 |  | 100 |  |  |  | Proposed | 14000000 | [7 empty] | 2003 Glen Lake area transmission study | Y | Y | Y
B | 2114 | 2006-08-24 | BR | N-NM | XEL | 1285 | 2006-08-24 | 7 | 2011-06-01 | Glencoe | West Waconia | 1 | 115 |  | 310/341 | Build 18 miles 115 kV line from Glencoe - West Waconia |  | MN | 0 | 18 |  |  |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2127 | 2006-08-24 | DV | N-NM | XEL | 1296 | 2006-08-24 | 16 | 2011-06-01 | LONG LK7 | circuit breaker |  | 115 |  |  | Add a breaker at 5P52 at Long Lake, removes the multi-terminal category B contingency |  | MN | 0 | 0 |  |  |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2126 | 2006-08-24 | BR | N-NM | XEL | 1297 | 2006-08-24 | 15 | 2011-06-01 | Oakwood | Hassan | 1 | 115 |  | 310/341 | Reconductor OAKWOOD7 - MNTCELO7, OAKWOOD7 - HASSAN 115 kV line with 795 ACSS |  | MN | 19 | 0 |  |  |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2125 | 2006-08-24 | BR | N-NM | XEL | 1297 | 2006-08-24 | 15 | 2011-06-01 | Oakwood | Monticello | 1 | 115 |  | 310/341 | Reconductor OAKWOOD7 - MNTCELO7, OAKWOOD7 - HASSAN 115 kV line with 795 ACSS |  | MN | 11.2 | 0 |  |  |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2275 | 2006-10-15 | BR | N-NM | XEL | 1365 | 2006-10-15 |  | 2007-06-01 | Edina | Eden Prairie | 1 | 115 |  | 310 | Reconductor |  | MN | [6 empty] | Planned | [9 empty] | Y | Y | Y
B | 2289 | 2006-10-15 | BR | N-NM | XEL | 1368 | 2006-10-15 | 3 Lakes | 2009-05-01 | Pine Lake | Three Lakes | 1 | 115 |  | - | New substation on existing Pine Lake - Willow River 115 kV line |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2290 | 2006-10-15 | BR | N-NM | XEL | 1368 | 2006-10-15 | 3 Lakes | 2009-05-01 | Three Lakes | Willow River | 1 | 115 |  | - | New substation on existing Pine Lake - Willow River 115 kV line |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2293 | 2006-10-15 | BR | N-NM | XEL | 1370 | 2006-10-15 | RSH | 2009-05-01 | Pine Lake | Rush River | 1 | 161 |  | - | Relocate the 69 kV rush River substation to existing 161 kV line from Pine Lake - Crystal Cave |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2294 | 2006-10-15 | BR | N-NM | XEL | 1370 | 2006-10-15 | RSH | 2009-05-01 | Rush River | Crystal Cave | 1 | 161 |  | - | Relocate the 69 kV rush River substation to existing 161 kV line from Pine Lake - Crystal Cave |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2295 | 2006-10-15 | BR | N-NM | XEL | 1371 | 2006-10-15 |  | 2009-06-01 | Black Dog | Wilson | 1 | 115 |  | 310 | Reconductor |  | MN | [6 empty] | Planned | [9 empty] | Y | Y | Y
B | 2296 | 2006-10-15 | BR | N-NM | XEL | 1372 | 2006-10-15 |  | 2010-06-01 | Glencoe | West Waconia | 1 | 115 |  | 310 | New Line |  | MN | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 2297 | 2006-10-15 | BR | N-NM | XEL | 1373 | 2006-10-15 |  | 2010-06-01 | Ft. Ridgeley | Searles Jc | 1 | 115 |  | 620 | new Line |  | MN | [6 empty] | Proposed | [9 empty] | Y | Y | Y
B | 2300 | 2006-10-15 | BR | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Hazle Creek | Minn Valley | 1 | 115 |  | 310 | New 1115 kV Line |  | MN | [6 empty] | Proposed | 5000000 | Planning MISO | [6 empty] | BRIGO | Y | Y | Y
B | 2301 | 2006-10-15 | SVC | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Hazle Creek | SVC |  | 115 |  |  | New SVC at Hazle Creek |  | MN | [6 empty] | Proposed | 10000000 | Planning MISO | [6 empty] | BRIGO, G287, G349 | Y | Y | Y |  | Net?
B | 2302 | 2006-10-15 | BR | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Lake Yankton | SE Marshall | 1 | 115 |  | 310 | New 115 kV line |  | MN | [6 empty] | Planned | 5000000 | Planning MISO | [6 empty] | BRIGO | Y | Y | Y
B | 2303 | 2006-10-15 | BR | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Nobles | Fenton | 2 | 115 |  | 620 | New 115 kV line |  | MN | [6 empty] | Planned | 8000000 | Planning MISO | [6 empty] | BRIGO, G287 | Y | Y | Y |  | Network
B | 2304 | 2006-10-15 | CAP | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Winnebago Jct | Capacitors |  | 161 |  | 60 MVAR | Capacitor Banks |  | MN | [6 empty] | Planned | 1000000 | Planning MISO | [6 empty] | BRIGO | Y | Y | Y |  | Network
B | 2305 | 2006-10-15 | CAP | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | McLeod | Capacitors |  | 115 |  | 120 MVAR | Capacitor Banks |  | MN | [6 empty] | Planned | 2000000 | Planning MISO | [6 empty] | BRIGO, G287, G349 | Y | Y | Y |  | Network
B | 2299 | 2006-10-15 | BR | N-NM | XEL | 1375 | 2006-10-15 | BRIGO | 2010-06-01 | Yankee | Brookings County | 2 | 115 |  | 310 | New 115 kV line | G7 | MN |  |  |  | 100 |  |  | Planned | 5000000 | Planning MISO | [6 empty] | BRIGO, G349 | Y | Y | Y |  | Network
B | 2308 | 2006-10-15 | BR | N-NM | XEL | 1376 | 2006-10-15 | Poplar Lk | 2011-05-01 | Poplar Lake | Apple River | 1 | 161 |  | - | New sub tap on SCF-APP 161 |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2307 | 2006-10-15 | BR | N-NM | XEL | 1376 | 2006-10-15 | Poplar Lk | 2011-05-01 | St Croix Falls | Poplar Lake | 1 | 161 |  | - | New sub tap on SCF-APP 161 |  | WI | [6 empty] | Proposed | [8 empty] | New Richmond Study | Y | Y | Y
B | 2310 | 2006-10-15 | BR | N-NM | XEL | 1378 | 2006-10-15 |  | 2011-06-01 | West St. Cloud | Granite City | 1 | 115 |  | 620 | Reconductor |  | MN | [6 empty] | Proposed | [8 empty] | St. Cloud Load serving study | Y | Y | Y
B | 1670 | 2005-10-12 | BR | N-NM | XEL/DPC | 1024 | 2005-10-12 | SE MN - SW WI | 2011-12-31 | North La Crosse | North La Crosse Tap | 2 | 161 |  | 304 |  | J6 | WI | 0.5 | 0.5 | 100 |  |  |  | Proposed | 400000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1669 | 2005-10-12 | BR | N-NM | XEL/DPC | 1024 | 2005-10-12 | SE MN - SW WI | 2011-12-31 | North La Crosse | North La Crosse Tap | 1 | 161 |  | 304 |  | J6 | WI | 0.5 | 0.5 | 100 |  |  |  | Proposed | 400000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1678 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | SE MN - SW WI | 2011-12-31 | North Rochester | Chester | 1 | 161 |  | 302 | new line | I6 | MN |  | 18 | 100 |  |  |  | Proposed | 9000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1677 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | SE MN - SW WI | 2011-12-31 | North Rochester | Northern Hills | 1 | 161 |  | 302 | new line | I6 | MN |  | 2 | 100 |  |  |  | Proposed | 1000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1676 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | CAPX Group 1 | 2011-12-31 | North La Crosse |  | 1 | 345 | 161 | 448 | new transformer | J6 | WI |  |  | 100 |  |  |  | Proposed | 9000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1675 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | CAPX Group 1 | 2011-12-31 | North Rochester |  | 1 | 345 | 161 | 448 | new transformer | I6 | MN |  |  | 100 |  |  |  | Proposed | 9000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1674 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | CAPX Group 1 | 2011-12-31 | Rochester | North La Crosse | 1 | 345 |  | 1165 | new line | I6 | MN |  | 100 | 100 |  |  |  | Proposed | 82000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
B | 1673 | 2005-10-12 | BR | N-NM | XEL/DPC/RPU | 1024 | 2005-10-12 | CAPX Group 1 | 2011-12-31 | Prairie Island | Rochester | 1 | 345 |  | 1165 | new line | I6 | MN |  | 50 | 100 |  |  |  | Proposed | 41000000 | MISO planning | [6 empty] | SE MN - SW WI | Y | Y | Y
. | 2314 | 2006-10-15 | BR | N-NM | XEL/GRE | 1380 | 2006-10-15 |  | 2010-05-01 | Scott County | West Waconia | 1 | 115 |  | 310 |  |  | MN |  | 25 | 100 |  |  |  | proposed | [9 empty] | Y | Y | Y
B | 1865 | 2006-07-05 | BR | West | ATC LLC |  |  | no Proj | 2008-06-01 | N. Madison | ABS -Yahara |  | 138 |  |  | Uprate of N.Madison-ABS 138kV and ABS-Yahara 138kV lines |  | WI |  |  |  |  | 100 |  | Planned | [8 empty] | A130, A174 | Y | N | Y |  |  | Y
Projects Outside of Plan Year
B | 649 | 2006-10-15 | BR | N-NM | EEI (MP) | 1025 | 2005-08-31 | Mesaba Energy | 2012-05-01 | Mesaba Plant Site | Blackberry | 2 | 345 |  | 1200 | re-energize 230kV circuits at 345kV | I4 | MN | 9 | 0 |  | 100 |  |  | Proposed |  | Planning MISO | [6 empty] | G597 | Y | Y | Y |  | Network
B | 442 | 2006-03-16 | BR | C-WUMS | ATC LLC | 174 | 2005-07-11 |  | 2012-06-01 | Canal | Dunn Road |  | 138 |  | 400 |  | L6 | WI |  | 7.64 | 60 |  | 10 | 30 | Planned | 4200000 | Eng | [7 empty] | Y | N | Y
B | 1249 | 2006-07-05 | BR | C-WUMS | ATC LLC | 568 | 2005-07-11 |  | 2012-06-01 | North Lake Geneva | White River | 1 | 138 |  | 237 | line to new T-D substation | K7 | WI |  | 1.4 | 100 |  |  |  | Proposed | 1250000 |  | Delayed T-D need | [6 empty] | Y | N | Y | ATC zone 3
B | 1372 | 2006-07-05 | BR | C-WUMS | ATC LLC | 682 | 2006-02-17 |  | 2012-06-01 | Huiskamp | Blount (convert) | 1 | 138 |  | 290 | convert 69 to 138 kV | J7 | WI | 5 |  |  |  |  | 100 | Proposed | 20000000 | Eng | [7 empty] | Y | N | Y | ATC zone 3
B | 802 | 2005-01-25 | BR | N-NM | GRE | 602 | 2005-06-15 |  | 2012-06-01 | Brownton | McLeod | 1 | 115 |  |  |  | H6 | MN |  | 9 | 100 |  |  |  | Planned | 4675000 | [8 empty] | Y | Y | Y
B | 907 | 2006-10-03 | TX | E-MIO | IPL | 897 | 2006-10-03 | IPL-07 | 2012-06-01 | Thompson 345-138 kV | transformer | 1 | 345 | 138 | 500 MVA | New 345/138kV Autotransformer | M9 | IN |  |  | 100 |  |  |  | Proposed | 4500000 | [8 empty] | Y | N | Y
B | 1104 | 2005-11-28 | BR | N-NM | GRE/MPC/XEL/OTP/MP/WAPA | 286 | 2005-07-29 | CAPX Group 1 | 2012-07-01 | Alexandria | Benton County | 1 | 345 |  | 720 | Add a new 345 kV line from Benton County to Alexandria Switching Station | G5 | MN |  | 62.5 | 100 |  |  |  | Proposed | 61069477 | Planning | [7 empty] | Y | Y | Y
B | 1105 | 2005-11-28 | BR | N-NM | GRE/MPC/XEL/OTP/MP/WAPA | 287 | 2005-07-29 | CAPX Group 1 | 2012-07-01 | Maple River | Alexandria | 1 | 345 |  | 720 | Add a new 345 kV line from Alexandria Switching Station to Maple River substation | F4 | MN/ND |  | 100 | 100 |  |  |  | Proposed | 64283661 | Planning | [7 empty] | Y | Y | Y
B | 580 | 2006-09-09 | TX | N-NM | MH | 288 | 2006-03-24 | 288 | 2012-08-01 | Riel Stn 500-230 kV | transformer | 1 | 500 | 230 | 1200 | New station and transformation for future Bipole | F2 | Manitoba |  |  |  | 100 |  |  | Proposed | 2756010.63 | Engineering | [7 empty] | Y | Y | Y
B | 242 | 2005-07-11 | BR | N-NM | MH | 98 | 2006-03-24 | 77 | 2012-11-01 | Ridgeway | Selkirk | 1 | 230 |  | 476 |  | G2 | Manitoba |  | 14.3 | 100 |  |  |  | Proposed | 1654807.7275 | [8 empty] | Y | Y | Y
B | 243 | 2005-07-11 | TX | N-NM | MH | 98 | 2006-03-24 | 77 | 2012-11-02 | Selkirk 230-115 kV | transformer | 1 | 230 | 115 | 250 |  | Manitoba | Manitoba |  |  | 100 |  |  |  | Proposed | 876923.1978 | [8 empty] | Y | Y | Y
B | 2431 | 2006-10-25 | TX | East | METC | 1428 | 2006-10-25 | 176 | 2013-05-01 | Roosevelt 345kV | 345/138kV transformer |  | 345 | 138 |  | Add 345/138kV transformer along with two 345kV breakers |  | MI | [6 empty] | Proposed | 6000000 | [8 empty] | Y | N | Y
B | 2432 | 2006-10-25 | LN | East | METC | 1428 | 2006-10-25 | 176 | 2013-05-01 | Roosevelt 138kV | Black River 138kV |  | 138 |  |  | Install new 3mile 795 ACSS 138kV line from Roosevelt-Black River with a 138kV breaker at each end |  | MI | [6 empty] | Proposed | 10000000 | [8 empty] | Y | N | Y
B | 820 | 2005-07-11 | TX | E-MIO | CIN | 841 | 2005-07-11 | AJ | 2013-06-01 | Westwood Bk1 | transformer | 1 | 345 | 138 | 412.9 | Replace 1200A 138kV equipment with 2000A to allow full xfr rating. | L9 | IN |  |  | 100 |  |  |  | Planned | 554000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
B | 1550 | 2005-07-27 | BR | E-MIO | METC | 987 | 2005-07-27 | 118 | 2013-06-01 | Emmet | Stover | 1 | 138 |  |  |  |  | MI | [6 empty] | Proposed | 10250000 | [8 empty] | Y | N | Y
B | 581 | 2005-07-11 | BR | N-NM | MH | 278 | 2006-03-24 | 273 | 2013-11-01 | Dorsey | Portage South | 2 | 230 |  | 384 |  | F2 | Manitoba |  | 43.5 | 100 |  |  |  | Proposed | 17923199.6774 | [8 empty] | Y | Y | Y
A | 462 | 2006-03-16 | BR | C-WUMS | ATC LLC | 102 | 2006-03-16 | 83 | 2014-06-01 | Cornell | Range Line | 2 | 138 |  | 248 |  | K7 | WI | 2.43 |  |  | 25 |  | 75 | Proposed | 6000000 | Eng | [6 empty] | G014, G093, A130 | Y | N | Y |  | Network | Y
B | 1925 | 2005-11-28 | BR | E-MIO | METC | 1225 | 2005-11-28 | 98 | 2015-05-01 | Thompson Road | Tallman | 1 | 138 |  |  |  | M7 | MI | 19.2 |  | 100 |  |  |  | Proposed | 5000000 | [8 empty] | Y | N | Y
A | 828 | 2005-07-11 | BR | E-MIO | CIN | 853 | 2005-07-11 | AV | 2015-06-01 | West Lafayette | Cumberland Ave | 1 | 138 |  | 306 | 13806 reconductor with 954ACSR 100C 604F6325 | L9 | IN | 2 |  | 100 |  |  |  | Planned | 646000 | Planning MISO |  | Y | [5 empty] | Y | N | Y
B | 2063 | 2006-07-05 | CAP | C-WUMS | ATC LLC | 434 | 2006-10-04 |  | 2015-06-01 | Butternut | Capacitor bank |  | 138 |  | 28.8 Mvar |  | K6 | WI | [5 empty] | 100 | Proposed | 1050000 | Eng | [6 empty] | A130 | Y | N | Y |  |  | Y
B | 2312 | 2006-10-15 | BR | N-NM | XEL | 1379 | 2006-10-15 | P-LS-B-L | 2015-06-01 | Linn Street | Becker | 1 | 115 |  | 310 | Upgrade from 69 kV to 115 kV |  | MN | [6 empty] | Proposed | [8 empty] | Buffalo Area load serving study | Y | Y | Y
B | 2313 | 2006-10-15 | BR | N-NM | XEL | 1379 | 2006-10-15 | P-LS-B-L | 2015-06-01 | Becker | Liberty | 1 | 115 |  | 310 | Upgrade from 69 kV to 115 kV |  | MN | [6 empty] | Proposed | [8 empty] | Buffalo Area load serving study | Y | Y | Y
B | 2311 | 2006-10-15 | BR | N-NM | XEL | 1379 | 2006-10-15 | P-LS-B-L | 2015-06-01 | Pulaski | Linn Street | 1 | 115 |  | 310 | Upgrade from 69 kV to 115 kV |  | MN | [6 empty] | Proposed | [8 empty] | Buffalo Area load serving study | Y | Y | Y
B | 1265 | 2006-07-05 | BR | C-WUMS | ATC LLC | 573 | 2006-07-05 |  | 2016-01-01 | North Madison | West Middleton | 1 | 345 |  | 1200 |  | K7 | WI |  | 20 | 100 |  |  |  | Proposed | 46700000 | Eng | [7 empty] | Y | N | Y
B | 1250 | 2006-07-05 | BR | C-WUMS | ATC LLC | 569 | 2006-10-04 |  | 2016-06-01 | South Lake Geneva | White River | 1 | 138 |  | 355 | line to new T-D substation | K7 | WI |  | 3 | 100 |  |  |  | Proposed | 2500000 | Eng | Delayed need | [6 empty] | Y | N | Y | ATC zone 3
B | 1270 | 2006-07-05 | BR | C-WUMS | ATC LLC | 575 | 2006-10-04 |  | 2016-06-01 | Pulliam (now Bayport) | Suamico | 1 | 138 |  |  |  | K6 | WI |  |  | 100 |  |  |  | Proposed | 3199539 |  | project redefined | [6 empty] | Y | N | Y
B | 1271 | 2006-07-05 | BR | C-WUMS | ATC LLC | 575 | 2006-10-04 |  | 2016-06-01 | Suamico | Sobieski | 1 | 138 |  |  |  | K6 | WI |  |  | 100 |  |  |  | Proposed | 1510893 | [8 empty] | Y | N | Y
B | 1272 | 2006-07-05 | BR | C-WUMS | ATC LLC | 575 | 2006-10-04 |  | 2016-06-01 | Sobieski | Pioneer | 1 | 138 |  |  |  | K6 | WI |  |  | 100 |  |  |  | Proposed | 1510893 | [8 empty] | Y | N | Y
B | 2382 | 2006-10-24 | TX | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Sprague Creek 765/345 kV | transformer | 1 | 765 | 345 | 3040 | New 765/345 kV Xfmr at Sprague Creek | N7 | MI | [6 empty] | Proposed | 25000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2371 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 765 kV | Site A 765 kV | 1 | 765 |  | 4465 | 135 miles of new 765 kV line and new 765 kV Site A Station | N8 | IN/OH |  | 135 |  |  |  |  | Proposed | 530000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2374 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 765 kV | South Canton 765 kV | 1 | 765 |  | 4465 | 170 miles of new 765 kV line | N8 | MI/OH |  | 170 |  |  |  |  | Proposed | 600000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2375 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 345 kV | Majestic 345 kV | 1 | 345 |  | 1828 | Taps the majestic end of the Allen Junction-Maj-Monroe 3 ender | N7 | MI | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2376 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 345 kV | Majestic 345 kV | 2 | 345 |  | 1828 | Taps the Majestic-Milan 345 kV Circuit | N7 | MI | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2377 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 345 kV | Milan 345 kV | 1 | 345 |  | 1828 | Taps the Majestic-Milan 345 kV Circuit | N7 | MI | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2378 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Sprague Creek 345 kV | Blackfoot 345 kV | 1 | 345 |  | 795 | Taps the Blackfoot-Madrid 345 kV Circuit | N7 | MI | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2379 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Sprague Creek 345 kV | Madrid 345 kV | 1 | 345 |  | 795 | Taps the Blackfoot-Madrid 345 kV Circuit | N7 | MI | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2373 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Site A 765 kV | Marysville 765 kV | 1 | 765 |  | 4465 | Taps Current Marysville-Dumont 765 kV line | N8 | IN/OH | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2383 | 2006-10-24 | TX | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 765/345 kV | transformer | 1 | 765 | 345 | 3040 | New 765/345 kV Xfmr at Bridgewater | N7 | MI | [6 empty] | Proposed | 25000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2380 | 2006-10-24 | TX | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Kenowa 765/354 kV | transformer | 1 | 765 | 345 | 3040 | New 765/345 kV Xfmr at Kenowa | M7 | MI | [6 empty] | Proposed | 25000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2384 | 2006-10-24 | TX | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Bridgewater 765/345 kV | transformer | 2 | 765 | 345 | 3040 | New 765/345 kV Xfmr at Bridgewater | N7 | MI | [6 empty] | Proposed | 25000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2370 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Sprague Creek 765 kV | Bridgewater 765 kV | 1 | 765 |  | 4465 | 50 miles of new 765 kV line and new 765 kV Bridgewater Station | N7 | MI |  | 50 |  |  |  |  | Proposed | 225000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2369 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Sprague Creek 765 kV | Denver 765 kV | 1 | 765 |  | 4465 | 100 miles of new 765 kV line and new 765 kV Sprague Creek Station | N7 | MI |  | 100 |  |  |  |  | Proposed | 400000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2368 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Kenowa 765 kV | Denver 765 | 1 | 765 |  | 4465 | 30 miles of new 765 kV line and new 765 kV Denver Station | M6 | MI |  | 30 |  |  |  |  | Proposed | 150000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2367 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Cook 765 kV | Kenowa 765 kV | 1 | 765 |  | 4465 | 100 miles of new 765 kV line and new 765 kV Kenowa Station | M7 | MI |  | 100 |  |  |  |  | Proposed | 400000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2372 | 2006-10-24 | LN | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Site A 765 kV | Dumont 765 kV | 1 | 765 |  | 4465 | Taps Current Marysville-Dumont 765 kV line | M8 | IN/OH | [6 empty] | Proposed | 10000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 2381 | 2006-10-24 | TX | East | ITC/METC | 1382 | 2006-10-24 | The 765 | 2016-12-31 | Denver 765/138 kV | transformer | 1 | 765 | 138 | 1119 | New 765/138 kV Xfmr at Denver | M6 | MI | [6 empty] | Proposed | 25000000 | Planning unit cost | [6 empty] | MTEP06 | Y | N | Y
B | 1334 | 2006-09-29 | BR | E-MIO | METC | 649 | 2005-07-27 | 81 | 2017-05-01 | Argenta | Palisades(Sag) | 1&2 | 345 |  |  | conductor sag | M7 | MI | 0.1 |  | 100 |  |  |  | Proposed | 500000 | [8 empty] | Y | N | Y
B | 1335 | 2006-09-29 | BR | E-MIO | METC | 650 | 2005-07-27 | 72 | 2017-05-01 | Battle Creek | Morrow | 1 | 138 |  |  |  | M7 | MI | 14.4 |  | 100 |  |  |  | Proposed | 3400000 | [8 empty] | Y | N | Y
B | 1350 | 2006-09-29 | BR | E-MIO | METC | 662 | 2005-07-27 | 117 | 2017-05-01 | Weeds Lake 345 | Weeds Lake 138 | 1 | 345 | 138 |  |  | M7 | MI |  | 10 | 100 |  |  |  | Proposed | 13000000 | [8 empty] | Y | N | Y
B | 1336 | 2006-09-29 | BR | E-MIO | METC | 480 | 2006-09-29 | 112 | 2017-06-01 | Brickyard J | Felch Road | 1 | 138 |  |  |  | M7 | MI | 12.8 |  | 100 |  |  |  | Proposed | 3000000 | [8 empty] | Y | N | Y
B | 1325 | 2006-07-05 | BR | East | METC | 642 | 2005-07-27 | 57 | 2017-06-01 | Argenta | Hazelwood(Sag) | 1 | 138 |  |  | conductor sag | M7 | MI | 0.1 |  | 100 |  |  |  | Proposed | 50000 | [8 empty] | Y | N | Y
B | 1329 | 2006-09-29 | BR | E-MIO | METC | 646 | 2005-07-27 | 86 | 2017-06-01 | Edenville J. | Warren | 1 | 138 |  |  |  | M6 | MI | 14.8 |  | 100 |  |  |  | Proposed | 4000000 | [8 empty] | Y | N | Y
B | 2434 | 2006-10-25 | CB | East | METC | 1430 | 2006-10-25 | 178 | 2017-06-01 | Buck Creek 138kV | 138kV Breakers |  | 138 |  |  | Convert 138/46kV substation to a switching station by installing 3 high side 138kV breakers at Buck Creek |  | MI | [6 empty] | Proposed | 4500000 | [8 empty] | Y | N | Y
B | 2435 | 2006-10-25 | LN | East | METC | 1431 | 2006-10-25 | 179 | 2017-06-01 | Vergennes 138kV | Kendrick 138kV |  | 138 |  |  | Build new 16mile 138kV line from Vergennes to Kendrick and puchase Kendrick-Plaster Creek spur |  | MI | [6 empty] | Proposed | 14000000 | [8 empty] | Y | N | Y
B | 2436 | 2006-10-25 | LN | East | METC | 1432 | 2006-10-25 | 180 | 2017-06-01 | Withey Lake 138kV | Twining 138kV |  | 138 |  |  | Rebuild 0.2 miles of Withey Lake-Twining 138kV line |  | MI | [6 empty] | Proposed | 100000 | [8 empty] | Y | N | Y
B | 589 | 2005-07-29 | BR | N-NM | OTP | 585 | 2006-03-27 |  | 2017-06-01 | Pelican Rapids | Pelican Rapids Turkey Plant | 1 | 115 |  | 85 | Convert an existing 41.6 kV line to 115 kV | G4 | MN | 2.5 |  | 100 |  |  |  | Planned | 858869 | Planning | [7 empty] | Y | Y | Y
B | 2255 | 2006-10-15 | DV | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Riel | Synchronous Comp | 1 | 230 |  | 300 |  | F2 | Manitoba |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2246 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa (dc) | Riel (dc) | 1 | 500 |  | 2000 | direct current line | Manitoba | Manitoba |  | 833 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2247 | 2006-10-15 | DV | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa (dc) | converter | 1 | 500 |  | 2000 | converter | Manitoba | Manitoba |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2248 | 2006-10-15 | DV | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Riel (dc) | converter | 1 | 500 |  | 2000 | converter | F2 | Manitoba |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2249 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 1 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2250 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 2 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2251 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 3 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2252 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 4 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2253 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 5 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2256 | 2006-10-15 | DV | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Riel | SC | 2 | 230 |  | 300 |  | F2 | Manitoba |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2254 | 2006-10-15 | BR | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Conawapa | Henday | 6 | 230 |  | 390 |  | Manitoba | Manitoba |  | 18.8 |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 2257 | 2006-10-15 | DV | N-NM | MH | 1357 | 2006-10-15 | Con-Riel DC | 2017-10-01 | Riel | SC | 3 | 230 |  | 300 |  | F2 | Manitoba |  |  |  | 100 |  |  | Proposed | [9 empty] | Y | Y | Y
B | 1337 | 2006-09-29 | BR | E-MIO | METC | 651 | 2005-07-27 | 83 | 2018-05-01 | Stover | Clearwater | 1 | 138 |  |  |  | M5 | MI | 8.8 |  | 100 |  |  |  | Proposed | 2800000 | [8 empty] | Y | N | Y
B | 103 | 2006-07-05 | TX | C-WUMS | ATC LLC | 89 | 2006-07-05 | 67 | 2018-06-01 | Mill Road (renamed, was Lannon Junction) | transformer |  | 345 | 138 | 500 | transformer | K7 | WI |  |  | 60 |  |  | 40 | Proposed | 29200000 | Eng | [7 empty] | Y | N | Y
B | 894 | 2006-07-05 | TX | C-WUMS | ATC LLC | 341 | 2006-03-16 | newgrp19 | 2018-06-01 | Bark River | transformer |  | 345 | 138 | 500 | transformer | K7 | WI | [5 empty] | 100 | Proposed | 8400000 | Eng | [7 empty] | Y | N | Y
B | 893 | 2006-07-05 | BR | C-WUMS | ATC LLC | 341 | 2006-03-16 | newgrp19 | 2018-06-01 | Concord | Bark River |  | 345 |  | 815 | new line | K7 | WI |  | 19 |  |  |  | 100 | Proposed | 50300000 | Eng | [7 empty] | Y | N | Y
B | 483 | 2006-07-05 | BR | C-WUMS | ATC LLC | 341 | 2006-03-16 | newgrp19 | 2018-06-01 | Rockdale | Concord (rebuild to dbl ckt 138/345) | 1 | 345 |  | 1200 | rebuild to dbl ckt 138/345 | K7 | WI | 22.6 |  |  |  |  | 100 | Proposed | 22200000 | Eng | [7 empty] | Y | N | Y
B | 477 | 2006-07-05 | TX | C-WUMS | ATC LLC | 341 | 2006-03-16 | newgrp19 | 2018-06-01 | Concord 345/138 kV | transformer |  | 345 | 138 | 500 |  | K7 | WI | [5 empty] | 100 | Proposed | 12900000 | Eng | [7 empty] | Y | N | Y
B | 895 | 2006-07-05 | BR | C-WUMS | ATC LLC | 341 | 2006-03-16 | newgrp19 | 2018-06-01 | Bark River | Mill Road |  | 345 |  | 815 | convert 138 to 345 kV | K7 | WI | 11 |  |  |  |  | 100 | Proposed | 800000 | Eng | [7 empty] | Y | N | Y
B | 2433 | 2006-10-25 | LN | East | METC | 1429 | 2006-10-25 | 177 | 2018-06-01 | Barry 138kV | Thompson Road 138kV |  | 138 |  |  | Build new 17mile 138kV line from Barry to Thompson Rd |  | MI | [6 empty] | Proposed | 20000000 | [8 empty] | Y | N | Y
B | 1094 | 2006-03-24 | BR | N-NM | MH | 283 | 2006-03-24 | 283 | 2020-05-30 | Rosser | Oak Point Tap | 1 | 115 |  | 110.1 | new 115-24 kV station with two banks | F2 | Manitoba | 6.6 |  | 100 |  |  |  | Proposed | 940331.2745 | Engineering | [7 empty] | Y | Y | Y
B | 1093 | 2006-03-24 | BR | N-NM | MH | 283 | 2006-03-24 | 283 | 2020-05-30 | Oak Point Tap | Augier | 1 | 115 |  | 110.1 | new 115-24 kV station with two banks | F2 | Manitoba | 6.6 |  | 100 |  |  |  | Proposed | 940331.2745 | Engineering | [7 empty] | Y | Y | Y
B | 1097 | 2006-03-24 | BR | N-NM | MH | 285 | 2006-06-28 | 280 | 2020-11-01 | St. Vital | Steinbach | 1 | 230 |  | 399 |  | F2 | Manitoba |  | 35 | 100 |  |  |  | Proposed | 13653801.9165 | [8 empty] | Y | Y | Y
B | 2366 | 2006-08-24 | BR | WUMS | ATC LLC | 1283 | 2006-08-24 | 5 |  | Tilden | Freeman | 1 | 138 |  | 195/202 | Retap CT at Freeman for new ratings of 195 SN/202 SE |  | WI | [6 empty] | Proposed | 5000 | MISO Planning | [7 empty] | Y | N | Y